|  | MINISTRY OF ENERGY and petroleum Nairobi Republic of Kenya |
| --- | --- |

KENYA OFF-GRID SOLAR ACCESS PROJECT (KOSAP) FOR UNDERSERVED COUNTIES

Component 1: Mini grids for Community Facilities, Enterprises, and Households

Comprehensive Project Report (CPR) FOR THE PROPOSED MKOKONI OFF-GRID SOLAR PROJECT AT COORDINATES 1°58'01.1"S 41°17'43.3"E

# CERTIFICATION

This Comprehensive Project Report (CPR) has been prepared by ESIA /EA Firm of Experts, Centric Africa Ltd, Reg. No.7112 and Norken International Ltd, Reg. No.0181. The report has been written with diligence in accordance with the World Bank Operational Procedures OP, Environmental Safeguards Standards (ESS), the EMCA 1999 (Amended, 2015) and the Environmental and Social Impact Assessment and Audit Regulations, 2003 to bring out the true nature of the intended development. The report was prepared based on the information provided by various stakeholders and village elders at Mkokoni, Lamu County as well as from primary and secondary sources. It is therefore, issued without any prejudice.

We the undersigned, certify that the particulars in this CPR are correct and righteous to the best of our knowledge.

PROPONENT:

Name and Address of Firm of Experts:

| P. O. Box 9882 - 00100 Nairobi, Kenya Tel. 254 020 2248762 Registration No. of Firm of Experts: 0181 | P.O. Box 102081-00101 Nairobi, Kenya Tel. +254718068517 Registration No. of Firm of Experts: 7112 |
| --- | --- |

Signed: ____________________________ 	Date: _____________________

Isaiah B. Kegora

Lead EIA/EA Expert (NEMA Reg. No 1893)

For: Norken International Ltd & Centric Africa Ltd

Name and Address of the Proponent:

Ministry of Energy,

P.O. Box 30582-00100,

Kawi Complex, Nairobi, Kenya

Signed: ____________________________ 		Date: _____________________

Rodney I. Sultani

Project Co-ordinator – KOSAP

Disclaimer:

This ESIA report is strictly confidential to MoE (the Proponent) and any use of the materials thereof should strictly be in accordance with the agreement between the Proponent and the consultants; Norken International Limited and Centric Africa Limited (the Environmental Impact Assessor). It is, however, subject to conditions in the Environmental (Impact Assessment and Audit) Regulations, 2003 under the Kenya Gazette Supplement No. 56 of 13th June 2003

# IST OF TABLES

Figure 1: Project Location	            Source: Google Earth 2021	13

Table 1: Applicable Legal and Policies Statutes	14

Table 1. Summary of World Bank Environmental and Social Safeguards Policies	15

Table 2. Summary of Construction Phase Impacts	19

Table 3. Summary of Operations Phase Impacts	19

Table 4. Summary of Decommissioning Impacts	19

Table 5. ESIA Project Team and Responsibilities	1-23

Table 5. Structure of the ESIA Report	1-30

Figure 4: Proposed site for the Mkokoni Solar Mini-grid project with shrubs and tree vegetation	2-32

Figure 6: Project Components	2-36

Figure 7: Proposed Project Site & Proximity to Consumer Sites	4-46

Table 10: Relevant Enforcement agencies	5-62

Table 12. Summary of World Bank Environmental and Social Safeguards Policies	5-63

Table 20. Impact qualitative scale	8-2

Table 21. Impact Significance	8-3

Figure 8: Receptors within a 1500m radius of project site	8-12

Table 39: Environmental and Social Management Plan During Construction Phase	9-1

Table 40: Environmental and Social Management Plan During Construction Phase	9-4

Table 41: Environmental and Social Management Plan During Operational Phase	9-10

Table 42: Environmental and Social Monitoring During Construction Phase	9-12

Table 43: Environmental and Social Monitoring During Operation Phase	9-16

# LIST OF ACRONYMS

ACRONYM	DEFINITION

ADR		Alternative Dispute Resolution

AoI		Area of Influence

CBOs		Community Based Organizations

CoK		Constitution of Kenya

CDI		County Development Index

CEMP		Construction Environmental Management Plan

C-ESMP	Contraction Environmental and Social Management Plan

CGRCs	County Grievance Redress Committees

CRA		Commission on Revenue Allocation

CSR		Corporate Social Responsibility

CIDP 		County Integrated Development Plan

CPS		Country Partnerships Strategy

DOSHS	Directorate of Occupational Safety and Health Services

EHS		Environment Health and Safety

EIA		Environmental Impact Assessment

EPRA		Energy Petroleum Regulatory Authority

EPT		Energy and Petroleum Tribunal

EPRA		Energy and Petroleum Regulatory Authority

ESI		Electrical Supply Industry

ESIA		Environmental and Social Impact Assessment

ESMF		Environmental and Social Management Framework

ESMP		Environmental and Social Management Plan

ESMMP	Environmental and Social Management and Monitoring Plan

ESMS		Environmental and Social Management Systems

EMCA		Environmental Management and Coordination Act

EMF		Electromagnetic Field

FGD		Focus Group Discussions

GBV		Gender Based Violence

GDC		Geothermal Development Company

GoK		Government of Kenya

HDPE		High Density Poly Ethylene

IAs		Implementing Agencies

IPPs		Independent Power Procedures

IPs		Indigenous Peoples

JV		Joint Venture

KETRACO	Kenya Electricity Transmission Company

KII 		Key Informant Interviews

KOSAP	Kenya Off-Grid Solar Access Project

KPC		Kenya Power Company

LEP		Labour and Employment Plan

LGRCs		Local Grievance Redress committee

LPGs		Liquid Petroleum Gas

MGs		Mini Grids

MOEP		Ministry of Energy Petroleum

MSDS		Material Safety Datasheet

NEMA		National Environmental Management Authority

NGOs 		Non-Governmental Organizations

NLC		National Land Commission

NPS		National Police Service

NTSA		National Transport and Safety Authority

OHS		Occupational Health and Safety

OM		Operation and Maintenance

OP		Operational Policies

PAD		Project Appraisal Document

PAPs		Project Affected Persons

PCU		Project Co-ordination Unit

PPAs		Power Purchase Agreements

PPEs		Personal Protective Equipment

PV		Photo-voltaic

REREC		Rural Electrification and Renewable Energy Corporation

RPF		Resettlement Policy Framework

SA 		Social Assessment

SEA		Strategic Environmental Assessment

SEA/SH	Sexual Exploitation and Abuse and Sexual Harassment

SHS		Solar Home Systems

SIA 		Social Impact Assessment

SOP		Safe Operation Procedure

STDs		Sexually Transmitted Diseases

STI		Science, Technology and Innovation

SMMP		Social Management and Monitoring Plan

ToR		Terms of Reference

VMGF		Vulnerable and Marginalised Groups Framework

VMGs		Vulnerable and marginalized groups

VMGP		Vulnerable and Marginalised Group Plan

WB		World Bank

WMP		Waste Management Plan

WRA		Water Resources Authority

- TABLE OF CONTENTS

CERTIFICATION	ii

IST OF TABLES	iii

LIST OF ACRONYMS	iv

LIST OF PLATES	13

EXECUTIVE SUMMARY	13

LIST OF FIGURES	xxiii

1	INTRODUCTION	1-24

1.1	Context	1-24

1.2	Project Overview	1-25

1.3	Purpose and Scope of Work	1-26

1.4	ESIA Study Team	1-26

1.5	ESIA Methodology	1-29

1.5.1	Screening and Scoping	1-29

1.5.2	Project Description	1-29

1.5.3	Baseline Condition	1-29

1.5.4	Impact Assessment Prediction	1-30

1.5.5	Stakeholder Consultation and Disclosure Requirement for the Project	1-30

1.5.6	Stakeholder Characterization and Identification	1-31

1.5.7	Stakeholder Analysis	1-32

1.5.8	Limitations	1-34

1.6	Layout of the Report	1-34

2	PROJECT DESCRIPTION	2-36

2.1	Introduction	2-36

2.2	Project Location	2-37

2.3	Area of Influence	2-37

2.3.1	Project Footprint Area	2-39

2.3.2	Study Area	2-39

2.4	Project site setting	2-39

2.4.1	Project cost	2-40

2.5	Land Requirement and Procurement Process	2-40

2.5.1	Land Requirement	2-40

2.6	Description of Project Facilities, Components and Activities	2-40

2.6.1	Project Components	2-41

2.6.2	Architecture and Basic Design Specifications	2-42

2.6.3	Project Phases and Activities	2-42

2.7	Resource Requirement	2-43

2.7.1	Workforce Requirement	2-43

2.7.2	Water Requirement and Source	2-43

2.7.3	Raw Material Requirement	2-44

2.7.4	Power Requirement	2-44

2.7.5	Fire Safety and Security	2-44

2.8	Pollution Streams during Construction Phase	2-45

2.8.1	Solid Waste Generation	2-45

2.8.2	Air Emissions	2-46

2.8.3	Waste Generation	2-46

2.8.4	Noise Emissions	2-47

3	BASELINE SETTINGS- ENVIRONMENT AND SOCIAL	3-48

3.1	Study Area	3-48

3.2	Environment Baseline	3-48

3.2.1	Geology and Soil	3-48

3.2.2	Topography	3-48

3.2.3	Hydrogeology and Drainage	3-48

3.2.4	Ground Water Development	3-48

3.3	Ecological Conditions	3-49

3.4	Climatic Conditions	3-50

3.4.1	Community Profile	3-50

3.4.2	Socio-economic status of Study Area	3-52

3.5	Site Selection	3-53

3.6	Power Scenario at Mkokoni	3-54

3.7	Analysis of Alternative	3-54

3.7.1	Alternate Location for Project Site	3-55

3.7.2	Alternate Sources of Energy	3-55

3.7.3	Zero or No Project Alternative	3-56

3.7.4	Analysis of Alternative Construction Materials and Technology	3-56

3.7.5	Conclusion	3-56

4	APPLICABLE AND REGULATORY FRAMEWORK	4-57

4.1	Introduction	4-57

4.2	Kenya Policy Provisions	4-57

4.2.1	Kenya Energy Policy, 2014	4-57

4.2.2	Policy paper on Environment and Development (Sessional Paper No. 6 of 1999)	4-61

4.2.3	National Policy on Water Resources Management and Development, 1999	4-61

4.2.4	Sessional Paper No. 10 of 2014 on the National Environmental Policy, 2014	4-61

4.3	National Legal Framework	4-63

4.3.1	Administrative Framework	4-63

4.4	Relevant statutes	4-64

4.5	Licenses and Permits Required	4-82

4.6	National Administrative Requirements	4-84

4.7	International Safeguard Requirements	4-85

4.7.1	Kenya Off-grid Solar Access Project (KOSAP) Environmental & Social Management Framework, 2017	4-87

4.7.2	Resettlement Policy Framework (RPF)	4-88

4.7.3	Vulnerable and marginalized Groups Framework (VMGF) for KOSAP	4-88

5	STAKEHOLDER ENGAGEMENT	89

5.1	Stakeholder Consultation and Disclosure Requirement for the Project	89

5.2	Stakeholder Characterisation and Identification	89

5.2.1	Stakeholder Mapping	89

5.3	Stakeholder Analysis	91

5.4	Information Shared to The Community Members	92

5.5	Summary of Community Consultation Meeting Leading to Land Identification and GRC Constitution-(screening level)	92

5.5.1	Land for the Project	93

5.5.2	Project Grievance Redress Mechanism	94

5.6	Summary of Community Consultation During the ESIA	96

5.6.1	Focused Group Discussions analysis	97

5.6.2	Positive Comments about the Project from the Participants	102

5.6.3	The identified negative impacts of the project	102

5.6.4	Additional Responses from the Consultant	103

5.6.5	Consent	103

5.6.6	Community Presentation	103

6	IMPACT ASSESSMENT AND MITIGATION MEASURES	104

6.1	Identification of Impacts	104

6.2	Impact Assessment Methodology	104

6.3	Defining Impact	104

6.4	Assessment of Significance	104

6.5	Magnitude of Impact	106

6.6	Sensitivity of Resources and Receptors	106

6.7	Likelihood	107

6.8	Definition of Mitigation Measures	107

6.9	Positive Impacts - Pre-Construction	108

6.10	Positive Impacts During Construction Phase	108

6.10.1	Creation of Employment Opportunities	108

6.10.2	Improving local economy	108

6.11	Positive Impacts during Operation Phase	109

6.11.1	Quality, Reliable Power Supply	109

6.11.2	Employment Creation	109

6.11.3	Reduction of Pollution Associated with Thermal Power Generation, Kerosene and Wood Fuel Usage:	110

6.11.4	Improvement of Local and National Economy	110

6.11.5	Education	110

6.11.6	Health Benefits of the Project	111

6.11.7	Improved Standard of Living	111

6.11.8	Security	111

6.11.9	Communications	111

6.12	Positive Impacts during Decommissioning Phase	111

6.12.1	Employment Opportunities	111

6.12.2	Site Rehabilitation	111

6.13	Negative Impacts during Pre-construction Phase	112

6.13.1	Land Take	112

6.14	Negative Impacts During Construction Phase	112

6.14.1	Vegetation Clearance	112

6.14.2	Soil Erosion Impact	113

6.14.3	Contamination of Soil from Fossil Fuels	113

6.14.4	Dust Emissions	114

6.14.5	Vehicle Exhaust Emissions	114

6.14.6	Pollution from Solid Waste Generation	114

6.14.7	Impacts on Water Resources and Water Quality	115

6.14.8	Noise and vibration	116

6.14.9	Impacts from Hazardous Materials	117

6.14.10	Accidental Oil Spills or Leaks	117

6.14.11	Fire Hazards	117

6.14.12	Impacts of construction material sourcing (e.g., quarrying)	118

6.14.13	Increased Water Demand	118

6.14.14	Energy Consumption	119

6.14.15	Occupational Health and Safety Impacts	119

6.14.16	Community Safety -Access to Site by General Public	119

6.14.17	Spread of HIV/AIDS and STIs	120

6.14.18	Increase in competition for scarce resources and strain on public utilities	120

6.14.19	Child Labor	121

6.14.20	Gender Based Violence- SEA and SH	121

6.14.21	Public Health Impacts	123

6.14.22	Forced Labour	124

6.14.23	Risks related to Inadequate Stakeholder Engagement	124

6.15	Negative impacts during Operation phase of the project	124

6.15.1	Solid Waste Generation	124

6.15.2	Liquid Waste/Oils Generation	125

6.15.3	Increased oil Consumption	125

6.15.4	Increased Storm Water Flow	126

6.15.5	Fire Outbreaks	126

6.15.6	Visual Impacts	126

6.15.7	Water demand	127

6.15.8	Sanitary waste	127

6.15.9	Flooding	127

6.15.10	Workers Occupation Health and Safety	127

6.15.11	Hazardous waste	128

6.15.12	Noise and Vibration	128

6.15.13	Electric and magnetic fields (EMFs)	128

6.15.14	Shocks and electrocutions to the PAPs	128

6.15.15	Community safety -Access to the facility by general public	129

6.15.16	Risks related to poor or inadequate stakeholder engagement (Conflict)	129

6.15.17	Gender Based Violence- SEA/ SH	129

6.15.18	Public Health Impacts –HIV/AIDs	130

6.15.19	Public health Impacts -Covid 19 disease	130

6.15.20	Dust emissions	131

6.15.21	Vehicle exhaust emissions	131

6.16	Negative impacts during decommissioning phase	131

6.16.1	Noise and Vibration	132

6.16.2	Solid Waste Generation	132

6.16.3	Dust Emissions	132

6.16.4	HIV/AIDs awareness and prevention	133

6.17	Social Protection	133

6.18	Social Inclusion	133

7	CHAPTER EIGHT: ENVIRONMENTAL AND SOCIAL MANAGEMENT AND MONITORING PLAN (ESMMP)	134

7.1	Introduction	134

7.2	Monitoring	134

7.3	Plan Monitoring	135

7.4	Environmental and Social Monitoring by Contractors	135

7.5	Management Plan during Construction Phase	7-176

7.5.1	Construction Management Plan	7-176

7.5.2	Rehabilitation and Site Closure Plan	7-177

7.5.3	Local Recruitment Plan	7-177

7.5.4	Workplace Health and Safety Plan	7-178

7.5.5	Community Health and Safety Plan	7-178

7.5.6	Emergency Preparedness Plan	7-178

7.5.7	SEA/SH Prevention and Response Action Plan	7-178

7.5.8	Stakeholder Engagement Management Plan	7-179

7.6	Grievance Mechanism	7-179

7.7	Grievance Redress Mechanism	7-180

7.7.1	Introduction	7-180

7.7.2	National GRC	7-180

7.7.3	Arbitration or legal redress in a court of law (the Environment and Land Court) and the Land Acquisition Tribunal	7-180

7.7.4	World Bank Grievance Redress Service (GRS)	7-181

7.7.5	National Grievances Redress Committee (NGRC)	7-181

7.7.6	County Grievance Redress Committees (CGRC)	7-181

7.7.7	Locational Grievance Redress Committee (LGRC)	7-182

7.7.8	Disclosure	7-184

7.8	World Bank Grievances Redress Mechanism	7-1

7.8.1	Labor Influx Management Plan	7-2

7.8.2	Rehabilitation and Decommissioning Management Plan	7-2

7.9	Institutional Implementation Arrangements for the Proposed Project	7-3

7.9.1	Proponent -Ministry of Energy and Petroleum (MoEP)	7-3

7.9.2	KOSAP Project Implementation Unit	7-3

7.9.3	The Implementing Agency (KP)	7-3

7.9.4	County Government of Lamu	7-3

7.9.5	National Environmental Management Authority	7-3

7.9.6	Roles and Responsibilities of the Supervising Consultant	7-4

7.9.7	Roles and Responsibilities of the Contractor	7-4

7.10	Management of Impacts during Operation Phase	7-5

8	CHAPTER NINE: CONCLUSIONS AND RECOMMENDATIONS	8-6

8.1	Conclusions	8-6

8.2	Recommendations	8-7

9	APPENDICES	9-9

9.1	Appendix 1 – Minutes of the ESIA meeting and the attendance list	9-10

9.1.1	Minutes of the ESIA meeting	9-10

9.1.2	The Public Participation List of attendance	9-16

9.1.3	FGD Lists	9-21

9.2	Appendix 2: Minutes Of Community Consultation Meeting Leading To Voluntary Land Acquisition and GRC Constitution	9-25

9.2.1	List of Participants	9-35

9.2.2	FGD Lists	9-41

9.3	Appendix 3: Lead Expert’s License	9-49

# LIST OF PLATES

Plate 2. View of site locality with some of the tree species present	3-51

# LIST OF FIGURES

Figure 3: Summary of Environmental and Social Impact Assessment Methodology	1-34

Figure 5: Map Showing the KOSAP Counties Lot 3	2-39

Figure 8. KOSAP Grievance Redress Mechanism	7-184

# EXECUTIVE SUMMARY

E.1 Introduction and Project Brief

The Ministry of Energy (MOE) hereinafter refer to as proponent is implementing the Kenya Off-Grid Solar Access Project (KOSAP) in 14 underserved counties in Kenya. The aim of the project is to provide clean and modern energy services through off-grid solar solutions. The Proponent is coordinating the implementation of the project through the implementing agencies; Kenya Power (KP) and the Rural Electrification and Renewable Emergency Corporation (REREC). The project is funded by the World Bank Group with $150 million and a $5 million grant from the Carbon Initiative for Development. The goal of the project is to bring electricity to around 250,000 households, 476 community facilities, and 380 boreholes in the target counties, benefiting low-income groups. It also includes the sale and installation of 150,000 efficient cook stoves. The project focuses on marginalized areas based on the County Development Index (CDI) and aims to address infrastructure deficits, lack of access to roads, electricity, water, and social services in these underserved counties. To ensure sustainability, the project relies on public funding, local community participation, and the institutional capacity of KP, REREC, and the MOE.

The KOSAP consists of four main components. The first component, focuses on the implementation of mini-grids to provide electricity to community facilities, enterprises, and households in areas where mini-grids are the most cost-effective option. The second component, aims to electrify households through standalone solar systems in areas without load clusters where standalone systems are the best technical and financial solution. The third component, supports the electrification of public institutions and community facilities using standalone solar systems. It also includes the installation of solar PV-powered water pumps for consumptive purposes. Lastly, the fourth component, provides funding for implementation support, technical assistance, and capacity building activities to ensure the sustainability and impact assessment of the interventions carried out under the other components of KOSAP.

In Lamu County, one of the target counties, the Proponent is proposing to develop 3 mini grid facilities including Mkokoni Mini Grid discussed in this report.  In order to adhere to both national and donor requirements, the Proponent engaged the services to the consortium of Norken International Limited and Centric Africa Limited to undertake the ESIA. The ESIA has been conducted following the requirements outlined in the Environmental Management and Coordination Act (EMCA) 1999 and its amendments, as well as international environmental and social policies such as the World Bank's OP 4.01 on environmental assessment.

E-2- Project Categorization and Justification

In the World Bank context, there have been several projects supported by the organization that aim to provide electricity to communities located far from the national grid. These projects utilize off-grid approaches, meaning they are independent of a national or regional grid. The experience gained from these projects provides valuable guidance for designing sustainable off-grid electrification initiatives, particularly those targeting dispersed and economically disadvantaged communities. The Mkokoni proposed site aligns with this category of projects that the World Bank has been involved in.

In the Kenyan context, the Environmental Management and Coordination Act (EMCA) of 1999, as amended in April 2019 through Legal Notice No. 31, classifies solar power farms and plants as medium risk projects. This categorization provides a framework for assessing and managing the potential environmental and social impacts associated with such projects. By categorizing the Mkokoni site as a solar power facility, it falls within the medium risk project category as per the Kenyan legislative framework.

E-3 Approach and Methodology

The Environmental and Social Impact Assessment (ESIA) for the proposed project followed a structured process, beginning with kick-off meetings and online discussions involving the Proponent, Implementing agencies, and the World Bank Environmental and Social Safeguard Team. These consultations were instrumental in establishing the project's scope, deliverables, timeline, and methodology. Subsequently, screening and scoping exercises were conducted to evaluate potential social and environmental risks. A thorough desk-based review was also undertaken to assess existing project documentation, legal requirements, and relevant plans.

The study employed a comprehensive approach to gather primary and secondary data for the project. Both qualitative and quantitative methods were utilized, with secondary data obtained through literature reviews. Primary data collection involved various techniques, including physical observations, photography, interviews, and stakeholder consultations. This comprehensive approach enabled a comprehensive examination of the project's environmental and social aspects, ensuring a holistic understanding of its potential impacts.

The study further involved the identification and assessment of potential impacts throughout the project's life cycle. Key areas of evaluation included land use, water resources, biodiversity, air quality, noise levels, community health and safety, and socio-economic conditions. To mitigate adverse effects, the study developed environmental and social management and monitoring plan, aiming to address both positive and negative impacts that may arise from the project. These measures aimed to ensure the project's sustainability and enhance its overall environmental and social performance.

E-4 Legislative Regulatory Framework

The evaluation, planning, and implementation of the proposed project is guided by the World Bank's Environmental and Social Framework, the national legislative framework, and the project's safeguard instruments. These measures aim to ensure environmental sustainability, protect the rights and needs of indigenous peoples and marginalized groups, and minimize adverse impacts through effective management and mitigation measures.

The Government of Kenya established the Environmental Management and Coordination Act (EMCA) in 1999, providing a legal framework for environmental management. EMCA takes precedence over other sectoral laws related to the environment. In 2013, the government formulated a national Environmental Policy with the goal of promoting sustainable management and use of the environment.

Collaboration and consultation among government agencies and stakeholders are essential for coordinating environmental management effectively. Key institutions in Kenya responsible for environmental issues include the National Environment Management Authority (NEMA), County Environment Committees, National Environmental Complaints Committee, National Environment Action Plan Committee, Standards and Enforcement Review Committee, National Environment Tribunal, and National Environment Council (NEC).

The project also adheres to the World Bank Safeguard Policies, which aim to improve decision-making processes, promote sustainable project options, and involve affected people in consultations. The applicable operational policies for this project include Environment Assessment, Natural Habitats, Indigenous Peoples, and Involuntary Resettlement. The Environmental and Social Impact Assessment (ESIA) considers these policies and addresses potential environmental and social concerns.

Additionally, the ESIA references other Safeguard Instruments prepared under the Kenya Off-Grid Solar Access Project (KOSAP), including the Environmental and Social Management Framework (ESMF), Resettlement Policy Framework (RPF), and Vulnerable and Marginalized Groups Framework (VMGF). These instruments provide procedures and guidelines for assessing and managing environmental and social aspects specific to the proposed subprojects under KOSAP.

E-5 Environmental Setting

The project site has sparsely populated trees with dense shrubs and grassland; main tree species found within the area includes neem tree (Azadirachta indica), acacia tree species (i.e Acacia tortilis). The area is characterized by sandy soils and is covered by grassland vegetation and shrubs. The area is located at about 0.5km north of Indian Ocean and is characterized by high rainfall amounts of above 1000mm. The land-use and land-cover of the study area (5kms) has been interpreted from visual interpretation, survey maps of the area, and subsequently by ground checking during field surveys. The area is majorly grassland and with shrubs with sandy soils.

The site is generally flat with an elevation difference of below 0.5m observed within the project site. The general slope of the surrounding areas leads into Indian ocean located on the Southern part at about 0.5km from the project site.

The area is marjorly sandy with ocean shores and archipelagoes located at a close proximity to the site (between 1-2km). The nearest river is located in Dodori forest and swampy areas to the north and eastern areas that provide evidence of groundwater in the area. The hydrology of the area is highly influenced by the topography and geology of the area with rivers and streams flowing south easterly in a direction perpendicular to the Indian Ocean coastline.

E-6 Project Description

The Mkokonil Mini Grid project aims to provide electricity to approximately 251 residential and 6 non-residential consumers in, Kiunga location, lamu East Sub County. The project will utilize solar photovoltaic panels, a Battery Energy Storage System, and a Diesel Generator to generate electricity. A Low Voltage Power Distribution Network will be established to distribute the power to customers. The estimated cost of the project is around USD 503,914 although this amount may change as more detailed plans are developed.

The project utilizes solar panels with a total capacity of 91 kWp to harness solar energy. Solar power is a clean and renewable energy source that will provide a significant portion of the electricity needed for the project. A 296 kWh Battery Energy Storage System is incorporated to store excess solar energy during the day, ensuring a consistent power supply even during cloudy or nighttime conditions. A 50 kVA diesel generator is included to serve as a backup power source for periods of low solar generation or in case of battery depletion. It provides reliability and backup in the event of extended periods of cloudy weather or high demand. A 2,000-liter fuel tank is provided to store diesel fuel for the generator, ensuring continuous operation during extended periods of low solar or high demand. Additionally, PV Inverter: A 76 kW solar PV inverter is used to convert the direct current (DC) electricity generated by the solar panels into alternating current (AC) electricity suitable for consumer use.

The proposed minigrid site has a circuit distribution length of 8km.

The project consists of two main components: Hybrid Mini-Grids and power line reticulation lines. The Hybrid Mini-Grids will combine solar panels and diesel power generation. These energy sources will be integrated through a centralized photovoltaic plant connected to a 3-phase AC busbar line. The configuration is designed to prioritize direct supply from the solar generator during daylight hours, reducing reliance on battery storage. The battery storage will primarily be used when solar generation is low or demand is high. The construction of power line reticulation lines will ensure the efficient distribution of electricity to residential, commercial, and other consumers, ensuring a reliable and efficient power supply.

To develop the Mini Grid, approximately 0.411 Hectares of land will be compulsorily acquired by the Proponent from the community. The proposed Project site is located on public land registered under the National Police Service (NPS)-surveyed and does not require compensation.

E-7 Project Alternatives

Solar energy is identified as a non-polluting and site-specific option, and the proposed site for Mkokoni MG is chosen as the most suitable location for the mini-grid based on factors such as sunlight availability and the community's lack of grid connectivity. The use of wind power, thermal power, fossil fuels, and power import from neighbouring countries are considered as alternative methods of power generation but are found to have limitations or environmental concerns. Solar energy is favoured due to its low production costs, versatility, clean nature, and economic savings. The "No Project" alternative is deemed unfavorable as it would maintain the current lack of electricity access and hinder socio-economic development. The project will be constructed using modern materials and technology, with a focus on public health, safety, security, and environmental requirements. The technology will involve a Battery Energy Storage System.

E-8 Stakeholder Engagement

It is important to highlight that two forms of stakeholder engagement were carried out for the project. The first form as noted earlier, focused on the acquisition of land for the project and involved the Proponent and the implementing agency (KP). The second form of engagement was conducted specifically for the Environmental and Social Impact Assessment (ESIA) study.

For the ESIA study, various methods were employed to engage stakeholders, taking into consideration their different categories. Face-to-face discussions were held with government officials and key stakeholders, while separate focused group discussions were conducted with men, women, and youth. Additionally, a public baraza or meeting was organized to allow community members to participate.

During the ESIA stakeholder engagement public meeting, which took place on 30th September 2021, a total of 104 stakeholders attended. The meeting provided an opportunity to discuss project details, including the preliminary design, positive and negative impacts, and mitigation measures. Stakeholders were encouraged to share their views and provide feedback on the project.

- The community raised they following concerns:

  - The members consulted registered their concerns in terms of delay to implementation of the project implementation period. It has already taken long time to commission the construction since the proponent initiated the land acquisition process.

  - The members enquired on the sustainability of the project in case of breakdown or malfunction of one of the project components. They posed a scenario of having a component such as battery or the generator running out fuel and enquired to know who will cover for the repair and purchasing costs.

  - Concerns were raised on safety of appliances used in household and business facilities such as Television and fridges and whether surge protectors (i.e., fridge guard) can be used

E-9 – Impacts and Mitigation Measures

The Environmental and Social Impact Assessment (ESIA) for the proposed Solar Mini-grid project has identified both positive and negative impacts across its different phases: pre-construction, construction, operation, and decommissioning. In the construction phase, positive impacts include local employment opportunities, boosting local businesses, and sourcing materials locally. During the operation phase, positive impacts encompass reliable power supply, economic improvement, education, health benefits, improved living standards, and enhanced security and communication. Similarly, the decommissioning phase offers positive impacts such as local employment and sourcing.

On the negative side, the pre-construction phase involves minor impacts like land acquisition, while the construction phase encompasses various minor to moderate impacts such as vegetation clearance, soil erosion, dust emissions, and occupational health and safety concerns. Challenges related to stakeholder engagement, labor influx, child labor, and exclusion of vulnerable individuals are also anticipated. In the operation phase, negative impacts include waste generation, increased oil consumption, fire outbreaks, occupational health and safety concerns, and inadequate stakeholder engagement. Issues of exclusion, inadequate grievance management, and public health concerns may arise as well.

During the decommissioning phase, negative impacts primarily relate to solid waste generation, noise and vibration, and challenges in stakeholder engagement, labor influx, child labor, gender-based violence, and exclusion of vulnerable individuals and households.

Tables 0-2 to 0-5 below present summaries of anticipated impacts and their corresponding levels of significance, both pre- and post-mitigation.

Table 0-2: Summary of Pre-construction Impacts

| Impact | Significance Of Impact (Pre-Mitigation) | Residual Impacts (Post-Mitigation) |
| --- | --- | --- |
| Land acquisition | Minor | Negligible |
| Acquisition of Way leaves | Minor | Negligible |
| Stakeholder identification and consultations | Major | Minor |

Table 0-3: Summary of Construction and Decommissioning Phases Impacts

| Impact | Pre-construction | Construction phase | Decommissioning phase |
| --- | --- | --- | --- |
| Impacts on Local Economy and Employment | Not Applicable | Positive | Positive |
| Change in land use | Not Applicable | Moderate | Positive |
| Site rehabilitation | Not Applicable | Not Applicable | Positive |
| Topography | Not Applicable | Minor | Not Applicable |
| Soil environment | Not Applicable | Minor | Minor |
| Air Quality | Not Applicable | Moderate | Moderate |
| Ambient noise | Not Applicable | Minor | Minor |
| Visual intrusion and change in landscape | Not Applicable | Minor | Positive |
| Waste generation and soil contamination | Not Applicable | Minor | Minor |
| Impact on water environment | Not Applicable | Minor | Not Applicable |
| Impacts from hazardous materials | Not Applicable | Minor | Not Applicable |
| Fire hazards | Not Applicable | Moderate | Minor |
| Impacts of construction material sourcing | Not Applicable | Moderate | Not Applicable |
| Energy consumption | Not Applicable | Negligible | Not Applicable |
| Occupational safety and health | Not Applicable | Moderate | Moderate |
| Community safety and health | Not Applicable | Moderate | Moderate |
| Labor influx | Not Applicable | Minor | Minor |
| Child labour | Not Applicable | Minor | Negligible |
| Cultural heritage | Not Applicable | Minor | Not Applicable |
| Gender based violence, SEA and SH | Not Applicable | Minor | Minor |
| Exclusion of VMGs, Vulnerable individuals and households | Not Applicable | Major | Major |
| Risk of communicable diseases | Not Applicable | Minor | Minor |
| Increased water demand |  | Negligible | Negligible |
| Forced labour |  | Minor | Negligible |

Table 0-4: Summary of Operation Phase Impacts

| Impact | Significance Of Impact (Pre-Mitigation) | Residual Impacts (Post-Mitigation) |
| --- | --- | --- |
| Impact On Economy and Employment | Positive | Positive |
| Quality, reliable power supply | Positive | Positive |
| Reduction of pollution associated with thermal power generation, kerosine and wood fuel usage | Positive | Positive |
| Education | Positive | Positive |
| Health benefits | Positive | Positive |
| Improved standard of living | Positive | Positive |
| Security | Positive | Positive |
| Communication | Positive | Positive |
| Soil environment | Minor | Negligible |
| Waste generation and management | Minor | Negligible |
| Water environment | Negligible | Negligible |
| Landscape and visual impacts | Minor | Negligible |
| Increased oil consumption | Minor | Negligible |
| Increased storm water flow | Minor | Negligible |
| Fire outbreaks | Moderate | Minor |
| Water demand | Negligible | Negligible |
| Sanitary waste | Negligible | Negligible |
| Flooding | Negligible | Negligible |
| Noise and Vibration | Negligible | Negligible |
| Electric and magnetic fields (EMFs) | Negligible | Negligible |
| Dust Emission | Negligible | Negligible |
| Vehicle Exhaust emission | Minor | Negligible |
| Collision and electrical hazards from distribution infrastructure | Minor | Negligible |
| Occupational safety and health | Moderate | Minor |
| Community safety and health | Moderate | Minor |
| Gender based violence, SEA and SH | Minor | Negligible |
| Exclusion of VMGs, Vulnerable individuals and households | Major | Minor |
| Risk of communicable diseases | Minor | Negligible |
| Shocks and electrocution to the PAPs | Moderate | Minor |
| Risks related to poor and inadequate stakeholder engagement (conflict) | Minor | Negligible |

E-10 Environmental and Social Management and Monitoring Plan

A comprehensive set of mitigation measures in the form of an Environmental and Social Management and Monitoring Plan (ESMMP) have been prepared for the project. The ESMMP serves as a comprehensive framework for the integrated management of all environmental and social impacts throughout the project's lifecycle. It has been prepared to ensure that the social and environmental impacts and risks identified during the Environmental and Social Impact Assessment (ESIA) process are appropriately managed during the construction, operations, and decommissioning phases of the project. It specifies the mitigation and management measures that the project proponent and contractor are committed to implementing and outlines how organizational capacity and resources will be mobilized to achieve these measures. The ESMMP also ensures compliance with the relevant laws, regulations within Kenya, as well as the environmental and social sustainability requirements of the World Bank's Operational Policies (OPs).

These measures emphasize a proactive approach, prioritizing prevention rather than reaction. They encompass various aspects such as proper waste handling and disposal to prevent pollution, engaging stakeholders to address grievances, providing personal protective equipment (PPE) for workers, ensuring adequate supervision, and emphasizing good workmanship from the contractor. Specific plans are also outlined to address specific issues that may arise. The ESMMP also highlights environmental performance indicators that should be regularly monitored. Monitoring serves as a means to detect and draw attention to any changes or problems in environmental quality. It involves continuous or periodic reviews of the ESMMP implementation progress, allowing for adjustments and improvements as necessary.

While accommodating the recommended mitigation measures to the extent practical and economically viable, the project proponent and contractor should ensure that the measures do not compromise the economic viability of the project or have long-lasting adverse impacts on the environment.

For the mitigation measures to be successful, it is imperative that the Kenya Power and Lighting Company (KPLC) allocates sufficient resources for the implementation of the ESMMP. Adequate resources will enable the proper execution of the proposed measures and ensure their effectiveness in minimizing the identified negative impacts.

Following the project's commissioning, it is mandatory to conduct statutory Environmental and Safety Audits in accordance with national legal requirements. These audits serve to evaluate the environmental performance of the site operations and assess their compliance with the recommended mitigation measures.

E- 11 Conclusion

Based on the assessment findings, the consultant concludes that there are no substantial reasons to hinder the proposed project from progressing to the next stage of planning and development. However, this progression is conditional upon the implementation of the recommended mitigations and the monitoring of potential environmental and socio-economic impacts as outlined in the ESMMP.

It is in the opinion of the Environmental expert that the anticipated negative impacts can readily and effectively be mitigated and on the whole the proposed project does not pose any significant threat to the Environment and may be licensed to proceed

# INTRODUCTION

The Ministry of Energy Petroleum (MOEP) Kenya is coordinating the implementation of the Kenya Off-Grid Solar Access Project (KOSAP) to provide access to clean and modern energy services through off-grid solar to 14 underserved counties. Lamu county was identified as one of the underserved Counties and others include Mandera, Narok, Garissa, Tana River, Samburu, Isiolo, Marsabit, West Pokot, Turkana, Taita Taveta, Kilifi and Lamu.

Driven by the imperative to provide equal opportunities across the entire Kenyan territory as key to achieving Kenya’s Vision 2030, and the National target of achieving universal access to electricity by 2020, the GoK now seeks to close the access gap by providing electricity services to remote, low density, and traditionally underserved areas of the country. The World Bank’s (WB)Country Partnerships Strategy (CPS) for Kenya (2014-18) also recognizes the access to basic electricity, as a key developmental issue. The Strategy sets at improving core infrastructure as one of the Projects the WB will be engaged in. It also emphasizes the importance of mobilizing concessional funding to expand the sector including electricity generation, transmission, and distribution to meet the Government’s economic growth targets.

KOSAP directly promotes the achievement of these objectives by supporting the use of solar and clean cooking Solutions to drive electrification of households (including host communities), enterprises, community facilities, and water pumps in Lamu county as one of the counties in Kenya that have been defined as “marginalized areas” based on the County Development Index (CDI) by the Commission on Revenue Allocation (CRA). According to the CRA as the communities in the marginalized areas have been excluded from social and economic life of Kenya for different reasons” (CRA, 2013).

Lamu County and other identified underserved counties, collectively represent 72% of the Country’s total land area and 20% of the Country’s population, including historically nomadic societies that even today continue to rely on pastoralism. The population in Lamu county is highly dispersed, at a density four times lower than the national average. They present profound infrastructure deficits, including lack of access to roads, electricity, water, and social services. There is also significant insecurity in certain areas, giving rise to substantial numbers of displaced persons and livelihood adaptations that further undermine economic prosperity.

## Context

This ESIA report has been prepared based on Site visit baseline survey, desktop survey, documentation review, consultation with stakeholders and in accordance Environmental Management and Coordination (Amendment) Act, 2015 and World Bank’s Environmental and Social Safeguards. The study has also assessed the requirement of the project with respect to the local and national regulations relevant to the project.

Norken International Limited in Joint Venture with Centric Africa Limited were appointed by Ministry of Energy to undertake consultancy services for the Environmental and Social Impact Assessment (ESIA), Social Assessment (SA) and Vulnerable and Marginalized Groups Plan (VMGP) as per the standard TOR and NEMA and WB ESS. As reported, land acquisition has not resulted in any economic or physical displacement and no resettlement is envisaged for the proposed project.

Due to the remoteness and sometimes dispersed nature of the target populations and considering the lifestyles and socio-economic status of those residing in underserved Counties, the Project is designed to address low affordability of the potential users, and sustainability of service provision. Therefore, sustainability of the proposed approach to energy access expansion beyond the Nationally owned power network is predicated on two primary factors - public funding, local community participation: and institutional capacity of Kenya Power and, Rural Electrification and Renewable Energy Corporation (REREC) and the Ministry of Energy Petroleum (MOEP) as the implementing agencies.

The project components are:

- Component 1- US$40M: Mini-grids for Community Facilities, Enterprises, and Households -This component will support electrification of areas where electricity supply through mini-grids represents the least cost option from a country perspective.

- Component 2- US$48M: Stand-alone Solar Systems and Clean Cooking Solutions for Households; This component will support electrification of households using standalone solar systems in areas where load clusters do not exist, and the best technical and financial solution is standalone solar systems.

- Component 3- US$40M: Stand-alone Solar Systems and Solar Water Pumps for Community Facilities; This component will support electrification of public institutions and community facilities using standalone systems. This component will also support the installation of solar PV-powered water pumps for consumptive purposes.

- Component 4- US$22M: Implementation Support and Capacity Building; This component will finance various technical assistance and capacity building activities to ensure the sustainability and measure the impact of the interventions devised and implemented within the other components of KOSAP.

The MOEP provides overall coordination of the project as well as lead in the implementation of components 2 and 4. Components 1 and 3(a&b) will be implemented by the Kenya Power Company (KPC) and the Rural Electrification and Renewable Energy Corporation (REREC), respectively.

## Project Overview

The project is located in village at about 0.6Km from the ocean line in Kiunga ward, Lamu East Sub County in Lamu County at coordinates of latitude 1°58'1.07"S and longitude 41°17'43.27"E. The proposed solar mini grid will be located on a 0.411  hectares piece of public land registered under the National Police Service (NPS)-surveyed. The MoEP has made a formal communication to NPS to grant consent for parcel of land. The land is at about 0.5km north of shopping centre along Kiunga Road.

Figure 2. Map showing the proposed Mkokoni Minigrid site

The solar mini grid will contain Solar panels, batteries, invertors, perimeter fence and length of transmission line to cover a circuit distance of approximately 8 km LV circuit distance on about 3km extent within the area. The project is expected to serve 257 consumers of which 251 are residential and 6 are non-residential.

## Purpose and Scope of Work

This report discusses the environmental and social baseline within which the proposed solar power project is commissioned and assesses the potential adverse and beneficial impacts that the project could have, along with suitable mitigation measures and an Environmental and Social Management Plan (ESMP) for the project. The report also evaluates the environmental and social risks associated with the project and implements mitigation measures to avoid adverse impacts for the remainder of the project’s lifecycle. The project must comply with international standards (World Bank Environmental and Social Safeguards) along with applicable national, state, and local regulations.

## ESIA Study Team

Table 5. ESIA Project Team

| NAME | INSTITUTION | POSITION |
| --- | --- | --- |
| Lavina Omondi | Centric Africa Ltd | Sociologist |
| Henry Karanja | Centric Africa Ltd | Environmentalist |
| Daniel Chumo | Centric Africa Ltd | Environment & Stakeholder Engagement Expert |
| Sharon Watiri | Norken International Ltd | Gender Expert |
| Pius Nyaga | Kenya Power & Lighting Company (KPLC) |  |
| George Ofula | Lamu County Renewable Energy Officer |  |

## ESIA Methodology

### Screening and Scoping

#### Screening Methodology

Evaluation of ESIA procedure has been undertaken as a fundamental procedure to implementation of the solar power mini-grid development project which is systematically mainstreamed into the project’s Cycle. World Banks Social safeguards underpin and demonstrate this commitment. The main aim of this is to enhance positive social opportunities and benefits as well as ensure that adverse social and environmental risks and impacts are avoided, minimized, and mitigated.

The below steps were followed.

#### Kick-off Meeting

Norken and Centric team had a brief kick-off meeting with the Proponent on 12th July 2021 followed by subsequent online meetings and discussion on various aspects of the project up to 5th August, 2021 and 15th September, 2021. The meetings addressed varied deliverables and thresholds to be achieved and maintained during this assessment in terms of scope of work, deliverables, timeline and the methodology. All communication and meetings were done online.

#### Desk based review and baseline assessment

A comprehensive description of the KOSAP Component 1: project includes a desktop review of all the existing project documentation provided by the Proponent including: the Project Appraisal Document and the four main safeguard framework documents prepared under KOSAP- these are Social Assessment, Vulnerable and Marginalized Group Framework, Resettlement Policy Framework and the Environmental and Social Management Framework.

### Project Description

The consultant has concisely described the project location including its geographical, ecological and the general layout of associated infrastructure including maps at an appropriate scale where necessary. Location of all project related development sites, including proximal offsite investments; general layout; flow diagrams/drawings of facilities/operation design basis, size, capacity, flow-through of unit operations, including pollution control technology included if any; pre-construction activities and construction activities; construction schedule; staffing size and support; facilities and services around; commissioning, operation and maintenance activities and plan.

### Baseline Condition

This entails description and collection of relevant primary data within the project site’s bio-physical, socio-economic and cultural profile with respect to the biodiversity profile, land use types, cultural heritage and practices, social and economic issues likely to be affected, expected project activities to be involved during the design, construction and operation of the proposed facility. The information also includes description of the community social structure, employment and labour market, sources and distribution of income, cultural/religious sites and properties, vulnerable groups and indigenous populations. This also covers description of the sites’ physical environment including their topography, land cover, geology, climate and meteorology, air quality and hydrology. This entailed use of secondary data sources and for some specific environmental parameters the deployment of specialized equipment to measure and record the environmental readings as primary data for analysis and inclusion in the ESIA report. The ecological and biophysical environment will is focused on describing the flora and fauna resident in the Lamu county and at the mini-grid site level. This was be based on observations of flora and fauna, KPIs on local indigenous knowledge on historical and current status of rare, endemic and endangered plant and animal species known to occur in the project area. Vegetation assessment was done to gain an understanding of the mini-grid sites habitat type. This has provided for an in-depth description of existing land use type and their linked socio-economic activities.

### Impact Assessment Prediction

The anticipated impacts generated by the project and subsequent evaluation of their significance is provided by this report. A suite of field data collection methods was deployed including public forums discussions, Focus Group Discussions, Key Informant Interviews incorporating questionnaires for social risks assessment. Based on the outcome of the evaluation, the need for emphasis on critical areas was discussed. In order to accomplish this task an initial listing of the range of all issues and concerns identified during the study has been undertaken subsequently followed by analysis of the identified potential environmental and social impacts in terms of type (direct, indirect, cumulative, positive, negative), magnitude (local, widespread, random, severity) and duration (temporary, permanent, long term, short term). Consequently, an evaluation system was used to categorize these impacts and evaluate them. This aided in determining the significance of the identified potential impacts in relation to established criteria or standards, geographic extent of effects, cumulative nature of the impact, community tolerance and preferences, etc. This culminated into generation of a short list of the most critical issues in terms of environmental, ecological and social impacts both positive and negative associated which the different phases of the project activities that are likely to affect the baseline environmental and social conditions presently occurring at the mini-grid sites.

Socio-cultural risks linked to Component 1 of KOSAP were identified during the assessment. These include, Labour influx, Gender Based Violence, Sexual Exploitation and Abuse, workplace Sexual Harassment, Spread of HIV/AIDS, STDs & other communicable diseases, Gender biases and inequality exclusion of vulnerable and marginalized groups (VMGs) and vulnerable individuals and households from accessing project decision making and governance structures, engagement processes, opportunities, and benefits. The vulnerable individuals and households will include the poor, elderly persons, PWDs, the sick, poor women, poor single mothers, child-headed households. The VMG’s include ethnic minority communities that are present in Mkokoni area.

The impacts and risks were identified in relation to free, prior, and informed comprehensive stakeholder consultations on land acquisition for construction of mini-grid, contractor’s facilities e.g., yard and workers camp site, way leave acquisition for the powerline distribution network; restricted access to grazing lands, water resources, soils and tree resources, economic/livelihoods displacement etc.

### Stakeholder Consultation and Disclosure Requirement for the Project

The World Bank OPs 10 emphasizes on engagement in meaningful consultations with all stakeholders. The stakeholders with timely, relevant, understandable, and accessible information, and consult with them in a culturally appropriate manner, which is free of manipulation, interference, coercion, discrimination, and intimidation.

A documented record of stakeholder engagement, including a description of the stakeholders consulted, a summary of the feedback received, and a brief explanation of how the feedback was considered is in place.

The respective minutes and list of participants for the public consultation undertaken at Mkokoni baraza park is enclosed under appendices in page 12-2 of this report. Further, an initial communication was shared with the county commissioner Lamu and Chief for Mkokoni location. Background information document (BID) with project details was posted clearly on one of the regular shops at Mkokoni shopping center.

### Stakeholder Characterization and Identification

A stakeholder is “a person, group, or organization that has a direct or indirect stake in a project/organization because it can affect or be affected by the Project/organization's actions, objectives, and policies” Stakeholders thus vary in terms of degree of interest, influence and control they have over the project.

Stakeholders are classified in the following two categories.

- Project affected persons- Stakeholders who have a direct impact on or are directly impacted by the project.

- Interested parties- Stakeholders who have an indirect impact or are indirectly impacted by the project.

In line with the nature of the project and its setting in Mkokoni the stakeholders have been identified and listed in the table given below.

Table 16. Identified Stakeholders

| Stakeholder Groups | Project-affected Persons | Interested Parties |
| --- | --- | --- |
| Community | Local Laboure’s VMG’s Local Community | Farmers, pastoralists |
| Institutions | Community & Faith Based Organizations Education & Healthcare institutions |  |
| Government Bodies | NEMA NPS County Government District and local administration |  |

The public (local community members, Laboure’s and VMG's at the Mkokoni Shopping centre) were consulted through a public baraza held at Mkokoni Baraza park on 30th September 2021 where 40 males and 64 women were in attendance including the area senior assistant chief as well as villages elders were engaged through face-to-face discussions as well as engagement walks on the proposed project site.

#### Stakeholder Mapping

Stakeholder mapping is a process of examining the relative influence that different individuals and groups have over a project as well as the influence of the project over them. The purpose of a stakeholder mapping is to:

- Identify each stakeholder group.

- Study their profile and the nature of the stakes.

- Understand each group’s specific issues, concerns as well as expectations from the project

- Gauge their influence on the Project.

The significance of a stakeholder group is categorized considering the magnitude of impact (type, extent, duration, scale, and frequency) or degree of influence (power and proximity) of a stakeholder group and urgency/likelihood of the impact/influence associated with the stakeholder group in the project context. The magnitude of stakeholder impact/influence is assessed taking the power/responsibility and proximity of the stakeholder group and the group is consequently categorized as negligible, small, medium, or large. The urgency or likelihood of the impact on/influence by the stakeholder is assessed in a scale of low, medium, and high. The overall significance of the stakeholder group is assessed as per the matrix provided in Table below.

Table 15: Stakeholder Significance and Engagement Requirement

|  |  | Likelihood of Influence on/ by Stakeholder |  |  |
| --- | --- | --- | --- | --- |
|  |  | Low | Medium | High |
| Magnitude of impact | Negligible | Negligible | Negligible | Negligible |
|  | Small | Negligible | Minor | Moderate |
|  | Medium | Minor | Moderate | Major |
|  | Large | Moderate | Major | Major |

### Stakeholder Analysis

The table below has been used to classify the identified stakeholders (directly or indirectly impacting

the project) in accordance with their levels of influence on the project. The influence and priority have

both been primarily rated as:

- High Influence: This implies a high degree of influence of the stakeholder on the project in terms of participation and decision making or high priority to engage with the stakeholder.

- Medium Influence: Which implies a moderate level of influence and participation of the stakeholder in the project as well as a priority level to engage the stakeholder which is neither highly critical nor are insignificant in terms of influence; and

- Low Influence: This implies a low degree of influence of the stakeholder on the project in terms of participation and decision making or low priority to engage that stakeholder.

The intermediary categories s of low to medium or medium to high primarily imply that their influence

and importance could vary in that range subject to context specific conditions or also based on the responses of the project towards the community.

The coverage of stakeholders as stated above includes any person, group, institution, or organization that is likely to be impacted (directly or indirectly) or may have interest/influence over project. Keeping this wide scope of inclusion in stakeholder category and the long life of project, it is difficult to identify all potential stakeholders and gauge their level of influence over project at the outset of the project. Therefore, the project proponent is advised to consider this stakeholder mapping as a live document which should be revised in a timely manner to make it comprehensive for any given period

#### Environmental and Social Management Plan (ESMP)

The ESMP as the implementation instrument of the ESIA has captured all the parameters that need to be monitored on a routine basis. The parameters as indicated in an Environmental and Social Management and Monitoring Plan (ESMMP) matrix, a detailed description of the implementation and monitoring program.

The ESMMP has a detailed arrangement of responsibilities for managing and monitoring the implementation of mitigation measures and the impacts of the project during construction, operation, and decommissioning. This include: a description of monitoring methodology, specific operations, and features to be monitored, monitoring reporting relationships and arrangements to ensure that monitoring is effective. Simple and straightforward monitoring processes established for ease of implementation through the project cycle. This plan follows through a description of the impacts and areas affected, key mitigation measures, monitor-able indicators, timeframe, responsibilities, and budget implications.

The ESMP include an implementation schedule and budget cost estimates for the mitigation measures both capital and recurrent costs estimates and the financing entity. It also describes institutional arrangements regarding the implementation of the ESMP among the implementing agencies, and the mini-grid contractor(s). This has specific responsibilities, procedures and resources required by each institutional actor engaged in implementing the ESMP.

The “Chance Find Procedures” has also been included in the ESMP as part of prevention and mitigation measures that will be implemented in the event physical cultural resources are encountered during subproject implementation.

Additionally, the ESMP has a component on contracting management that will ensure the implementation of the ESMP by all contractors and subcontractors. A contracting mechanism is included in the ESMP to incentivize contractors and their subcontractors to comply with the ESMP or alternatively penalize them for failure to comply with the ESMP. It also includes contractor clauses that will cover worksite health and safety, the environmental and social management of construction sites; labour camps/out of area workers, HIV/AIDS, and other Sexually Transmitted Diseases (STDs), stakeholder engagement plans, grievance redress mechanism, child protection, gender equity and sexual harassment, labor rights and the employment of community members. The ESMP also have a budget to guide the contractor on resources required for the implementation and monitoring of the ESMP.

Figure 3 is a summary of the methodology the firm will adopt in undertaking environmental and social impacts assessment for the proposed KOSAP project.

- Preparation and Planning

- Desk Review of available reports and documents

Inception Report

- Stakeholders Consultation and Participation:

  - Key informant interviews

  - Focus Group Discussions (FGDs

Draft ESIA Reports

Incorporation of Review Comments from PCU & IAs

Deliverable 1

Deliverable 2

Final ESIA Reports for the proposed Mkokoni Minigrid

Deliverable 3

- Baseline data gathering

- Identification of Potential Social Impacts

- Summary of mitigation & Management measures

- Preparation and Planning

- Desk Review of available reports and documents

Inception Report

- Stakeholders Consultation and Participation:

  - Key informant interviews

  - Focus Group Discussions (FGDs

Draft ESIA Reports

Incorporation of Review Comments from PCU & IAs

Deliverable 1

Deliverable 2

Final ESIA Reports for the proposed Mkokoni Minigrid

Deliverable 3

- Baseline data gathering

- Identification of Potential Social Impacts

- Summary of mitigation & Management measures

Figure 3: Summary of Environmental and Social Impact Assessment Methodology

### Limitations

The limitation experienced during the study are illustrated below.

- Risk of being infected or transmitting COVID-19. The teams had to adopt preventive measures by wearing face mask and providing the community members with face mask and sanitizers during the public meetings and interactions. During public participation meetings, the attendants had to be sanitized at every instance before being offered writing materials or stamp pads for inputting finger prints, this led to extended meeting periods.

## Layout of the Report

Table 5. Structure of the ESIA Report

| SECTION | TITLE | DESCRIPTION |
| --- | --- | --- |
| Section 1 | Introduction | Introduction to the Project and ESIA scope and methodology adopted. |
| Section 2 | Project Description | Technical description of the Project & related infrastructure and activities. |
| Section 3 | Applicable Legal and Regulatory Framework | Discusses the applicable environmental and social regulatory framework and its relevance for the Project. |
| Section 4 | Environmental and Social Baseline | Outlines Environmental, Ecology and Social Baseline status in the study area of the Project |
| Section 5 | Stakeholder Engagement and Grievance Redress | Provides an overview of the stakeholder engagement activities undertaken during the ESIA, stakeholder categorization and profiling Additionally, it details the provision of Grievance Redress Mechanism for the project |
| Section 6 | Impact Assessment and Mitigation Measures | This section includes details of identified environmental impacts and associated risks due to Project activities, assessment of significance of impacts and presents mitigation measures for minimizing and /or offsetting adverse impacts identified. |
| Section 7 | Environmental and Social Management Plan | Outline of the ESMP taking into account identified impacts and planned mitigation measures and monitoring requirements. |
| Section 8 | Impact Summary and Conclusion | Summary of impacts identified for the Project and conclusion of the study. |

# PROJECT DESCRIPTION

## Introduction

This section provides a description of the project in terms of location, facilities and associated project infrastructure and activities during the project lifecycle and facilitates and identification of the potential impacts on resources and receptors that could result from project activities during the pre-construction, construction, operation, and decommissioning stages.

The components of the proposed solar mini grid are provided as follows.

Table 6. Component of the proposed Solar Mini-grid

| S/NO. | PARTICULARS | DESCRIPTION |
| --- | --- | --- |
| 1. | Project location | The proposed Project site is located on public land registered under the National Police Service (NPS)-surveyed, measuring approximately 0.411 Hectares in sub-location, Kiunga location, lamu East Sub County. Geographically, the site is located on latitude 1°58'1.07"S and longitude 41°17'43.27"E, at altitude of 172 metres above the sea level. Power from the project will be evacuated through a 8km distribution line to the households within a 1.5 km radius within area and 0.5km to the shopping centre. |
| 2. | Land Size/Tenure | The proposed solar mini grid will be located on a 0.411 Hectares piece of land along -Kiunga Road next to AP’s Camps at sub-location, Kiunga location. The land is a surveyed public land under National Police Service (NPS). |
| 3. | Minigrid Power | PV Capacity 91kw; 296kWh Battery; 50kVA backup generator |
| 4. | Distribution line | LV Circuit of 8km |
| 5. | Target Consumers | 257 (251 Residential and 6 Non-Residential) |
| 6. | Climatic condition | The mean annual potential evaporation is high at 2,327 mm per year and the Temperatures range from 24° (May to July) to 30°C (December to April). The area lies along along the Equatorial Climate Systems which is characterized by two monsoon winds and warm climate with rainfall amounts of between 800mm during dry seasons and 1200mm during wet seasons. The area is also influenced by the four oceanic currents that influence the sediment distribution along the coastline. These are the South Equatorial Current; East Africa Coastal Current; The Equatorial Counter Current; and Somali Current. area is greately affected by the Northeast Monsoon (November to March) and the South East Monsoon (May to August) that joins the Somali Current which reverses its direction of flow under the influence of the monsoon. |
| 8. | Site Conditions | The site is generally vegetative with grass and shrubs. Dumped waste materials also present at the southern part of the site |
| 9. | Road Accessibility | Dirt road. |
| 10. | Nearest Airport | Kiwayu Airstrip at about 0.5km |
| 11. | River/canal/nallah/ pond present in project footprint | Kiwayu-Ndau Waterway, 400m north of the proposed site |
| 12. | Protected areas (National Park/ Sanctuary)/ Forest land within 10 kms | Dodori National Reserve, located 2km northwards |

## Project Location

The project site is located at about 500m off shopping centre along -Kiunga Road at sub-location, Kiunga location, lamu East Sub County on latitude 1°58'1.07"S and longitude 41°17'43.27"E, at altitude of 172 metres above the sea level. The proposed project site can be accessed through the coastal waterway from Lamu in the Eastern side and via unpaved rural road connecting to Kiunga and Somalia to the North Western Side.

The site is on NPS land and neighbours the National Police/Administration Police (AP) post offices at about 100m to the south and Primary school at about 200m southwards.

Figure 4: Proposed site for the Mkokoni Solar Mini-grid project with shrubs and tree vegetation

Figure 4: Proposed site for the Mkokoni Solar Mini-grid project with shrubs and tree vegetation

## Area of Influence

The Area of Influence (AoI) of the project comprises of the project site and the surrounding area, where the influence of the project activities is anticipated. The areas likely to be affected by the project and its associated activities include:

- The areas where project activities and facilities operated and managed by the Ministry of Energy, Kenya Power Company (KPC), will be established,

- Project site where project components such as solar modules, control room and transmission line to power grid sub-stations; and any other selected Corporate Social Responsibility (CSR) project, such as the construction water abstraction and distribution points will be established;

- Areas where impacts from unplanned but predictable developments caused by the project that shall occur later or at a related location such as increase in traffic on the approach road;

- Areas where there is biodiversity or on ecosystem services upon which affected communities’ livelihood are dependent; and

- Areas where associated facilities will be established e.g. approach road construction and widening of existing road.

Further to this, the AoI with respect to the environmental and social resources was considered based on the following reach of impacts:

Air Quality

- Impact on ambient air quality from vehicle exhaust;

- Impact of air pollutants emission from construction activities and

- Dust fall- typically up to 200 m from construction activities

Noise

- Noise impact area (defined as the area over which an increase in environmental noise levels due to the project can be detected) - typically 500 m from operations and 200 m from the access road

Water

- Surface water body- typically 500m upstream and downstream of water intake point and downstream of discharge point

- Other surface water bodies within 1 km of the project footprint

- Groundwater in 1-2 km radius of project footprint

Flora and Fauna

- The direct footprint of the project comprising the project site

- The areas immediately adjacent to the project footprint within which a zone of ecological disturbance is created through increased dust, human presence and project related activities (e.g., trampling, water intake/outfall, transportation). This kind of disturbance has been estimated to occur within the project footprint and surrounding areas of about 500 m to 1 km from the activity areas. Based on the above the AoI for environmental studies was limited to 5 km from the project site.

Socio-economic/Social

The AoI for social receptors was fixed to include 2 km radial zone which has been developed based on the reconnaissance site visits and stakeholder consultations with the local community. The AoI for development of the social baseline is within the village which according to the administrative structure falls within Kiunga Location. The socio-economic information presented in this report has drawn from primary socio-economic survey and the Population and housing census 2019, Kenya Bureau of Statistics (KBS).

### Project Footprint Area

The site is located in Mokoni Village, Mkokoni sub-location, Kiunga location, Lamu East Sub County. The area has indigenous forest mainly composed of tree vegetation and shrubs. The local communities practice fishing and farming (maize, cashew nuts, water melons, mangoes, simsim.. etc) within the area. The site is relatively flat; however, the surrounding areas within Mkokoni Sub location have undulating very gentle slopes (1-5%) that slopes towards the ocean to the south and is located at about 500m from the site. The forested Dodori National Reserve is also located at about 2km northwards with Dodori River plain and wildlife species in place. The site is located at a close proximity to community shopping centre that is at about 500m to the site. Land is largely communal within the area.

### Study Area

The project site is located in Mkokoni Village, Mkokoni Sub location, Kiunga Location, Lamu East Sub County in Lamu County. Based on the secondary information of the region, the sampling locations were identified to obtain the representative baseline information. Sampling locations for underground water quality was selected based on the drainage pattern of the area. Soil sampling locations were selected based on the land use and land cover of the study area. Locations of ecological and social surveys were also selected based on receptor locations; in addition, special emphasis is given to areas within 1.5 km radius of the project site and distribution lines

## Project site setting

The proposed Mkokoni mini grid is in Lamu County. It falls under cluster 1 with a total of 147 minigrids and lot 4 which has a total of 49 mini-grids. Geographically, Mkokoni site falls on coordinates latitude 1°58'1.07"S and longitude 41°17'43.27"E.

Figure 5: Map Showing the KOSAP Counties Lot 3

Figure 5: Map Showing the KOSAP Counties Lot 3

### Project cost

Mkokoni solar project cost is estimated at USD. 503,914

## Land Requirement and Procurement Process

### Land Requirement

The land on which the proposed Mkokoni Mini grid will be constructed covers a total 0.411 Ha in size.

#### Land Tenure

Majority of land in Lamu county is categorized as unsurveyed community land. In Mkokoni, the site falls on a public land that belongs to National Police Service (NPS).

#### Compensation Details

The project location had initially targeted a community land. The proposed location however is on a public land and does not require compensation.

## Description of Project Facilities, Components and Activities

| Residential Users (No.) | 251 |
| --- | --- |
| Non-Residential Users (No.) | 6 |
| PV Capacity (kWp) | 91 |
| Battery Capacity (kWh) | 296 |
| PV Inverter (kW) | 76 |
| Generator Capacity (kVA) | 50 |
| Fuel Tank for diesel generator (Litres) | 2,000 |
| LV Network (km) | 8 |

Key Components of the Project:

Power Generation Sources:

Solar Photovoltaic Panels: The project utilizes solar panels with a total capacity of 91 kWp to harness solar energy. Solar power is a clean and renewable energy source that will provide a significant portion of the electricity needed for the project.

Battery Energy Storage System: A 296 kWh Battery Energy Storage System is incorporated to store excess solar energy during the day, ensuring a consistent power supply even during cloudy or nighttime conditions.

Diesel Generator: A 50 kVA diesel generator is included to serve as a backup power source for periods of low solar generation or in case of battery depletion. It provides reliability and backup in the event of extended periods of cloudy weather or high demand.

Fuel Tank for Diesel Generator: A 2,000-liter fuel tank is provided to store diesel fuel for the generator, ensuring continuous operation during extended periods of low solar or high demand.

Inverters and Chargers:

PV Inverter: A 76 kW solar PV inverter is used to convert the direct current (DC) electricity generated by the solar panels into alternating current (AC) electricity suitable for consumer use.

Battery Inverter Charger: A 41 kW battery inverter charger is employed to manage the energy flow to and from the battery storage system. It ensures efficient charging and discharging of the battery, maximizing the system's overall performance.

Low Voltage Power Distribution Network:

A 8-kilometer Low Voltage (LV) power distribution network is established to distribute the generated electricity to the residential and non-residential consumers. The LV network is designed to efficiently transmit power while minimizing losses, ensuring a stable supply to the customers.

Project Metrics:

Monthly Energy Demand: The project is expected to meet a total monthly energy demand of 10,601 kWh.

Daily Energy Demand: The average daily energy demand is approximately 353 kWh, ensuring a consistent supply for the consumers.

Peak Demand: The peak demand of the system is 24 kW, which is the maximum power requirement during any given moment.

PV Capacity: The solar photovoltaic panels have a total capacity of 91 kWp.

### Project Components

#### Solar PV modules

The project will use PV Array (DC-kW) polycrystalline silicon module with three strings connected in series. Each string will have five sets of panels connected in series, with output converged at the six-way combiners. The life expectancy of the PV modules is estimated at 25-30 years.

#### Battery Energy Storage System

The Battery Energy Storage System (BESS) will comprise of Lithium-ion Battery pack that conforms to IEC standards with warranty of 10 years, 3,000 cycles minimum. The Lithium-ion Battery Power Packs will be used to cater for required energy capacity, or equivalent as per approved design, minimum 80% DOD for Lithium-Ion. Batteries will be capable of at least C/4 charge and discharge rate. Batteries will be charged by Battery Inverter / Charger.

#### Battery Inverters/ Chargers

The Inverters/charges shall be designed for nominal voltage of 415 Vac which will be continuous, reliable power supply as per specification and shall have internal protection arrangement against any sustained fault in the feeder line and against lightning strikes in the feeder line. The inverters shall be capable of complete automatic operation including wake-up, synchronization & shut down independently & automatically. The inverter shall be 3-phase multi-mode (DC to AC and AC to DC), bi-directional, four-quadrant capability.

#### Distribution lines

The site will have a distribution line circuit of 8km in total. Supply of concrete poles for the distribution lines will be based on detailed survey and accessories like phase plates, circuit plates, number plates, danger plates, anti-climbing devices as per KPC requirements/specifications. Erection of the Poles, fixing of insulator strings, stringing of conductor and earth wires along with all necessary line accessories and earthing will be as per KPC requirements/specifications.

### Architecture and Basic Design Specifications

This hybrid power generation site is projected to generate 91 (kWp) and is meant to serve approximately 257 households (customers). The proposed mini-grid installations will be built to comply the International Electro technical Commission (IEC) standards. It will have an installation of solar panels of with a capacity of 91 (kWp) and battery house with 296 kWh. The solar panels will have a connection to the batteries through underground cables. The standby generator will also be connected to the system as a backup.

This generator will be a capacity of 50 kVA capacity with a fuel tank. To optimize this hybrid system the HOMER software will be used. The goal of the hybridization of diesel systems is to reduce fuel consumption by switching off diesel generator set(s) for several hours a day, in order to reach a PV energy, share in the final mix of at least 60% or more. The power will be distributed to the customers by overhead lines. The project site is expected to serve clients within a radius of 6km from the site (generation source).

The PV plant and the battery capacity have been sized accordingly to the daily demand and the solar resources. In addition to this Design architecture, the project site shall have a site office that shall also have a Control Room adjacent as well as a guard house. The guard house shall be constructed using concrete and masonry works whereas the control room and office can also be a containerized facility.

The Solar PV hybrid system is based on a centralized photovoltaic plant connected to a 3-phase 415V AC busbar line, where the multi-mode battery inverter and the diesel generator are also connected.

The plant is configured such that a significant portion of daytime loads is fed directly from the solar generator (grid-tie inverter) without intermediate battery storage usage. The solar PV power plant is also equipped with a Diesel Generator, which is normally used as reserve power. The diesel generator switches on automatically whenever the battery state of charge reaches a certain defined DOD (Depth of Discharge). The diesel generator comprises of 50 kVA unit in three-phase operation and it’s equipped with automatic startup function controlled by the battery inverter charger.

### Project Phases and Activities

The main project activities include site clearance and leveling, civil works and construction of utilities and structures for the facilities, installation, and connection of the power plant.

#### Construction Procedures

The project will be constructed based on applicable standards of Kenya, environmental guidelines and health and safety measures in line with OSHA Act 2007.

The project inputs will include the following.

- Construction of raw materials will include solar modules, inverter, wires, metals, among others. All these will be obtained from licensed dealers and especially those that have complied with the environmental management guidelines and policies.

- Construction machines will include machinery such as trucks, and other relevant construction equipment. These will be used for the transportation of materials, clearing of resulting construction debris.

- A construction labour force of both skilled and non-skilled workers will be required.

Construction activities will include the following:

- Contractor mobilization.

- Site Preparation.

- Procurement of construction material from approved dealers and transport to the site.

- Storage of PV modules delivery and their installation.

- Laying of internal electrical connections.

- Installation of inverters, Battery Energy storage system.

#### Land Tenure

Land ownership in Lamu can be categorized into three main categories namely; community land, public land and private land.  The site is on a public land registered under the National Police Service (NPS)-surveyed.

#### Compensation Details

The land provided is a public land and therefore will not require compensation. The community however listed their needs so as to be considered if the proponent may want to undertake a project for the community;

- Renovate and equip maternity wing provided at the dispensary, the dispensary is located at the southern part of shopping centre, or

- Provide for fencing around the school area and build one or more classrooms in Primary School.

## Resource Requirement

### Workforce Requirement

Approximately 40 skilled, semi-skilled and unskilled labourers will be required at the construction stage. During the operation phase, about 15 no. staff will be required of which 8 will be skilled staff comprising; 0ne operations and maintenance head, 2 engineers, 5 technicians and 2 security guards. Unskilled staff will be approximately 5 and will be hired for grass cutting and module cleaning.

### Water Requirement and Source

#### Construction Phase

It has been estimated that approximately 50,000 liters of water will be required per day for civil works during construction stage. Further, water will be required for workers at project site. However, this quantity of water requirement will vary depending on the mobilisation of construction workers at site. The water for the construction phase will be supplied by local water vendors.

#### Operation Phase

The water required during operation phase of the project will be mainly for washing the face of the solar modules, minimal water will be used for this purpose. The quantity of Water requirement during operational phase of the project is not known at this stage of the project. The water for the construction phase will be purchased from the vendors in the area.

As noted previously, approximately, employees (direct and contractual) will be working during operation phase. For this workforce, approximately 10,000 Litres of water will be required for domestic consumption.

### Raw Material Requirement

#### Construction Phase

The major raw materials required for the construction phase will be solar modules, fencing materials, construction materials like cement, sand, and aggregate. The fencing materials and the construction materials will be sourced from the local hardware facilities. Solar Modules for the project along with associated structures will be obtained from appropriate sources within or outside the country.

#### Operation Phase

There will not be major requirement of raw materials during operation phase. Only maintenance spares will be required at this phase.

### Power Requirement

Power requirement during the construction phase will be met through Diesel Generators sets. The exact number of Diesel Generator sets to be used, as well as the quantity of fuel, will be ascertained once the project design is finalized.

### Fire Safety and Security

#### Construction Phase

Appropriate firefighting system and equipment shall be provided throughout the construction period. The fire extinguishers will be well distributed according to the fire risks and will be available in areas such as the site office, security area, storage yard etc. A comprehensive emergency response plan with all the emergency numbers will be well displayed at the site and on the fence.

Signage, danger plates and name plates will also be displayed at the site. To prevent and avoid hotspots and their negative effect on solar panels, the panel design will take hotspot problems into consideration without obstructions of vegetation or building. Vegetation undergrowth will be controlled through regular slashing and cleaning up of the project site

#### Operation Phase

Suitable fire protection and fighting systems that will include portable fire extinguishers, automatic fire detection system and means of fire communication will be made available at the entire PV array area, inverter stations, main control room and switchyard. The facility will have an approximate of twelve (12) batteries 12 to a minimum of nine (9) due to the varied sizes of the batteries.

The systems and equipment’s will align to the Kenyan Fire Reduction Rules of 2007. The Fire protection and fighting systems will be maintained and serviced after every 6 months.

Because off-the-grid systems generally involve an underground wiring system, they are much less prone to weather accidents that lead to fires. They are also much smaller than the typical power grid, so if a fire were to start (against all odds), it would remain contained in a small area. The maintenance contractor using a Vegetation Management Program combining herbicides with mechanical methods will help provide effective vegetation control during the dry season.

An effective grounding system will be installed during power wiring for protection against lightning damage. In addition, lighting arrestors and surge protectors will be installed. To reduce hotspot effects, the contractor will ensure that panels are installed without obstructions. This means they won't be too close or in the shade of anything else, as this will cause shadows on each other.

Physical barriers consisting of conduits and short circuit withstanding capacity will be part of the design to prevent a rodent from gnawing on a cable during the operation phase. To ensure the workers are not exposed to occupational hazards from contact with live power lines and cables during maintenance, and operation activities will ensure they: employ prevention and control safety measures associated with live power lines; employ measures to prevent, minimize, and control injuries related to electric shock; all electrical installations should be performed by certified personnel and supervised by a certified person; ensure that there are no equipment, appliances and machinery with unsafe electrical conditions. No equipment or machinery with worn-out or un-insulated wires and conductors; and ensure all electric installations and cables are properly labelled.

The Mini grid facility will have neutralization kits for managing battery acid spills in case of spillage.

## Pollution Streams during Construction Phase

### Solid Waste Generation

#### Construction Phase

The key solid waste that is expected to be generated during construction phase include. Broken solar panels and PV Modules, Hazardous waste like waste oil, lubricants, oil contaminated rags and Domestic soil from the temporary site office.

The hazardous wastes will be stored onsite at separate designated covered area provided with impervious flooring and secondary containment. The storage containers/ bins/ drum will be clearly marked, and color coded for their hazards. The waste will then be collected by a NEMA approved waste handler.

Any broken solar panels or PV Modules will be sent back to the vendor as part of buyback arrangement. Alternatively, the e-waste will be disposed by licensed waste handlers in sites that are licensed by NEMA and local authorities to dump e-waste. All the other domestic solid waste will be disposed at the nearest municipality dumpsite.

#### Operation Phase

During operation phase, waste generated from the project will include domestic waste at site office, scrap materials like scrap tools, damaged PPEs etc.; hazardous waste like waste oil, lubricants, used oil; damaged batteries; electronic waste like damaged PV modules etc.

The hazardous wastes will be stored onsite at separate designated covered area provided with impervious flooring and secondary containment. The storage containers/ bins/ drum will be clearly marked, and color coded for their hazards. The waste will then be collected by a NEMA approved waste handler.

Any broken solar panels or PV Modules will be sent back to the vendor as part of buyback arrangement. Alternatively, the e-waste will be disposed by licensed waste handlers in sites that are licensed by NEMA and local authorities to dump e-waste. All the other domestic solid waste will be disposed at the nearest municipality dumpsite.

### Air Emissions

#### Construction Phase

Air quality will be impacted due to onsite construction activities. The likely emissions from construction activities would include the following:

- Dust emissions from the dusty roads leading to the site.

- Increased vehicular emissions due to the high traffic of vehicles transporting construction materials, PV Modules, and accessories.

- Dust emissions from site clearing, material handling, piling and use of the construction machinery.

- Exhaust emissions from the diesel generator.

The high dust emissions arising from various activities such as piling, transportation of material (loading and unloading), vehicular movement (on unpaved roads) should be minimized through sprinkling of water and maintaining vehicular speed to 10-15 km/hr.

All the vehicles and the Diesel generator should be well maintained and serviced to reduce the rate of exhaust emissions.

All waste tracking documents must be maintained onsite by the contractor.

#### Operation Phase

It is expected that the normal operations of the site will produce minimal gaseous emissions from all the operating areas. The minimal gaseous and fugitive dust emissions will be attributed to the in and out movement of the maintenance vehicles. It will be ensured that well maintained vehicles are used for maintenance purposes.

### Waste Generation

#### Construction Phase

The liquid effluents generated during the construction phase will include domestic sewage from temporary site offices, kitchen and washing areas. As part of the site preparation stage, septic tank will be constructed for the camp and site office. Sewage disposal trucks should be used to periodically remove the sludge/sewage from the septic tank.

#### Operation Phase

The operational phase will have negligible wastewater generation at site office. Septic tank and soak pits will be provided at the site office for disposal of sewage.

### Noise Emissions

#### Construction Phase

Noise emissions will be generated from piling, movement of vehicle and other construction machinery and operation of the Diesel Generator. The main noise receptors will be the neighboring settlements and the construction workers. Noise from Diesel Generators will be minimized through provision of acoustic enclosures and occasional maintenance of the generator. Every single noise generating activity will be restricted to Day time only.

#### Operation Phase

Under normal operations, none of the activities of solar power plant will generate noise. The only noise that can be generated at this phase is during the maintenance works and it will be restricted to daytime only. However, during cloudy periods and when solar energy is low, the backup generator that will be utilised will produce noise. Mufflers and silencers will be installed so as to minimize noise pollution from the backup generator.

# BASELINE SETTINGS- ENVIRONMENT AND SOCIAL

## Study Area

The project site is located in Mkokoni village, Kiunga ward in Lamu East subcounty, Lamu county. Based on the secondary information of the region, the sampling locations were identified to obtain the representative baseline information. Sampling locations for underground water quality was selected based on the drainage pattern of the area. Soil sampling locations were selected based on the land use and land cover of the study area. Locations of ecological and social surveys were also selected based on receptor locations; in addition, special emphasis is given to areas within 1.5 km radius of the project site and distribution lines.

## Environment Baseline

### Geology and Soil

Mkokoni area is generally covered with sandy loam to sandy soils. Lamu County is characterized by Quaternary to Recent sediments mainly of, limestone and coral reef stones. It has distinct sandstone facies which formed from the Permo-Carboniferous through the Tertiary in four Mega-sequences that show variation in grain sizes, porosity, permeability, compaction, shaliness and cementation. This geology influence groundwater availability. The hydrology of the area is highly influenced by the topography and geology of the area with rivers flowing south easterly from the north western area to the sites and flowing into the Indian Ocean coastline.

### Topography

The site is generally flat with an elevation difference of below 0.5m observed within the project site. The general slope of the surrounding areas leads into Indian ocean located on the Southern part at about 0.5km from the project site and along latitude 1°58'1.07"S and longitude 41°17'43.27"E. Lamu County is a physically diverse county and lies between 0 meters and 68 meters above sea level. The topography of the project site is gently sloping southwards to Indian Ocean. The county is prone to seasonal flooding during the rainy seasons which makes roads impassable.

### Hydrogeology and Drainage

Geologically, major parts of the Lamu East sub county are occupied by limestone karsts and sandstones. The area is marjorly sandy with ocean shores and archipelagoes located at a close proximity to the site (between 1-2km). The nearest river is located in Dodori forest and swampy areas to the north and eastern areas that provide evidence of groundwater in the area.

The hydrology of the area is highly influenced by the topography and geology of the area with rivers and streams flowing south easterly in a direction perpendicular to the Indian Ocean coastline.

### Ground Water Development

The ground water resources were majorly identified during the site assessment by means of observation and selected data hydrological model of the area. The site has a borehole indicating presence of underground water, the water is slightly salty.

## Ecological Conditions

The different agro-ecological zones in the county are highly influenced by the rainfall variability patterns experience throughout the County and somehow define the natural potential of Lamu County. As such the county can be sub divided into two livelihoods zones with varying economic diversities which are distinct in terms of ecology, infrastructural network and population distribution. The area, Mkokoni; the rich agricultural and fishing zones in the mainland (mainly settlement schemes) and the fishing and marine zones (Islands).

The project area located in Kiunga Ward, Lamu East sub county in Lamu County, the area encompasses scarce tree species. Lamu county has a robust ecological system that residents depend on for agriculture, the main crops in these areas include fruit and nut trees such as coconut, mangoes and cashew nuts; and cereals such as simsim, maize, and bixa. Cotton, water melons and pulses, are also grown in the area. The habitats range from highly productive near-shore regions within the Lamu Archipelago of islands, channels and creeks, to off-shore coral reefs, to the deep-sea habitats. The Kiunga-Lamu seascape features rich marine habitats such as mangroves, sea grass and coral reefs and sustains a population of keystone species such as turtles, dugongs, sharks and dolphins.

The coral reef ecosystems support a rich biodiversity, which includes sea turtle’s species, fish species, six dolphin species and species of hard corals. Coral reefs in Lamu are found within the Kiunga Marine National Reserve (KMNR) as well as at the rest of the coastline, mainly occurring in patch reefs, with fringing reef in Kiunga, the northern part. The archipelago area has extensive mangrove forests. The northernmost islands are Kiunga located only 15 kilometers to the border with Somalia and are part of a major marine conservation area, the Kiunga Marine National Reserve. The reserve is an important.

Azadirachta indica

Azadirachta indica

Acacia senegal

Acacia senegal

Plate 2. View of site locality with some of the tree species present

Plate 2. View of site locality with some of the tree species present

Arecaceae

Arecaceae

## Climatic Conditions

Temperature is usually high ranging from 230 C to 300 C. The mean annual minimum and maximum temperatures range between 240 C to 340 C. Celsius respectively. The hottest months are December and April while the coolest months are May and July. The mean relative humidity in the County is 75%. The total amount of evapo-transpiration is 2,230m per annum, with the highest values occurring in March and September and the lowest in May.

The high relative humidity levels in Lamu discourage certain development land use aspects as the proposed coal Plant under LAPSSET as the resultant emissions will be absorbed in the evaporation processes resulting to destructive rains as opposed to productive rains.

### Community Profile

Mkokoni village is in Kiunga ward, Lamu East subcounty in Lamu County. It is located 40 km from Kiunga town. The top community development priorities are 1st electricity, 2nd mobile network 3rd market in that order. The village has been in existence for 71 years. Houses in the community are mainly African manyatta made of “makuti” thatched mud walled houses. The community support mechanism includes Kiboko CBO that deals with conservation of animals, there were no other identified community support organizations. The main ethnic groups are the Bajun group with also Awer ethnic group present as a minority in the area. Islam is the dominant religion. Below is a summary of demographic profile of Mkokoni.

| Attribute | Magnitude/Number |
| --- | --- |
| Approx. population | 1,200 |
| Households | 200 |
| Gender. | Male – 65% Female – 32% |
| Ave. No. per household | 6 per household |
| Indigenous | Indigenous (Bajun) - 75% Settlers (Awer) - 25% |
| Vulnerable classes | PLWDs, the poor |
| Dominant ethnic group | Bajun |
| Primary religion | Islam |
| Other groups | Awer |
| Employment (formal/Informal) | Formal – Less than 1% Informal – 99% |

Table 13. Demographic profile of Mkokoni

### Socio-economic status of Study Area

#### Demographic Profile

The information shared on community profile by the area chief (Kiunga location) showed that Kiunga location has a population of approximately 1,200, and with an estimated number of households to be 200 with an average of 6 people. Mkokoni has a gender ration that is currently estimated to be about 35% male and 65% female.

#### Educational Infrastructure

The village has only one primary school - Mkokoni Primary School located at about 200m south of the site. the school is at an easily accessible area to the community settlement points.

#### Occupation and Livelihood Profile

Mkokoni community are mainly farmers and a few pastoralists. The main crops grown in Kiunga is for subsistence use, the crops include; maize, cashew nuts and mangoes and goats being the main animals kept in the area. The community rely of crop products for food at the household level and some for sale in Lamu. The goats kept within the area are consumed and sold kept for sale. Formal employment is <1%. Other sources of income in the society include sale of fish, retail shops and other businesses.

#### Land Use

Land in the community is mainly communal. The land is used for homesteads, crop growing and mainly for agriculture, livestock grazing, underground water is also harnessed from the land.

#### Health facilities

Mkokoni has only one public health dispensary with one female nurse and a support staff. Main service provided is Out-patient, maternity, antinatal care, child welfare, family planning, cancer screening and immunisation services. The facility however has inadequate supply of water.

#### Social and Physical Infrastructure

Water: There are two sources of water in the village; hand dug well and commercially available water.

Water from hand dug wells are supplied to the community through common water points stationed at strategic points within Mkokoni area.

Potable water is commercially accessible and the community buys it at 20 shillings per 20litres of water.

Sanitation: Private toilet facilities are provided in the school, dispensary, Mosque and nearly all the households within the area.

Road Network: Road’s connectivity within the area is also poor and not regularly maintained. The main forms of transport within the area are Motor bikes, taxis and Matatus. The other main transport connectivity to the area is the waterway connecting from Lamu mainland at Mokowe through Kiwayu to the Mkokoni.

Mobile Network Coverage: there is no reliable network connectivity within the area. Calls can be made only along the coastline and available only for Safaricom network. There are no internet services within this area.

Power/electricity: - the community is not connected to the mains. The population use mainly portable solar at the household for charging mobiles and lighting.

## Site Selection

Solar projects are non-polluting energy generation projects which are site-specific and dependent on the availability of solar irradiance resource.

The proponent identified one location for the proposed solar project which located to the immediate North of Mkokoni AP Post. The site was identified based on the location of settlement areas, commercial/ public facilities and land availability in Mkokoni. The site is within 500m to the shopping center and at a accessible point to the business premises and settlement areas within Mkokoni. The project extent is provided as shown in Figure 7 below.

Further details on the other locations identified were not available.

- No settlement present in the project site;

- The project site land is a surveyed public land for National Police Service;

- The project site has shrubs, bushes and trees and is located next to Kiunga-Mkokoni Road and the AP Post offices to the immediate south;

The proposed project site has the following location advantages:

- The area is in a predominantly fishing and farming setting. The population is dense within shopping centre where they majorly rely on fishing a trading activity, and majority of the surrounding land is use for agricultural purposes. Apart from fishing, the residents majorly grow maize, cashewnuts and mangoes for domestic and economic purposes. The land area within is also utilised for rearing goats with a significant impact on grazing land. The community is further marginalised with no electricity grid connectivity compared to other regions in the country.

- The land is unoccupied and does not have any ecological sensitive receptor such as national parks, Wildlife Sanctuary within 10 km radius. The site however borders Indian Ocean at about 500metres to the south, and

- Mkokoni station’s power supply is from an electric generator owned by WWF with the closest available power from is from mini-grid located in Kiunga Township at about 35 km away.

Figure 7: Proposed Project Site & Proximity to Consumer Sites

Figure 7: Proposed Project Site & Proximity to Consumer Sites

## Power Scenario at Mkokoni

Kiunga location has an estimate of 1,200 number of people with approximately 200 households within the area. The proposed solar off grid project is estimated to cover up to 257 residential and non-residential consumers within the area.

The existing sources of energy at Kiunga location include solar powered appliances supplied by private enterprises. The current energy availability provided by the solar appliances is insufficient and does not meet the objective of the aim of project. Solar energy is mainly utilized for lighting and charging mobile phones. Whereas wood fuel, charcoal and lpg gas is utilized for cooking, heating water and providing for warmth.

The use of firewood contributes to massive environmental degradation, increased health risks and additional workload for women and girls, and increased emissions of carbon content. Moreover, low enrollment, retention and transition for girls is partly attributed to increased workload related to energy search (firewood).

Currently, Mkokoni station’s power supply is from an electric generator owned by WWF. Power is supplied to staff quarters and bandas during the night and to offices when needed.  However, operating a generator is expensive and not eco-friendly. It is therefore important solar power be installed at Mkokoni and the other administration stations that will be established.

The county has a huge potential for renewable energy which can tapped through wind and solar energy and hence be channeled to productive sectors within the county as well as export to other counties.

Failure to construct and operate the minigrid in Mkokoni will lead to the failure of achieving one of the Kenya’s national long-term development policies that aims to transform Kenya into a newly industrializing, middle-income country, by providing a high quality of life to all its citizens by 2030 in a clean and secure environment. PAPs will be households, public and community institutions, enterprises and community facilities that cannot access electricity through the national grid and whose use of electricity will replace kerosene and other fuels for lighting and other activities like pumping water.

## Analysis of Alternative

As per IFC Performance Standards, an analysis of probable alternatives for the chosen technology and location of project site along with other similar factors that contribute to the project as a whole has been carried out. The following scenarios have been taken into consideration:

- Alternate Location for Project Site

- Alternate Sources of Energy

- Zero or No Project Alternative

### Alternate Location for Project Site

In determining the most appropriate site for the establishment of the minigrid, several options were explored. This site selection process considered the following criteria:

- Geophysical Factors-Proximity to Hills-Shade effect, Soil erosion, Drainage of the area, Flooding etc.

- Land identified is free from any dispute on ownership or any other encumbrances

- Proximity to public utilities-Schools, Dispensaries, Places of worship and community settlements

- No squatters, encroachers or other claims to the land

- 5. The Size of the Mini-grid to be constructed and the optimal coverage of a Mini-grid in terms of the      number of people to be reached.

- The Land identified should be on spaces set aside for public use within the community centres.

Mkokoni was identified as the most suitable area for the establishment of the proposed minigrid based on the following factors:

Location: The area is in a predominantly pastoral and fishing setting. The population density is low, and majority of the surrounding land is idle with shrubs and bushes. There is enough grazing land for the community and use of the site to construct the mini grid will not significantly impact grazing land whereas fishing is undertaken is also undertaken in the near ocean fronts away from the site.

Proximity to consumer sites: Kiunga location has an estimate of 1,200 number of people with approximately 200 households within the area. The proposed solar off-grid project is estimated to cover up to 257 residential and non-residential consumers within the area.

### Alternate Sources of Energy

Harnessing solar energy is an eco-friendly process, with an inexhaustible solar resource and minimal pollution. There are minimal fuel requirements for operational activities. Solar energy has a short development timeframe, more predictable energy output and low maintenance costs as compared to some other forms of renewable energy sources.

The possible alternatives to solar energy include;

- Wind power: shortfalls associated with wind power includes; lack of time series data of wind, trained human resources to intricate design of wind power etc., providing wind power for Mkokoni residents is technically and financially challenging, expensive to install, dependent on wind pattern (not strong in Mkokoni). However, generation is cheap, low emissions & insignificant pollution levels.

- Thermal power: High fossil consumption, high emissions levels, high water consumption levels (water highly scarce in Mkokoni). Besides coal and petroleum products used in thermal power processing are not readily available within Mkokoni area and may have to be sourced from far locations. Therefore, thermal power option based on coal and petroleum products is not a viable option for Mkokoni. It however has high distribution and large-scale production potential

- Nuclear power: disadvantages include; use of other fuel sources, has hazards associated with radioactive materials, expensive disposal of waste, high cost of project and long gestation period. The mode however does not emit smoke particles, low fuel cost, low emission levels and continuous electricity production.

- Wood fuel/ Firewood: The use of firewood and solid waste for electricity generation using thermal technology is another option. But the issue of air pollution and destruction of vegetative cover through firewood harvesting and charcoal burning already are environmental problems of serious concern which will further aggravate the natural environment. For these reasons, the wood fuel options evaluated above seem inappropriate for Mkokoni on environmental as well as economic grounds

- Fossil fuel

Solar energy was a desirable option because:

- It has low energy-production costs

- The project is environment friendly with minimal greenhouse gas emissions

- Versatile installation

- It is a clean source of energy hence minimal impact on the environment air quality

- Economic savings.

### Zero or No Project Alternative

The No Project option in respect to the proposed project implies that the status quo is maintained. This option is the most suitable alternative from an extreme environmental perspective as it ensures non-interference with the existing conditions. This option will, however, involve several losses both to Mkokoni area and Kiunga ward as a whole. The village and the surrounding area will continue to have no electricity, and this will not help in maximizing and utilizing the area facilities. The No Project Option is the least preferred from the socio-economic and partly environmental perspective due to the following factors:

- The economic status of the local people would remain unchanged.

- Employment opportunities will not be created.

- Increased poverty in the area.

From the analysis above, it becomes apparent that the No Project alternative is no alternative to the local people, Kenyan Government, and Investors.

### Analysis of Alternative Construction Materials and Technology

The proposed project will be constructed using modern, locally, and internationally accepted materials to achieve public health, safety, security, and environmental aesthetic requirements. These may not be desirable from a cost and durability perspective. The technology to be adopted will be the most economical and one sensitive to the environment.

### Conclusion

The proposed project should be upheld to support the local community based.

# APPLICABLE AND REGULATORY FRAMEWORK

## Introduction

This Chapter outlines the existing national and international environmental and social legislation, policies, and institutions applicable to energy generation that guide the development of the Project.

As Kenya is a signatory to various international conventions and laws, national projects need to be aligned with their requirements; relevant international conventions and laws are therefore presented in this chapter.

Finally, a summary of the World Bank (WB) Environmental and Social operational policies. S relevant to this Project are presented.

## Kenya Policy Provisions

### Kenya Energy Policy, 2014

The Energy Policy sets out the national policies and strategies for the energy sector that align to the Constitution of Kenya and Kenya’s Vision 2030.

The Energy Policy envisages promoting an energy mix that includes solar energy at both the household/institutional levels as well as large-scale solar energy generation. The Government of Kenya has initiated and has been promoting programmes for the provision of electricity to institutions far from the grid through solar PV systems. The Government has also embarked on a programme to provide solar/diesel and solar/wind hybrid generation capacity to off-grid stations.

The Policy strategizes the need to:

- promote the widespread use of solar energy while enforcing existing regulations and standards.

- provide incentives to promote the local production and use of efficient solar systems.

- provide a framework for connecting electricity generated from solar energy to the national and isolated grids, through direct sale or net metering.

- promote the use of hybrid power generation systems involving solar and other energy sources; and

- facilitate the generation of electricity from solar energy by, among other things, funding, provision of land, fast-tracking issuance of permits and licenses, as well as acquisition of data and information to realize at least 100 MW from solar by 2017, 200 MW by 2022 and 500 MW by 2030.

The Kenya Electricity Supply Industry (ESI) is one of the sub-sectors in the energy sector which the Ministry of Energy and Petroleum oversees on behalf of the Government of Kenya (GoK). Under the Energy Act of 2006, the Ministry is responsible for formulation and articulation of policies to provide an enabling environment for operators and other stakeholders in the energy sector.  Relevant stakeholders in the ESI are briefly described below.

Table 7. Kenya power stakeholders and their roles

| Stakeholders | Role |
| --- | --- |
| Kenya Power Company | Responsible for distribution and retail supply of electrical energy to end users. Kenya Power purchases power in bulk from the Kenya Electricity Generating Company Limited (KenGen) and the Independent Power Producers (IPPs) through bilateral contracts or Power Purchase Agreements (PPAs) approved by the Energy Regulatory Commission (ERC) (). |
| The Energy and Petroleum Regulatory Authority (EPRA) | Established by the Energy Act of 2019. The EPRA’s mandate extends beyond electricity and includes natural gas (including petroleum), renewables and all other forms of energy. The generation, transmission, distribution, supply, import and export of electricity can only be carried out by parties in possession of a license, or a permit issued by the EPRA. If the capacity involved is for own use and less than 1 MW, authorization is not required. Although the generated electricity is expected to be less than 1 MW (0.3 – 1 MW), the fact that the generated electricity is intended for use in a factory and there is a possibility for connection to the national grid and sale of excess power to the government, The project requires a license from the EPRC to generate electricity as stipulated in the Energy Act, 2019. |
| Ministry of Energy and Petroleum | Aims to facilitate provision of clean, sustainable, affordable, reliable, and secure energy services for national development while protecting the environment. |
| The Rural Electrification and Renewable Energy Corporation (REREC): | Is established under Section 43 of the Energy Act, 2019 as a corporate body. The Corporation is the successor to the Rural Electrification Authority established under section 66 of the Energy Act No. 12 of 2006 (now repealed) and subject to this Act, all rights, duties, obligations, assets and liabilities of the Rural Electrification Authority existing at the commencement of this Act is to be automatically and fully transferred to the Corporation and any reference to the Rural Electrification Authority in any contract or document shall, for all purposes, be deemed to be a reference to the Corporation. |
| The Geothermal Development Company (GDC): | Is a 100% state-owned company, formed by the Government of Kenya as a Special Purpose Vehicle to fast track the development of geothermal resources in the country. The creation of GDC was based on the government’s policy on energy - Sessional paper No. 4 of 2004, and the energy Act No. 12 of 2006. |
| The Kenya Electricity Transmission Company (KETRACO): | Was incorporated on 2nd December 2008 and registered under the Companies Act, Cap 486 pursuant to Sessional paper No. 4 of 2004 on Energy. KETRACO’s mandate is to design, construct, operate and maintain new high voltage electricity transmission infrastructure that will form the backbone of the National Transmission Grid, in line with Kenya Vision 2030. |
| Energy and Petroleum Tribunal (EPT): | The tribunal is established under section 25 of The Energy Act, 2019. The tribunal is established for the purpose of hearing and determining disputes and appeals in accordance with The Energy Act, 2019 or any other written law. In relation to the proposed Project, any disputes or appeals if they arise will need to be addressed by the EPT. |

### Policy paper on Environment and Development (Sessional Paper No. 6 of 1999)

The overall goal of this Sessional Paper is to ensure that environmental concerns are integrated into the national planning and management processes and provide guidelines for environmentally sustainable development. The objectives of the Paper are to conserve and manage the natural resources of Kenya including air, land, flora, and fauna and promote environmental conservation about soil fertility and conservation, biodiversity, to foster afforestation activities, and to protect water catchment areas. More importantly, the Policy emphasizes the enhancement of public awareness and appreciation of the essential linkages between development and environment, involving NGOs, private sector, and local communities in the management of natural resources and their living environment and ensures that an environmental impact assessment report is undertaken for all public and private projects and programmes.

The proposed solar plant facility must ensure that it promotes this integrated approach to environmental management and development, without compromising the livelihoods of the local community.

### National Policy on Water Resources Management and Development, 1999

While the National Policy on Water Resources Management and Development enhances a systematic development of water facilities in all sectors for promotion of the country’s socio-economic progress, it also recognizes the by-products of this process as wastewater. The Policy therefore calls for development of appropriate sanitation systems to protect people’s health and water resources from institutional pollution. This implies that industrial and business development activities should be accompanied by corresponding waste management systems to handle the wastewater and other waste emanating therefrom.

During construction, water will be required for concrete works and during the operational period water supply may be necessary for cleaning the PV modules.  Appropriate water treatment and waste handling must be incorporated into the Project design to be in alignment with this policy.

### Sessional Paper No. 10 of 2014 on the National Environmental Policy, 2014

The overall goal of this Session Paper is to ensure better quality of life for present and future generations through sustainable management and use of the environment and natural resources. This Session Paper calls for the use of environmentally sound technologies based on the best available techniques and policies as a way of minimizing negative impacts to the environment.

Section 5.6 of this Session Paper focusses on infrastructure development and environment and makes explicit policy statements to ensure sustainable management and use of the environment and natural resources during the construction and operation of infrastructure developments. These policy statements require the commitment of the government to:

- Ensure Strategic Environmental Assessment (SEA), Environmental Impact Assessment, Social Impact Assessment and Public participation in the planning and approval of infrastructural projects.

- Develop and implement environmentally friendly national infrastructural development strategy and action plan.

- Ensure that periodic Environmental Audits are carried out for all infrastructural projects

In line with the above policy statements, this ESIA has been conducted for the proposed solar project (including the associated infrastructure) to ensure that environmental and social issues are appropriately addressed.

Once approved by NEMA, the Project Proponent will also need to conduct periodic Environmental Audits to ensure continuous conformity with the overall goal of this Session Paper. In addition, this ESIA has considered analysis of alternatives including alternatives to technology to ensure that the best available and appropriate technology is used.

## National Legal Framework

### Administrative Framework

In 2001, the Government established the administrative structures to implement the Environmental Management and Co-ordination Act of 1999 (EMCA). The main administrative structures are described in the following sections:

Table 8. Administrative stakeholders and their roles

| Stakeholders | Role |
| --- | --- |
| NEC | The National Environmental Council is responsible for policy formulation and directions for the purposes of EMCA. The Council also sets national goals and objectives and determines policies and priorities for the protection of the environment. The proponent should ensure that the project abides by the set goals and objectives of the Council. |
| NEMA | The responsibility of NEMA is to exercise general supervision and co-ordination over all matters relating to the environment and to be the principal instrument of Government in the implementation of all policies relating to the environment. This ESIA has been prepared for submission to NEMA for review and approval prior to the commencement of the Project activities, in compliance to the EMCA. |
| PCC | EMCA has also established a Public Complaints Committee, which provides the administrative mechanism for addressing environmental harm. The Committee has the mandate to investigate complaints relating to environmental damage and degradation. The members of the Public Complaints Committee include representatives from the Law Society of Kenya, NGOs, and the business community. The proponent should address all issues arising from the Project in accordance with the above requirements, including a clear policy of stakeholder engagement and feedback. |
| WRA | Water Resources Authority is responsible for regulation of water resources issues such as water allocation, source protection and conservation, water quality management and pollution control and international waters. One of its functions among others is to receive water permit applications for water abstraction, water use and recharge and determine issue, vary water permits; and enforce the conditions of those permits as well as formulate and enforce standards, procedures and Regulations for the management and use of water resources and flood mitigation. The project area experiences serious water scarcity. The proponent will have to purchase water for use during construction. |

## Relevant statutes

The current legal provisions for natural resource management in Kenya are contained in over seventy sector-specific statutes. For a long time, the country lacked an umbrella legislative guide for harmonious and holistic environmental management. As such, resources were managed sectoral in accordance with the statutes that were in place.

As these statutes were contradictory at times, in 1999, the Government of Kenya enacted the Environmental Management and Co-ordination Act (EMCA) which is an umbrella legal framework under which the environment is being managed. EMCA establishes the institutional framework under which environmental management is to be coordinated. EMCA prevails over all other Sectoral laws relating to the environment in cases of conflict or contradictions. It also grants the public a locus standi in matters of the environment.

Table 9. Policy and Legislative Framework

| S.No. | Legislation/ Guidelines | Description of the Legislation/Guidelines | Relevance of the legislation/Guidelines |
| --- | --- | --- | --- |
|  | NATIONAL POLICY |  |  |
|  | Vision 2030 | Kenya Vision 2030 is the current national blueprint for development from its inception in 2008 until the milestone year of 2030. This plan is the national long-term development policy that aims to transform Kenya into a newly industrialized, middle-income country by 2030. The Vision is comprised of three key pillars (economic, social, and political), two of which are projected to be positively affected by project implementation. | Under Vision 2030, Energy is identified as one of the key sectors that form the foundation for socio-political and economic growth. Promoting equal opportunities across the entire Kenyan territory and enhancing access to competitively priced, reliable, quality, safe and sustainable energy is essential to the achievement of this vision. |
|  | National Environmental Action Plan (NEAP) of 1994 | The NEAP for Kenya was prepared in mid 1990s. It was a deliberate policy whose main effort is to integrate environmental considerations into the country ‘s economic and social development. The integration process was to be achieved through multi-sectoral approach to develop a comprehensive framework to ensure that environmental management and the conservation of natural resources forms an integral part of societal decision-making. | The NEMA does not approve a development project unless the impacts of the proposed project are evaluated and mitigation measures proposed for incorporation in the project ‘s development plan, which is in line with the requirements of the NEAP. The project will be reviewed by NEMA for approval before implementation. |
|  | The Poverty Reduction Strategy Paper (PRSP) of 2001 | The PRSP has the twin objectives of poverty reduction and enhancing economic growth. The paper articulates Kenya ‘s commitment and approach to fighting poverty; with the basic rationale that the war against poverty cannot be won without the participation of the poor themselves. | The proposed project aims at provision and access of renewable electricity geared towards improved economic performance and thus will contribute to poverty alleviation in the project area. |
|  | Environmental and Development Policy (Session Paper No.6 1999) | As a follow-up to the foregoing, the goal of this policy is to harmonize environmental and developmental goals to ensure sustainability. The paper provides comprehensive guidelines and strategies for government action regarding environment and development. | The proponent: - Is undertaking an Environmental Impact Assessment, Social Impact Assessment and Public participation as part of the planning and approval of infrastructural projects. - Will ensure that periodic Environmental Audits are carried out for the project |
|  | The Gender and Development Policy (Sessional paper no.2 2019) | The overall goal of this policy is to achieve gender equality by creating a just society where women, men, boys, and girls have equal access to opportunities in the political, economic, cultural, and social spheres of life. | In the absence of appropriate measures, the project can exacerbate gender inequalities and sexual and gender-based violence. In adherence to this policy, measures will be put in place to: - ensure gender inclusivity in decision making, employment opportunity and access to the energy generated from the Mini-Grid - mitigate social risks including sexual and gender-based violence, and any form of discriminations |
|  | The HIV/ AIDS Policy 2009 | In summary, the policy aims at: - Establishing and promoting programmes to ensure non-discrimination and non- stigmatization of the infected. - Contributing to national efforts to minimize the spread and mitigate against the impact of HIV and AIDS. - Ensuring adequate allocation of resources to HIV and AIDS interventions; | The proposed project is to be implemented in the rural setting a Mkokoni. The area is not economically empowered hence few HIV/AIDS prevention resources are available. This policy shall provide a framework to both the project proponent and contractor to address issues related to HIV/AIDS during the entire project phase. |
| National Laws |  |  |  |
|  | The Constitution of Kenya, 2010 | The Constitution of Kenya promulgated in 2010 is the supreme law of the republic and binds all persons and all State organs at all levels of government. The Constitution provides the broad framework regulating all existence and development aspects of interest to the people of Kenya, and along which all national and sectoral legislative documents are drawn. | The proposed project complies with the Constitution by proposing a structure in its ESIA on how to deal with Social, Health, safety and environmental issues for sustainable development. |
|  | Environmental Management and Coordination Act, 1999 (And the Amendments Of 2015) | The EMCA is a framework environmental law in Kenya. This Act (assented to on January 14, 2000) provides a structured approach to environmental management in Kenya. With the EMCA coming into effect, the environmental provisions within the sectoral laws were not superseded; instead, the environmental provisions within those laws were reinforced to better manage Kenya’s ailing environment. | The proposed project will be undertaken in accordance with relevant sections of the EMCA, specifically Clauses 58 – 63. These sections of the Act are operationalized by subsidiary legislation promulgated under the Act and specifically Legal Notice (L.N.) 101: Environment (Impact Assessment and Audit) Regulations, 2003. |
|  | L.N. 101: EIA/EA Regulations, 2003 And 2016 Amendments | These regulations provide the framework for undertaking EIAs and EAs in Kenya by NEMA licensed Lead Experts and Firms of Experts. An EIA or EA Study in Kenya is to be undertaken by a firm duly licensed by the NEMA. The EIA/EA Regulations also provide information to project proponents on the requirements of either an EIA or EA as required by the EMCA. | The proposed project is subject to relevant provisions of these regulations and subsequently, the ESIA has been undertaken in accordance with the requirements. |
|  | L.N. 120: Water Quality Regulations, 2006 | This regulation provides for the sustainable management of water used for various purposes in Kenya. The regulation contains discharge limits for various environmental parameters into public sewers and the environment. | The contractor will be required to properly manage the effluent from construction activities in accordance with the above regulations prior to discharge into the environment. |
|  | L.N. 121: Waste Management Regulations, 2006 | Generally, it is a requirement under the regulations that a waste generator segregates waste (hazardous and non-hazardous) by type and then disposes them in an environmentally acceptable manner. | Waste to be disposed in accordance with these regulations. |
|  | L.N. 61: Noise and Excessive Vibration Control Regulations, 2009 | The general prohibition of these regulations states that no person shall make or cause to be made any loud, unreasonable, unnecessary, or unusual noise which annoys, disturbs, injures, or endangers the comfort, repose, health, or safety of others and the environment. | Rules 13 and 14 of the regulations define the permissible noise levels for construction sites. These noise limits will be applicable to the proposed project. |
|  | Environmental Management and Coordination, (Conservation of Biological Diversity) (BD) Regulations 2006 | These regulations are described in Legal Notice No. 160 of the Kenya Gazette Supplement No. 84, December 2006. These regulations apply to conservation of biodiversity which includes conservation of threatened species, inventory and monitoring of BD and protection of environmentally significant areas, access to genetic resources, benefit sharing and offences and penalties. Additionally, this regulation provides for the local enforcement of the International Convention on Biological Diversity (CBD). | The proposed project will impact biodiversity through clearance of vegetation on the proposed site. This will be done in strict adherence to ESMMP and revegetation of degraded site will be done as spelt out in the ESMMP |
|  | Environmental Management and Coordination, (Fossil Fuel Emission Control) Regulations 2006 | These regulations are described in Legal Notice No. 131 of the Kenya Gazette Supplement No. 74, October 2006. These regulations include internal combustion engine emission standards, emission inspections, the power of emission inspectors, fuel catalysts, licensing to treat fuel, cost of clearing pollution and partnership to control fossil fuel emissions. The proposed project will generate fuel emissions linked to the back-up generator. This will only happen when the sun rays are poor. | This legislation gives caution to proponent on proper handling and management of fuels.KP will adhere to the ESMMP while handling and managing the fuels |
|  | Licenses and Permits Required Under The EMCA | The subsidiary legislations under the EMCA are partially monitored using permits and licenses. Subsequently all licenses and permits required during the construction phase shall be the responsibility of the individual contractors and their agents. During the operational phase, all permits, and licenses required to operate the project will be the responsibility of the proponent. | The following permits to be available for inspection during the construction and operational phases of the project: - EIA License under Environmental Management and Coordination Act, 1999; - Workplace Registration under Occupational Safety and Health Act, 2007; - Construction Permit by the County Government; and - Noise Permit under Legal Notice 61: The Environment Management and Coordination (Noise and Excessive Vibration Control) Regulations, 2009. |
|  | Occupational Health and Safety Act, 2007 | The Occupational Safety and Health Act (OSHA) was enacted to provide for the health, safety and welfare of persons employed in workplaces, and for matters incidental thereto and connected therewith. | The contractors will be required to fully comply with Legal Notice 40 titled: Building Operations and Works of Engineering Construction Rules, 1984 (BOWEC). Each contractor will develop and implement a formal construction health and safety plan. |
|  | L.N. 31: The Safety and Health Committee Rules, 2004 | These rules came into effect on April 28, 2004, and require that an Occupier formalize a S&H Committee if there is a minimum of 20 persons employed in the workplace. The size of the S&H Committee will depend on the number of workers employed at the place of work | The contractor will be required to constitute Health and Safety Committee to oversee safety and health at the construction site |
|  | L.N. 24: Medical Examination Rules, 2005 | These rules provide for Occupiers to mandatorily undertake pre-employment, periodic, and termination medical evaluations of workers whose occupations are stipulated in the Eighth Schedule to the OSHA and the First Schedule to this Rules. Workers that fall under the above two schedules are required to undergo medical evaluations by a registered medical health practitioner duly registered by the DOSHS. | The contractor should that the workers exposed to hazards and or accidents undergo requisite medical examinations as required by these rules |
|  | L.N. 25: Noise Prevention and Control Rules, 2005 | The rules set the permissible level for occupational noise in any workplace (which includes construction sites) The Proponent is to ensure that - any equipment brought to the site for use shall be designed or have built-in noise reduction devices that do not exceed 90 dB(A). - those employees that may be exposed to continuous noise levels of 85 dB(A) are medically examined as indicated in Regulation 16. If found unfit, the occupational hearing loss to the worker will be compensated as an occupational disease. | The contractor to ensure that equipment is serviced properly and/or use equipment that complies with the threshold noise values provided in the act. Alternatively, each contractor will be required to develop and implement a written hearing conservation programme during the construction phase. |
|  | L.N. 59: Fire Risk Reduction Rules, 2007 | Several sections of the rules apply to the proposed project as enumerated below. - Regulation 16 requires Proponents to ensure that electrical equipment is installed in accordance with the respective hazardous area classification system. It is also a requirement that all electrical equipment is inspected every six months by a competent person and the Proponent is required to keep records of such inspections. - Regulation 22 provides a description of the functions of a fire-fighting team. - Regulation 23 requires Proponents to mandatorily undertake fire drills at least once a year. - Regulation 34 requires Proponents to develop and implement a comprehensive written Fire Safety Policy - Regulation 35 requires a Proponent to notify the nearest Occupational S&H area office of a fire incident within 24 hours of its occurrence and a written report sent to the Director of DOSHS within 7 days. | The proponent is expected to comply with the requirements of L.N. 59: Fire Risk Reduction Rules, 2007 by - Carrying out, and record, a fire risk assessment identifying any possible dangers and risks. - Reducing, or where possible remove, the risk of fire and take precautions to deal with the remaining risks. - Developing an emergency plan should a fire occur which includes evacuation procedures etc. |
|  | The Energy Act, 2019 | The Energy Act of 2019 deals with all matters relating to all forms of energy including the generation, transmission, distribution, supply and use of electrical energy as well as the legal basis for establishing the systems associated with these purposes. The Act also established the Energy and Petroleum Regulatory Authority (EPRA). | The proponent is in line with the Energy act regulations in the following ways. - The proponent has identified an available site - Alignment of the Mini-Grid Project to County development plans. - The Mini-Grid proponent has the technical and financial capability to conduct the project - The proponent has conducted the necessary engagement with the community. |
|  | Water Act, 2016 | Part 2 section one of the Act notes that every water resource is vested in and held by the national government in trust for the people of Kenya. Section 143 (1) notes that; A person shall not, without authority conferred under this Act- (a) Willfully obstruct, interfere with, divert or obstruct water from any watercourse or any water resource, or negligently allow any such obstruction, interference, diversion or abstraction; or (b) Throw, convey, cause or permit to be thrown or conveyed, any rubbish, dirt, refuse, effluent, trade waste or other offensive matter or thing into or near to any water resource in such manner as to cause, or be likely to cause, pollution of the water resource. | All construction, operation and decommissioning phases will take caution to refrain from polluting any water resource and will endeavour to prevent pollution in line with the ESMMP. |
|  | The Energy (Solar Photovoltaic Systems) Regulations, 2012 | These regulations shall apply to a solar PV system manufacturer, importer, vendor, technician, contractor, system owner, a solar PV system installation and consumer devices. The Regulations prohibits any person from designing or installing any solar PV system unless he/she is licensed by EPRA. | The Regulations regulates the design and installation of PV systems. The persons engaged in the designing and installation of the Mini-Grid shall be licensed by EPRA |
|  | The Public Health Act (Cap. 242) | The Act prohibits the proponents from engaging in activities that cause environmental nuisance or those that cause danger, discomfort or annoyance to inhabitants or is hazardous to human and environmental health and safety. | The proponent will be in line with the regulations of this act and will ensure suppression of infectious diseases and maintain proper sanitation during all the phases of the project. |
|  | The Standards Act Cap 496 | The Act is meant to promote the standardization of the specification of commodities, and code of practice; to establish a Kenya Bureau of Standards, to define its functions and provide for its management and control. | KP will ensure that commodities and codes of practice utilized in the proposed project adhere to the provisions of this Act. All materials and spares used to construct the project will comply with the standardized specifications and certification. |
|  | Penal Code Act (Cap.63) | Section 191 of the penal code states that if any person or institution that voluntarily corrupts or foils water for public springs or reservoirs, rendering it less fit for its ordinary use is guilty of an offence. Section 192 of the same Act says a person who makes or vitiates the atmosphere in any place to make it noxious to health of persons /institution, dwelling or business premises in the neighbourhood or those passing along public way, commits an offence. | KP shall observe the guidelines as set out in the environmental management and monitoring plan laid out in this report as well as the recommendation provided for mitigation/minimization/avoidance of adverse impacts arising from the project activities. |
|  | The Land Act, 2012 | An Act of Parliament to give effect to Article 68 of the Constitution, to revise, consolidate and rationalize land laws; to provide for the sustainable administration and management of land and land- based resources, and for connected purposes Forms of Tenure. 5. (1) There shall be the following forms of land tenure- (a) freehold; (b) leasehold; (c) such forms of partial interest as may be defined under this Act and other law, including but not limited to easements; and (d) customary land rights, where consistent with the Constitution. Methods of acquisition of title to land. 7. Title to land may be acquired through— (a) allocation; (b) land adjudication process; (c) compulsory acquisition; (d) prescription; (e) settlement programs; (f) transmissions; (g) transfers; (h) long term leases exceeding twenty-one years created out of private land; or (i) any other manner prescribed in an Act of Parliament. Conversion of land. 9. (1) Any land may be converted from one category to another in accordance with the provisions of this Act or any other written law. (d) Community land may be converted to either private or public land in accordance with the law relating to community land enacted pursuant to Article 63(5) of the Constitution. | The proposed site will be developed on public land and no resettlement of people will be done. |
|  | Community Land Act, 2016 | This Act is critical for the proposed project is within community land. Section 6(1) of the Act provides that ‘county governments shall hold in trust all unregistered community land on behalf of the communities for which it is held’. Furthermore, Section 6(2) maintains that ‘the respective county government shall hold in trust for a community any monies payable as compensation for compulsory acquisition of any unregistered community land’. Section 30(1) states that ‘Every member of the community has a right to equal benefit from community land’. Section 26(1) provides that ‘a community may set aside part of the registered community land for public purposes and Sub-section (2) holds that ‘where land is set aside for public purposes under Sub-section (1), the (Land) Commission shall gazette such parcel of land as public land’. These provisions offer a window for the proposed project to acquire land for project works legally for communities as necessary and to convert the same into public land. This is useful for the project as once done powerful groups will not have opportunity to exclude them on account of their socio - economic statuses. In any event, Section 35 holds that, ‘subject to any other law, natural resources found in community land shall be used and managed- (a) Sustainably and productively. (b) For the benefit of the whole community including future generations. (c) With transparency and accountability; and (d) On the basis of equitable sharing of accruing benefits. The concept of community land has been defined broadly enough to include VMGs. Women, children, old people, and future generations have been thought of as PAPs and thus their rights secured in this Act | -The initially identified section that was later dropped was on community land and the land belong to the Bajun community in Mkokoni with minority being the Awer community. -The proposed project site falls under public land owned by NPS. The establishment of the mini grid will convert the public land to industrial use for long term. -The proponent should adhere to the provision of this legislation |
|  | Land Registration Act, 2012 | Section 27 (2) provides that a transfer without valuable consideration shall have the same effect as a transfer for valuable consideration when registered. | Once the KOSAP PIU finalizes stakeholder engagements in all the identified counties, the transfer process shall be commenced to ensure that the land rights are secured. This gives the project the required land security to allow project implementation, which is in compliance with this legal requirement. |
|  | Land value amendment Act 2019 | It aims at standardizing the value of land in Kenya for the primary purpose of enhancing efficiency and expediting the compulsory land acquisition process for public projects. It introduces Section 107A into the Land Act, which provides the criteria for the valuation of freehold and community land that is the subject of compulsory acquisition. Community Land, like freehold land, shall be valued based on the criteria outlined in Section 107A and the Land Value Index which will be jointly developed by the national government and county government. Section 5 introduces a list of the forms in which compensation can be made. | The proposed project site falls under public land owned by NPS. The establishment of the mini grid will convert the public land to industrial use for long term and no compensation will be done. |
|  | The Environment and Land Court Act 2011 | This is an Act of Parliament intended to give effect of article 162(2) b of the constitution; to establish a superior Court to hear and determine disputes relating to the environment and the use and occupation of, and title to, land and to make provision for its Jurisdiction functions and powers, and for connected purposes. The principal objective of this Act is to enable the Court to facilitate the just and expeditious, proportionate and accessible resolution of disputes governed by this Act. | The project will have a grievance redress mechanism with a committee. The work of the committee will be to receive and respond to all the grievances raised. As explained in chapter five of this report, an aggrieved party will turn to the legal system after exhausting the GRM levels of resolution set. In the event any disputes on land and environment are not resolved through the project GRM, this court will provide a forum for timely resolution of such grievances. |
|  | The Physical and Land Use Planning Act, 2019 | This Act of Parliament makes provision for the planning, use, regulation, and development of land and for connected purposes. | The proposed site is not in contravention of any Zoning regulations. The project site is within a public land registered under the National Police Service (NPS)-surveyed. The MoEP has made a formal communication to NPS to grant consent for parcel of land; necessary county approvals will be sought by the proponent e.g., Project design approval and change of use. The approvals shall be issued by the Physical planner in the department of Lands, Housing and Urban Development – Lamu County. |
|  | The Employment Act No 11 of 2007 | This Act is important since it provides for employer – employee relationship that is important for the activities that would promote management of the environment within the energy sector. | With the Contractor and the Project Proponent being primary employers during the construction and operational phases of the Project, respectively, they are bound by this law to abide to its stipulations on employee management and relations |
|  | The Work Injury Benefit Act, 2007 | This is an Act of Parliament to provide for compensation to employees for work related injuries and diseases contracted in the course of their employment | The Proponent and Contractor will maintain an insurance policy cover for its employees, record of accident, carryout proper accident investigations; organize for pre-employment and regular medical examinations for staff. |
|  | Air Quality Regulations (2014) | Regulation 3 stipulates that the objective of these Regulations is to provide for the prevention, control, and abatement of air pollution to ensure clean and healthy ambient air. | The Proponent and contractor will implement mitigation during construction to ensure neighbouring properties are not impacted by nuisance dust |
|  | The Traffic Act Chapter 295 Laws of Kenya | This Act consolidates the law relating to traffic on all public roads. Key sections include registration and licensing of vehicles; driving licenses; driving and other offences relating to the use of vehicles on roads; regulation of traffic; accidents; offences by drivers other than motor vehicles and other road users. Many types of equipment and materials shall be transported through the roads to the proposed site. Their registration and licensing will be required to follow the stipulated road regulations. The Act also prohibits encroachment on and damage to roads including land reserved for roads. | The project will observe the provisions of the Act including management of traffic of construction vehicles as guided by the ESMMP |
|  | National Museums and Heritage Act, 2006 | The Act seeks to consolidate the law relating to national museums and heritage; to provide for the establishment, control, management and development of national museums and the identification, protection, conservation and transmission of the cultural and natural heritage of Kenya; to repeal the Antiquities and Monuments Act and the National Museums Act. | During implementation of the project, the Act will be followed in the event of case of chance find of cultural heritage on the proposed site |
|  | The Prevention, Protection and Assistance to Internally Displaced Persons and Affected Communities Act, 2012 | This an Act of Parliament that provides for the prevention, protection and provision of assistance to internally displaced persons and affected communities and give effect to the Great Lakes Protocol on the Protection and Assistance to Internally Displaced Persons, and the United Nations Guiding Principles on Internal Displacement and for connected purposes. | According to this Act, displacement in projects should be avoided to the extent possible and implementation of KOSAP sub-projects will adhere to this requirement. |
|  | County Government Act, 2012 | This Act makes provisions for county governments’ powers, functions and responsibilities to deliver services and for connected purposes. Part VIII of the act on Citizen Participation (87) (b) emphasizes on the right of citizens to participate to any development projects prior to their implementation. This Act gives guideline on planning in the County and especially the partnership in development between the National Government and other investors. | In complying with this requirement, the ESIA team held consultations on the project with the County Government of Lamu namely the Governor, County Executive Committee members for Environment, Energy and Public service and Administration. Additionally, the County government through the CEC Public service administration and the Chiefs office mobilized the communities for the consultation forums |
|  | The Sexual Offenses Act 2006 | This is a comprehensive law that criminalizes a wide range of behaviours including rape, sexual assault, defilement, compelled or induced indecent acts with child imbeciles or adults, gang rape, child pornography, child trafficking, child sex tourism, child prostitution, exploitation of prostitution, incest by male and female persons, sexual harassment, deliberate transmission of HIV or other life threatening sexually transmitted disease, stupefying with sexual intent, forced sexual acts for cultural or religious reasons among others. The Act also has orders for medical treatment for victims including free HIV prophylaxis, emergency pregnancy pill and counselling. The Act provides stiff penalties in which most of the crimes attract minimum of ten years imprisonment which can be enhanced to life imprisonment. | Implementation of a project creates changes in a community in which it is implemented and is has potential to cause shifts in power dynamics between community members and within households. For instance, male jealousy is a key driver of Gender Based Violence (GBV) which can be triggered by labour influx on a project when workers are believed to be interacting with community women. Hence, abusive behaviour can occur not only between project-related staff and those living in and around the project site, but also within the homes of those affected by the project. |
|  | The Children Act, 2012 | Part 2 of the Act denotes the rights of the children and their welfare shall be protected from child labour and armed conflict i.e. Every child shall be protected from economic exploitation and any work that is likely to be hazardous or to interfere with the child’s education, or to be harmful to the child’s health or physical, mental, spiritual, moral or social development. The Act also notes that a shall be protected from sexual exploitation and use in prostitution, inducement or coercion to engage in any sexual activity, and exposure to obscene materials. | Sensitization to the community on the need to ensure the protection of children has been done and will continue throughout the project cycle. In addition, the contractor will sensitize workers against abuse and exploitation of children. |
|  | Persons with Disability Act, Chapter 133 | This Act provides for the protection of the rights of people with disabilities ensuring they are not marginalized and that they enjoy all the necessities of life without discrimination. The Act guarantees that (1) No person shall deny a person with a disability access to opportunities for suitable employment. (2) A qualified employee with a disability shall be subject to the same terms and conditions of employment and the same compensation, privileges, benefits, fringe benefits, incentives or allowances as qualified able-bodied employees. (3) An employee with a disability shall be entitled to exemption from tax on all income accruing from his employment. | The Act will be adhered to in order to ensure that persons with disability are included in all decision making that affects their lives. This will be monitored to make sure they are not excluded from project benefits and exposed to negative impact from the project that could adversely affect them. |

## Licenses and Permits Required

The subsidiary legislation under the EMCA is partially monitored through the use of permits and licenses. Subsequently all licenses and permits required during the construction phase shall be the responsibility of the individual contractors and their agents. During the operational phase, all permits and licenses required to operate the project will be the responsibility of the proponent.

Before the contractor mobilizes to the site, there are certain permits that he will need to put in place. Some permits may be obtained during construction since they will be determined as need arises. Table 10 overleaf lists the environment-related permits required for this project.

Table 10: Project Permit and License Requirements

| No. | Relevant activity | Statute | Permit and License Requirement | Competent Authority | Responsible Agency for Obtaining Clearance | Date of Acquisition | Duration |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Pre-Construction Stage |  |  |  |  |  |  |  |
| 1 | Construction and operation of the solar mini grid | Environmental Management and Coordination Act (EMCA) Cap 387, Rev 2018 | Need to submit ESIA report to obtain EIA license | NEMA | Proponent | Upon approval of ESIA report | Max 90 Days from date of submission of ESIA Report |
| 2 | Construction activities | Occupational Safety and Health Act (OSHA), 2007 | Need to apply registration of premises | DOSHS | Contractor | Before commencement of construction | 1 – 4 weeks |
| 3 | Setting up of construction camp sites | Environmental Management and Coordination Act (EMCA) Cap 387, Rev 2018 | Need to submit Project report for the Camp Sites to obtain EIA License | NEMA | Contractor | Before commencement of construction | 1– 1.5 months |
| 6 | Storage, transport and disposal of ordinary domestic and office waste | Environmental Management and Coordination Act (EMCA) Cap 387, Rev 2018 | Need to obtain waste license through submission of Waste Management Plan | NEMA | Contractor | Before commencement of construction | 1 – 1.5 months |
| 7 | Storage, transport and disposal of hazardous waste | Environmental Management and Coordination Act (EMCA) Cap 387, Rev 2018 | Need to obtain hazardous waste license through submission of Waste Management Plan | NEMA | Contractor | Before commencement of construction | 1 – 1.5 months |
| Construction stage |  |  |  |  |  |  |  |
| 4 | Food handling in the campsite | Public Health Act | Obtain Food Handler Certificate | County Government | Contractor | Before handling of food in the campsite | 6 months |
| 5 | Workplace registration | Occupational Safety and Health Act, 2007 | Apply for Registration of a Workplace | DOSHS | Contractor | Before utilizing the campsite | Annual |

## National Administrative Requirements

A brief description of the relevant enforcement agencies with respect to the institutional framework is described in the table below.

Table 10: Relevant Enforcement agencies

| Main Actors | Key Functions |
| --- | --- |
| #### Ministry of Energy | Under the leadership of a Cabinet Secretary, the ministry is responsible for formulation and articulation of energy policies through which it provides an enabling environment for all stakeholders. Its tasks include national energy planning, training of manpower and mobilization of financial resources. |
| #### Energy and Petroleum Regulatory Authority (EPRA) | The Energy Act establishes the EPRA to, among other functions: regulate production, conversion, distribution, supply, marketing and use of renewable energy; collect and maintain energy data; ensure, in collaboration with the Kenya Bureau of Standards, that only energy-efficient and cost-effective appliances and equipment are imported into the country; and co-ordinate the development and implementation of a national energy efficiency and conservation action plan. The powers of the Authority include, but are not limited to, the power to: issue and renew licenses and permits for all undertakings and activities in the energy sector; manage electric power tariffs and tariff structures; investigate tariff charges; formulate, set, enforce and review environmental, health, safety and quality standards for the energy sector; approve electric power purchase and network service contracts for all persons engaging in electric power undertakings; investigate and determine complaints or disputes between parties over any matter relating to licenses and license conditions under the Energy Act; and impose such sanctions and fines as may be appropriate for violation. |
| #### Energy and Petroleum Tribunal | The Energy Act establishes the Tribunal to hear and determine civil disputes and appeals from the EPRA and any other licensing authority relating to the energy and petroleum sector. The Tribunal has powers to grant equitable reliefs including, but not limited to injunctions, penalties, damages, specific performance, and the power to, on its own motion or upon application by an aggrieved party, review its judgments and orders. |
| #### Rural Electrification and Renewable Energy Corporation (REREC) | The main purposes of the RERC are to spearhead development of renewable energy resources in Kenya and to accelerate the pace of rural electrification in the country. The REREC is mandated under The Petroleum Act to undertake feasibility studies and maintain data with a view to availing the same to developers of renewable energy resources and provide an enabling framework for the efficient and sustainable production, conversion, distribution, marketing, and utilization of renewable sources in Kenya. |
| #### Renewable Energy Resource Advisory Committee | The Committee is intended to play an advisory role to the Cabinet Secretary for the Ministry of Energy and Petroleum on the criteria for allocation of renewable energy resource, licensing of renewable energy resource areas, management of water towers and catchment areas, development of multi-purpose projects such as dams and reservoirs for power generation and management and development of renewable energy resources. |

## International Safeguard Requirements

The table below shows the applicability of World Bank Operational Safeguards as it applies to the proposed project in Mkokoni site.

World Bank Operational Safeguards

Table 11 Summary of World Bank Environmental and Social Safeguards Policies

| S.No. | Description of World Bank Safeguards | Applicability | Objectives and Applicability to Project |
| --- | --- | --- | --- |
|  | OP 4.01 (Environmental and Social Impact Assessment) | Applicable | Guided by this OP, the following has been considered: Safeguard instruments and World Bank operation policies; Subproject area baseline information; Potential risks and impacts related to acquisition of land; Impacts related to Covid 19, GBV (SEA/SH and HIV/STD); Process and community level structures related risks; Policy, legal and institutional frameworks and ESM and monitoring plans The proposed project is likely to have potential environmental and social impacts. The objective of OP 4.01 is to ensure that Bank-financed projects are environmentally sound and sustainable, and that decision-making is improved through appropriate environmental and social screening, analysis of actions and mitigation of their likely environmental and social impacts and monitoring. The consultants have identified that the overwhelming majority of project PAPs in area are considered vulnerable and marginalized. Therefore, OP 4.01 is applicable, and in line with this operational policy, the environmental and social screening process for the mini-grid project. |
|  | OP 4.10 (Indigenous People) | Applicable | The objective of this policy is to (i) ensure that the development process fosters full respect for the dignity, human rights, and cultural uniqueness of IPs; (ii) avoid adverse effects from the project, or minimize, mitigated or compensated; and (iii) ensure that IPs receive culturally appropriate and gender and intergenerational inclusive social and economic benefits. The 14 counties targeted by this project are considered as marginalized areas in Kenya. Therefore, the Borrower has prepared an SA report to identify and avert any potentially adverse effects from project interventions on VMGs and to ensure that project benefits that are culturally appropriate reach these groups in an equitable manner. |
|  | OP 4.12 (Land Acquisition and Involuntary Settlement) | Applicable | The objective of this policy is to (i) avoid or minimize involuntary resettlement where feasible, exploring all viable alternative project designs; (ii) assist displaced persons in improving their former living standards, income earning capacity, and production levels, or at least in restoring them; (iii) encourage community participation in planning and implementing resettlement; and (iv) provide assistance to affected people regardless of the legality of land tenure. The proposed project will involve land take for construction purposes including, solar panels; generator rooms and distribution lines, as well as contractor yard and workers camp site. The consultant has described land tenure and implications for the project. |
|  | Natural Habitats OP/BP 4.04 | Applicable | This policy recognizes that the conservation of natural habitats is essential to safeguard their unique biodiversity and to maintain environmental services and products for human society and for long-term sustainable development. The Bank therefore supports the protection, management, and restoration of natural habitats in its project financing, as well as policy dialogue and economic and sector work. Predicated on the assumption that natural habitats may be affected by erection of poles and construction of mini-grid stations. The proposed project may be in or close to areas with natural unique flora and fauna though the component is unlikely to have significant negative impacts on natural habitat. Works will nevertheless be implemented in an area in Mkokoni that may not negatively affect diverse flora, fauna, and avifauna. The area has scattered vegetation. |

### Kenya Off-grid Solar Access Project (KOSAP) Environmental & Social Management Framework, 2017

The World Bank is concerned about the environmental and social impacts of its activities and requires environmental assessments be done for all projects it finances. Its safeguard policies are aimed at preventing and mitigating undue harm to people and their environment in the development process also provide a platform for the participation of stakeholders in project design and implementation.

The framework was prepared because the geographic coverage for KOSAP was generally known but the exact locations for the sub projects had not been identified. The ESMF provides guidelines for MoEP, KPC & REREC in determining the appropriate level of environmental and social assessment required for the sub-projects and in preparing the necessary environmental and social mitigation measures for these sub-projects.

The proposed project will consider all relevant guidelines as provided by the KOSAP- ESMF

### Resettlement Policy Framework (RPF)

The RPF states that K-OSAP component 1 (Mini grids for Community Facilities, Enterprises, and Households) which involves installation of mini grids will require land acquisition.

The Framework seeks to avoid, manage, and/or mitigate potential risks arising out of damage to assets, disruption to work, temporary negative impacts on livelihoods and/or in the unlikely case of displacement. To develop a Resettlement Action Plan and propose an implementation framework for RAP to mitigate such effects. Involuntary resettlement and land acquisition will be avoided where feasible, or minimized or compensated where it cannot be eliminated. Where involuntary resettlement and land acquisition are unavoidable, resettlement and compensation activities will be conceived and executed as sustainable development programs, providing resources to give PAPs the opportunity to share project benefits. PAPs will be meaningfully consulted and will participate in planning and implementing of the resettlement activities

There will be no displacement of people/crops/etc. as the land identified for Minigrid construction in open public land registered under the National Police Service (NPS)-surveyed. The MoEP has made a formal communication to NPS to grant consent for parcel of land.

### Vulnerable and marginalized Groups Framework (VMGF) for KOSAP

As noted above the O.P 4.10 policy on Indigenous People is applicable to this KOSAP project and therefore a Vulnerable and Marginalized Groups Framework (VMGF) was prepared for use by the Ministry of Energy and Petroleum (MOEP) and the implementing agencies KPC and REREC and other stakeholders. The framework was prepared then because was known that IPs are present in all the 14 target project counties. However, at that stage of project preparation, the exact sub-project sites were not yet identified and the exact impacts of the project on VMGs were not yet completely known. The VMGF describes the policy requirements and planning procedures that during the preparation and implementation of components especially those identified as occurring in areas where VMGs are present.

The purpose of the VMGF is to guide management of issues related to vulnerable and marginalised groups during the development and operation of proposed sub projects and to ensure effective mitigation of potentially adverse impacts while enhancing sharing of benefits.

The project area is inhabited by predominantly by the Bajun Community. Their presence in the project’s footprint was clear with the only other  communities present in the area that will benefit from the project being the Awer.

The Bajun and the Awer falls under communities in Kenya who are categorized by the World Bank’s OP 4.10 and the Constitution of Kenya, 2010, as vulnerable and marginalized groups. Thus the VMGs that have been identified as those who would potentially be impacted by the project are the Bajun and Awer communities who have extensive presence in the project area.

# STAKEHOLDER ENGAGEMENT

This section profiles the key stakeholders of the Mkokoni mini-grid site and assesses their potential concerns and levels of influence. The process of stakeholder engagement involved;

- stakeholder identification and analysis

- planning for the stakeholder engagement;

- disclosure of information;

- consultation with stakeholders

- addressing and responding to grievances; and

- reporting to stakeholders

## Stakeholder Consultation and Disclosure Requirement for the Project

The World Bank OP 4.01 Environmental Assessment- Stakeholder Engagement and Information Disclosure emphasises on engagement in meaningful consultations with all stakeholders. The stakeholders should be provided with timely, relevant, understandable, and accessible information, and consult with them in a culturally appropriate manner, which is free of manipulation, interference, coercion, discrimination, and intimidation. The ESIA report will be made available in public places that are accessible to project-affected groups and local NGOs (NEMA website and Respective NEMA County offices).

A documented record of stakeholder engagement, including a description of the stakeholders consulted, a summary of the feedback received, and a brief explanation of how the feedback was collected, has been presented below. The consultations were conducted in form of:

- Meeting with the client

- Consultation with the county commissioner and the county officials

- Key stakeholder interviews with the county officials

- Public meeting in Mkokoni

- Focus Group Discussions

## Stakeholder Characterisation and Identification

A stakeholder is “a person, group, or organization that has a direct or indirect stake in a project/organization because it can affect or be affected by the Project/organization's actions, objectives, and policies” Stakeholders thus vary in terms of degree of interest, influence and control they have over the project.

### Stakeholder Mapping

Stakeholder mapping” is a process of examining the relative influence that different individuals and groups have over a project as well as the influence of the project over them. The purpose of a stakeholder mapping is to:

- Identify each stakeholder group;

- Study their profile and the nature of the stakes;

- Understand each group’s specific issues, concerns as well as expectations from the project

- Gauge their influence on the Project;

In line with the nature of the project and its setting in Mkokoni, the stakeholders have been identified and listed in the table given below;

Table 5-1: Identified Stakeholders

| Stakeholder Category | Stakeholder Group | Connection to the KOSAP | Consultation tool |
| --- | --- | --- | --- |
| Project Affected Persons | Local Community | - Local communities to be affected either directly or indirectly by the project - Vulnerable Individuals and Households - Health institutions - Education institutions | Public Meeting - 1 public meeting was held in Mkokoni - The meeting was held with attendance of 104 people. Focus Group Discussions (FGD) - The FGDs were conducted with the men, women, youth. Key Informant Interviews (KII) - The KIIs were conducted through one-on-one interviews. The chief was also interviewed on the Community Profile of Mkokoni. |
| Interested Parties | - Government agencies - National regulatory bodies | National Government are of primary importance in terms of establishing policy | Meeting A meeting was held with the Lamu County Commissioner |
|  | County government | - County government are also of primary importance in county energy requirements and proposed interventions - They will play an important role in implementation and sustainability of the project |  |

The significance of a stakeholder group is categorized considering the magnitude of impact (type, extent, duration, scale and frequency) or degree of influence (power and proximity) of a stakeholder group and urgency/likelihood of the impact/influence associated with the particular stakeholder group in the project context. The magnitude of stakeholder impact/influence is assessed taking the power/responsibility and proximity of the stakeholder group and the group is consequently categorized as negligible, small, medium or large. The urgency or likelihood of the impact on/influence by the stakeholder is assessed in a scale of low, medium and high. The overall significance of the stakeholder group is assessed as per the matrix provided in Table 5-2 below.

Table 5-2: Stakeholder Significance and Engagement Requirement

|  |  | Likelihood of Influence on/ by Stakeholder |  |  |
| --- | --- | --- | --- | --- |
|  |  | Low | Medium | High |
| Magnitude of impact | Negligible | Negligible | Negligible | Negligible |
|  | Small | Negligible | Minor | Moderate |
|  | Medium | Minor | Moderate | Major |
|  | Large | Moderate | Major | Major |

## Stakeholder Analysis

The Stakeholder influence and priority have both been primarily rated as:

- High Influence: This implies a high degree of influence of the stakeholder on the project in terms of participation and decision making or high priority to engage with the stakeholder;

- Medium Influence: Which implies a moderate level of influence and participation of the stakeholder in the project as well as a priority level to engage the stakeholder which is neither highly critical nor are insignificant in terms of influence; and

- Low Influence: This implies a low degree of influence of the stakeholder on the project in terms of participation and decision making or low priority to engage that stakeholder.

The intermediary categories of low to medium or medium to high primarily imply that their influence and importance could vary in that particular range subject to context specific conditions or also based on the responses of the project towards the community.

The coverage of stakeholders as stated above includes any person, group, institution or organization that is likely to be impacted (directly or indirectly) or may have interest/influence over project. Keeping this wide scope of inclusion in stakeholder category and the long life of project, it is difficult to identify all potential stakeholders and gauge their level of influence over project at the outset of the project. Therefore, the project proponent is advised to consider this stakeholder mapping as a live document which should be revised in a timely manner so as to make it comprehensive for any given period of time.

| Stakeholder Category | Relevant Stakeholders | Magnitude of Influence | Urgency/Likelihood of Influence | Overall rating of stakeholder rating |
| --- | --- | --- | --- | --- |
| Interested Parties | National Government agencies | Large | High | Major |
|  | National regulatory bodies | Large | Medium | Major |
|  | County Government | Large | Medium | Major |
| Project affected Persons | Local communities to be affected either directly or indirectly by Projects | Large | High | Major |
|  | Vulnerable Individuals and Households | Medium | High | Major |
|  | Education and Health institutions | Medium | Low | Minor |

## Information Shared to The Community Members

The MoE representative assisted by the KP representative gave a description of the KOSAP projects and clarified that its objective was to electrify Mkokoni because the area is not connected to the national grid. They also informed the community that they would access the electricity at a subsidized cost and that the public facilities such as the schools, dispensaries and public boreholes would be also be connected. The environmental and social experts also shared with the community the ESIA process and discussed the potential impacts associated with the project and the proposed mitigation measures that would reduce their significance.

## Summary of Community Consultation Meeting Leading to Land Identification and GRC Constitution-(screening level)

Project: Proposed Mkokoni village Solar Mini-grid

Venue of meeting; Mkokoni Village

Date: 23/09/2020

The meeting was called to order at 11:12am

Mr Jamal Fumo the ward administrator, recognized the following present in the meeting: MoE officials, KPLC, REREC and Lamu county government.

Eng. Zadock  from KPLC, explained to the meeting that the government of Kenya through vision 2030 is planning that every household should be connected with power hence the government has come up with this project called Kenya off Grid Solar Access Project (KOSAP) that is meant to connect Kenyans in the rural areas which are far from the national grid. This project is being implemented in the 14 counties where Lamu is one of them The main purpose of the Baraza was to consult and engage the community in land acquisition process for the mini grid and the establishment of a grievance resolution committee.

### Land for the Project

The community members were informed by Mr. Joseph Korir (Surveyor), that the land required for the construction of the Mini grid is 0.411 hectares Further confirmation of the same will be carried out during the acquisition process. He explained to the gathering that he would map out the land donated. He further said that he was the surveyor of the team and would take the coordinates of the land to commence the land acquisition process. He further explained that he would then prepare a sketch map of the land and forward the same to the County Government for approval. Once the county approved the scheme it would be forwarded to the National Land Commission for approval and the process of preparation of a letter of allotment. The meeting was told that the title would finally be in the name of Kenya Power and Lightening Company (KPLC)

Plenary Session

Table 6-2: Issues /Comments Raised during the plenary session

| QUESTION/COMMENTS | ANSWER/REMARKS |
| --- | --- |
| Ali Azwaj Appreciate the implementation and welcomed the project in the area. | Abaya The project implementation will be done as per the requirement of the Government, the community to agree on the project implementation since the project has limited time. |
| Lali Abubakari “How long will we wait for the implementation” Incase of delay in the implementation, if the community gets another project the land will be given out. | Zadock The implementation will be done after tendering, what remains is land acquisition. Manager – Kplc lamu Land donation and community partnership needed for the implementation of the project. The land will be transferred to KPLC Ward admin – Fumo Land donations remains on the community |
| Mohmoud What benefit will we gain by donating the land in kind? How much is the connection fee? | Irene Connection fee is 1k compared to other communities paying 15k. There is no compensation for land donation. |
| Fesuol monte There is no compensation yet the money is from world bank, how will the youths benefit? In case kplc moved the site to another area, can the land be used for another project? | Manager – Kplc lamu The community will be employed in the project works through the skilled and unskilled jobs, the power plant will not be moved to another area that’s why KPLC will do the transfer of land to enable them secure the site. |

### Project Grievance Redress Mechanism

Mr. Samuel Abaya explained to the community that it is important to put in place a project grievance redress mechanism (GRM). He noted that the GRM to be set should borrow heavily from the existing conflict resolution structures in the community. He explained that the need for a GRM is to provide the community and other stakeholder’s opportunity to share project information and raise questions and grievances about the project. He told the community that they are free to raise any complain or request information about the project..

The community nominated the following as members of the GRC:

| No | Name | DESGN. | ID No. |
| --- | --- | --- | --- |
| 1 | Atik Mohamed Atik | Chief | 8520863 |
| 2 | Ali Hassan Ali | Youth | 37927463 |
| 3 | Khadija Mohamed Aboud | Pwd | 34412469 |
| 4 | Ahmed Mohamed | Elder | 2238916 |
| 6 | Salma Mohamed | Women | 20346195 |
| 7 | Baraki Mbwana Athman | Religious leader | 2238845 |

FOCUSSED GROUP DISCUSSIONS

The social system amongst the communities is dominantly patriarchal, in which power, leadership, moral authority and control of property are vested in males. Clan-based culture and religion drives this strict male hierarchy and authority. Women, girls and youth roles in society are thus limited as is their decision-making powers. At the apex of the community is the clan and beneath it the elders, below them lies the Male family heads, then their wives and male children. Female children lie at the bottom of society. Due to this cultural set-up of power in the community, when elders, women and youth  are placed together in same meeting some group members may shy away from expressing their views. It is for this reason that, during the course of the Baraza the environmental/social specialist called for separate meetings between the different stakeholders (Women, Youth and elders) in an attempt to allow them to freely express their hopes, fears, aspirations and expectations in relation to the mini grid and the project as a whole. Whereas all the groups expressed their unreserved support for land donation to the project, the following were noted as the main concerns/issues:

Focus Group Discussion with the men

A focus group discussion was held with the men. The main objective of this discussion was to assess whether the men had understood the project and its requirements and to provide them an opportunity to air their issues/give their opinions on the project.  Samuel gave a summary of the project and its requirements again just to keep them abreast of the issues discussed in the public forum. He then asked the men whether they agree to the donation of community land to the project. The men said they support the donation of land for the project. We then allowed for a plenary session to hear their views and question from the men.

| Questions/ comments | Response/ Remarks |
| --- | --- |
| Abu Bakar: How long will the community wait for this project? | Abaya: Currently the project is under preparation stage once the project proponent acquires a piece of land and get the required approvals then the construction will commence. It will roughly take a year tentantively. |
| Bakari Mbwana: What size of land will be required for the proposed mini grid project? | Joseph Korir: If the community can donate between 0.411 hectares will be appropriate for the proposed project. |
| Ahmed Mohamed Athman: How far will be the land where the proposed minigrid shall be installed | Eng. Zadock: We recommend the proposed minigrid is constructed next to the settlement for the purpose of ensuring all residents of Mkokoni are connected with power in their households. |
| Mzee Ali: Expressed his gratitude to the government for initiating such project in their community. He further asked who the financials of the proposed project? | Abaya: The KOSAP project is being funded by the World Bank and the government of Kenya |

Women

A focus group discussion was held with women. The main objective of this discussion was to assess whether the women had understood the project and its requirements and to provide an opportunity for them to air their issues/give their opinions on the project.

Dorothy (MOE) explained to the women that it was important to hold a separate discussion with them so that they have an opportunity to freely express themselves. She explained the agenda of the visit by the officers from the National and County government was to undertake an environmental and social screening of the proposed site to check for its suitability in terms of environmental, technical, social and health requirements.  The second objective was to undertake community engagement to sensitize the community on the project. The third objective was to explain the land requirements for the project and the need for a project grievance redress mechanism. Dorothy then gave a summary of the project in terms of its positive and negative impacts and their mitigation measures and the requirements for donating land. She also explained the need for the women to select a representative to the project committee who would represent their views/issues to the committee for redress.

Question, Suggestions, feedback and response for Focus Group Discussion with women

| Name of Person making the contribution | Question, Comment, Suggestion | Feedback/Responses by project team |
| --- | --- | --- |
| Ruweiyda Mohamed Mkokoni | -We welcome the project; it will open a lot of business opportunities for us and help those of us with businesses to grow -When should we expect lights to be on in Mkokoni? | -Noted -The implementation is at an advance stage and the contractors should be on site by July 2021 |

Youth

The youth were particularly excited about oncoming mini grid as they anticipated employment opportunities that would accrue during project implementation phase as well as opportunities to establish income generating business ventures upon completion (economic empowerment). They also wanted to know whether the project had a component for training of local youth on electrical installation.

Youth group discussion

## Summary of Community Consultation During the ESIA

A Consultative Public Participation (CPPs) session is conducted to provide project information and facts to the local community and other stakeholders especially local government administrator thus giving them a platform to enable them to express their appreciation, concerns and fears as well as contribute ideas and opinions towards the project sustainability.

A detailed CPP and community engagement for Mkokoni Solar Mini Grid was held in Mkokoni village, at Mkokoni Baraza park on 30th September 2021 chaired by the area chief.

The general stakeholder consultation was done in a public meeting (Baraza) organized at Mkokoni community baraza point where 40 males and 64 women were in attendance. The meeting was chaired by the area ward administrator assisted by the chief and the “Nyumba Kumi” leaders. The feedback received during the stakeholder consultation process have been summarized below.

| No | Issues/Concerns | comments discussed |
| --- | --- | --- |
| 1. | Issues on the reliability of the electrical power during operation stage. | The consultant responded and informed members consulted that an automatic backup generator will be available to provide backup electrical power when solar energy is unavailable. |
| 2. | concerned by the project timelines and registered his concerns over the project implementation process and steps. | The consultant informed the Mr. Ahmed and members consulted that ESIA process is an important component of project implementation and construction will be initiated once the process is complete and approval granted. |
| 3. | Concerns on how employment opportunities will be distributed once the project is complete | In response, the consultant informed him that the available opportunities will always be advertised and information provided on basic requirements and qualifications. The consultant noted that those who will be eligible will be considered, local capacity is encouraged. The Consultant further added that during project implementation, the contractor will be encouraged to source locally available materials from within so as to create more opportunities for the community. |
| 4. | Concerns on the employment opportunities available for the project | The consultant informed Mr. Ahmed that the project will follow guidelines and set out laws in seeking qualified staff and workers to work on the project. The consultant further informed them that the contractor will be advise to utilise locally available human resources where available. The consultant further informed the members consulted that a redress mechanism will be available for the community members to air their respective grievances that include provision of relevant opportunities for the locals. |

The Focus Group Discussions were held with Men, Women and the Youth as indicated in Table 18;

### Focused Group Discussions analysis

The in-depth interviews were used as a tool for stakeholder identification and mobilization as well as collection of baseline data to enable identification of the likely project impacts. In addition, it provided an opportunity to the participants to raise their fears and concerns as well as make recommendation as pertains to the project.

During the discussions, information was gathered different roles, livelihood, health issues, challenges, perception of quality of life, education options for children, health care and project perception.

Table 18: FGD dates and attendance

| Group | Date | Attendance | Venue |
| --- | --- | --- | --- |
| Men | 30th September 2021 | 12 | -Mkokoni Meeting Area |
| Women | 30th September 2021 | 9 | -Mkokoni Meeting Area |
| Youth | 30th September 2021 | 8 | -Mkokoni Meeting Area |

The consultative meeting had a wide representation as follows:

Table 19. The consultative meeting had a wide representation

| Category | Male | Female | Total |
| --- | --- | --- | --- |
| TOTAL (M&F) | 39 | 16 | 55 |

The target groups of the FGD were Males, Females, Health sector, Education sector as well as and the Youths.

The key concerns and expectations that were raised during FGDs have been summarized below:

Summary of feedback from the Men FGD in:

- The men informed that the area has security challenges and that they provide security for the community as one of their main roles.

- They explained that they take part and resolve internal and external issues within the community through conflict resolution mechanisms established by community elders and leadership. They expounded on the need of the contractor and project implementing parties to utilise the available community structures for resolving issues.

- The men also informed that their main income generating activities include fishing, farming and small businesses/trade.

- They informed that mangrove forest resources and unique aquatic ecosystems that includes fish are one of the main natural resources at the area. They explained on the need of the contractor and proponent to ensure that they guard this resource.

- They expounded on the challenges experienced in education sector due to then unavailability of electricity to which CBC system is greatly anchored on. They informed that they anticipate this project to provide a sustainable solution.

- Men own all the land. They have control and access to all the land resources in the community.

- They informed that the main form of transportation within the community are dhows, motorboats, vehicles and airstrip. They further explained that travelling by boat is very expensive and the local community members cannot afford.

- The men confirmed that at the project site there are no artifacts of cultural importance. The Bajun and Awer communities in the area are predominantly Muslims.

- The men also enquired on the stability of electrical energy to be produced by the minigrid. The were mainly concerned about safety of their electrical devices.

Summary of feedback from the Women in:

- The women reported they had heard about the project before and feel they knew what it was about.

- They informed that the current source of energy is sought from selected private sources that includes D-light which is very expensive. They were delighted about the project noted that it will be affordable and cheaper

- The women insisted on the community and general public being trained and informed on electrical safety

- The women want to be involved in the project, particularly in terms of job opportunities. They said women are not usually engaged whenever there are major projects in the area.

- Women in the community engaged in crop farming (rain fed agriculture), fishing and small scale businesses.

- Women in the community believe they do not have equal opportunities as men in terms of decision making, education and employment.

- In comparison to men, women control far fewer resources. They noted that their male counterparts own land but do not have title deeds.

- Women feel safe in the community and do not have challenges in terms of security apart from rampant drug abuse.

- They reported that most of the household responsibilities are left for women whereas they do not have any income generating activity

- Women receive news about local issues and community development through regular talks with fellow women and the administration representative (chief).

- They informed that women participate in community decision making processes through public meetings and contributing to household needs.

- Women rely on one another for clothing, food, and money. Women in have active and function women groups “Chamas”.

- According to the women, the community priority needs in the order of priority are:

- Provision of beds in the dispensary ward

- Equipping of the maternity wing at the dispensary

- Fencing of Mkokoni Primary school boundaries

- Women do not have access to credit facilities and moreover they use Mpesa services and use it to meet family needs.

- They informed that their main farming activities is crop farming.

- The women source firewood from as far as 4km from their homesteads.

- They informed that young girls generally know how to read and write whereas, a majority of the women from the age of 40years and above are illiterate and does not know how to read and write.

- Flu related diseases are the most serious health issue that girls and women face in the , followed by ulcers, pressure and diabetes.

- They have access to family planning services for contraception as well as pre- and post-natal care.

- The women informed that majority of the households have pit latrines.

- They get their drinking water from local traders who source desalinated water from Kiunga and rain harvesting and sell to the locals.

- They cook with firewood and use other solar appliances as lighting sources.

Summary of feedback from the youth in:

- The youth had heard of the project and they understood it.

- The projects will create job opportunities.

- Power distribution will make it easier for businesses that rely on electricity to operate, such as storage of fish before selling.

- There are two youth groups in the project area; Kiunga Turtle Conservation Group (KTCG), which was conceptualized in 2005 and deals with conservation of turtles within the area and Tuwajibike Youth Group, started in 2019.

- Extracurricular activities is one of the main priorities for the youth and would wish to have uniforms and balls for football

- They indicated that they have successfully undertaken mangrove planting sensitisation and fishing business initially.

- youth play a minor role in decision making, they are almost never heard.

- Fifty percent of the youth have completed secondary school, while twenty percent have completed vocational school.

- The young people have electricidal, welding and plumbing skills hence they should be given priority in employment.

- Less than one percent of young people have full-time salaried jobs. Fifty percent are self-employed.

- The majority of the youth are fishermen, motorboats owners/driving and offloading of goods at the docking points.

- The youths play football and undertake cleaning activities for leisure

| Public participation “Baraza” Session |  |
| --- | --- |
| Focused Group Discussion with the Men |  |
| Focused Group Discussion with Women |  |
| Focused Group discussion with the Youths |  |

### Positive Comments about the Project from the Participants

Some of the positive impacts that were identified by the participants include the following.

- Learning will improve due to availability of lighting

- Business opportunities will improve since farmers will be able to cool their milk, welding business will arise

- Employment opportunities will increase for the youth due to increase in business opportunities

- Security will improve due to availability of lighting

- Medical services will improve due to availability of refrigeration services

- The electricity will assist in pumping of water from the boreholes

### The identified negative impacts of the project

Some of the positive impacts that were identified by the participants include the following.

- Accidents: some of the members raised concerns of possible accidents from falling poles, electrocution especially the children as well as possible accidents from falling of the electric poles. The community suggested extra care when, protection of appliances and reinforcement of electric poles to mitigate these accidents.

- Employment Disputes: There was a concern over the possibility of disputes arising between the local community with people of different cultures in the construction sites. The community suggested that proponent should consider employing local construction workers.

- Dust Generation: The participants expressed concern over possibility of generation of large amounts of dust within the project site and surrounding areas because of demolition, excavation works and transportation of building materials.

The proponent will ensure that dust levels at the site are minimized through sprinkling water in areas being excavated and along the tracks used by the transport trucks within the site. Additional mitigation measures presented in this report will be fully implemented to minimize the impacts of dust generation.

- Environmental Aesthetics It was seen that the aesthetics of the area would be affected negatively during construction. It was suggested that the proponent should ensure landscaping is conducted after construction.

- Noise Pollution: The neighbouring school and neighbors will be affected by possible noise and exhaust fumes from the site.

Other concerns

- Some of the members asked whether they be required to pay the cost of connection or only the daily usage

- Questions were also raised on whether the labor and raw materials will be sourced from the community.

- A youth felt that the proposed site was an individual’s plot and suggested that an alternative site be considered

### Additional Responses from the Consultant

The consultant while addressing the community’s issues raised, gave the following response.

- Every resident, business or public facility will be connected to the electricity at an affordable cost

- That the Contractor/KOSAP will rehabilitate and plant trees after the construction phase of the project

- All non-skilled labor will be sourced from the Mkokoni Community and not from outside

- He assured the community that the project will commence soon after ESIA

- That noise form the Machinery will be minimized.

### Consent

The Community members present agreed unanimously accepted the Project Proposal.

### Community Presentation

#### Adult to youth Representation

During the stakeholder’s consultation adults were more represented than the youth as shown in the table below.

#### Gender Representation

Table 16. The consultative meeting had a wide representation

| Category | Male | Female |
| --- | --- | --- |
| TOTAL (M&F) | 39 | 16 |

#### Heads of Households

It was noted during the stakeholder consultation that male are the household heads during the stake

# IMPACT ASSESSMENT AND MITIGATION MEASURES

## Identification of Impacts

This Section identifies and discusses both negative and positive impacts associated with the proposed construction of solar Mini-grid. The impacts are identified across all the phases namely: Pre-construction Phase, Construction Phase, Operational Phase and Decommissioning Phase.

Identification of project’s positive and negative environmental impacts was done through observations, literature review, consultations and use of experts’ analysis. The positive impacts are presented first then the negative impacts and their mitigation measures.

## Impact Assessment Methodology

An impact is essentially any change to a resource or receptor brought about by the presence of the Project component or by the execution of a Project related activity. In general, the assessment of impacts will proceed through an iterative process considering four key elements:

- Prediction of potential impacts and their magnitude (i.e., the consequences of the development on the natural and social environment);

- Evaluation of the importance (or significance) of potential impacts taking the sensitivity of the environmental resources or human receptors into account;

- Development of mitigation measures to avoid, reduce or manage the potential impacts or enhancement measures to increase positive impacts; and

- Assessment of residual significant impacts after the application of mitigation and enhancement measures.

Where significant residual impacts remain, further options for mitigation may be considered and impacts re-assessed until they are as low as reasonably practicable for the Project and would be deemed to be within acceptable levels:

## Defining Impact

Impacts will be defined in a number of ways, including:

- Nature of impact: positive or negative;

- Type of impact: direct, indirect, or cumulative;

- Duration of impact: temporary, short-term, national, international

- Scale of impact: onsite, local, regional, national, international.

## Assessment of Significance

Criteria for assessing the significance of impacts will stem from the following key elements:

- Status of compliance with relevant Kenyan legislation, policies and plans and any relevant Kenyan or industry policies, standards or guidelines, as well as international best practice standards and guidelines;

- The magnitude (including nature, scale and duration) of the change to the natural or socioeconomic environment (e.g. an increase in coastal erosion, or an increase in employment opportunities), expressed, wherever practicable, in quantitative terms. The magnitude of all impacts is viewed from the perspective of those affected by considering the likely perceived importance as understood through stakeholder engagement;

- The nature and sensitivity of the impact receptor (physical, biological, or human). Where the receptor is physical, the assessment considers the quality, sensitivity to change and importance of the receptor. For a human receptor, the sensitivity of the household, community or wider societal group is considered along with their ability to adapt to and manage the effects of the impact; and

- The likelihood (probability) that the identified impact will occur. This is estimated based upon experience or evidence that such an outcome has previously occurred.

It is generally accepted that significance is a function of the magnitude of the impact and the likelihood of the impact occurring.

For this assessment, significance has been defined in Table 8-1 based on five levels described in table below;

Table 7-1: Categories of Significance

| Category | Significance |
| --- | --- |
| Positive impacts | Positive impacts provide resources or receptors, most often people, with positive benefits. It is noted that concepts of equity need to be considered in assessing the overall positive nature of some impacts such as economic benefits, or opportunities for employment |
| Negligible impacts (or Insignificant impacts) | Negligible impacts (or Insignificant impacts) are where a resource or receptor (including people) will not be affected in any way by a particular activity or the predicted effect is deemed to be ‘negligible’ or ‘imperceptible’ or is indistinguishable from natural background variations. |
| Minor | An impact of minor significance (‘Minor impact’) is one where an effect will be experienced, but the impact magnitude is sufficiently small (with or without mitigation) and well within accepted standards, and/or the receptor is of low sensitivity/value. |
| Moderate | An impact of moderate significance (‘Moderate impact’) is one within accepted limits and standards. Moderate impacts may cover a broad range, from a threshold below which the impact is minor, up to a level that might be just short of breaching a legal limit. Clearly to design an activity so that its effects only just avoid breaking a law and/or cause a major impact is not best practice. The emphasis for moderate impacts is therefore on demonstrating that the impact has been reduced to a level that is ALARP (as-low-as-reasonably-possible). This does not necessarily mean that ‘Moderate’ impacts have to be reduced to ‘Minor’ impacts, but that moderate impacts are being managed effectively and efficiently. |
| Major | An impact of major significance (‘Major impact’) is one where an accepted limit or standard may be exceeded, or large magnitude impacts occur to highly valued/sensitive resource/receptors. An aim of EIA is to get to a position where the Project does not have any major residual impacts, certainly not ones that would endure into the long-term or extend over a large area. However, for some aspects there may be major residual impacts after all practicable mitigation options have been exhausted (i.e., ALARP has been applied). It is then the function of regulators and stakeholders to weigh such negative factors against the positive ones in coming to a decision on the Project. |

For environmental impacts the significance criteria used in this ESIA is shown in Table 8-2:

Table 7-2: Overall Significance Criteria for Environmental Impacts

| Receptor sensitivity | Impact Magnitude |  |  |
| --- | --- | --- | --- |
|  | Low | Medium | High |
| Low | Minor | Minor | Moderate |
| Medium | Minor | Moderate | Major |
| High | Moderate | Major | Major |

For the social impact assessment, the perceptions of stakeholders, expressed as opinions around certain issues, can be as important as actual impacts. Consequently, the concept of perception is explicitly brought into the evaluation of significance after an impact is evaluated. When an impact is of significant stakeholder concern, this may be causing to raise the significance rating. This prompts the formulation of more rigorous and appropriate mitigation measures which focus on the source of the impact and also address stakeholder perceptions. The risk of not addressing stakeholder perceptions is that reputational damage could arise, resulting in the loss of a ‘social license to operate.

## Magnitude of Impact

The impact assessment describes what will happen by predicting the magnitude of impacts and quantifying these to the extent practical. The term ‘magnitude’ covers all the dimensions of the predicted impact to the natural and social environment including:

- the nature of the change (what resource or receptor is affected and how);

- the spatial extent of the area impacted, or proportion of the population or community affected;

- its temporal extent (i.e., duration, frequency, reversibility); and

- where relevant (accidental or unplanned events), the probability of the impact occurring.

For social impacts, the magnitude considers the perspective of those affected by taking into account the likely perceived importance of the impact, the ability of people to manage and adapt to change and the extent to which a human receptor gains or loses access to, or control over, socio-economic resources resulting in a positive or negative effect on their well-being (a concept combining an individual's health, prosperity, their quality of life, and their satisfaction).

## Sensitivity of Resources and Receptors

Sensitivities are defined as aspects of the natural or social environment which support and sustain people and the physical environment. Once affected, their disruption could lead to a disturbance of the stability or the integrity of that environment. For ecological impacts, sensitivity can be assigned as low, medium or high based on the conservation importance of habitats and species. For habitats, these are based on naturalness, extent, rarity, fragility, diversity and importance as a community resource.

For socio-economic impacts, the degree of sensitivity of a receptor is defined as ‘a stakeholder’s (or groups of stakeholders’) resilience or capacity to cope with sudden changes or economic shocks. The sensitivity of a resource is based on its quality and value/importance, for example, by its local, regional, national or international designation, its importance to the local or wider community, or its economic value.

## Likelihood

Terms used to define likelihood of occurrence of an impact are explained in Table 8-3 below.

Table 7-3: Explanation of Terms Used for Likelihood of Occurrence

| An impact with a |
| --- |
| High probability | Refers to a very likely impact | Refers to very frequent impacts |
| Medium probability | Refers to a likely impact | Refers to occasional impacts |
| Low probability | Refers to rare impacts | Refers to rare impacts |
|  | As far as one-time events (e.g., air emissions) or slowly developing effects are concerned (e.g., impacts on local life style) | As far as possibly recurring impacts are concerned, such as accident or unplanned events (e.g., traffic accident, fire) |

## Definition of Mitigation Measures

Mitigation measures are developed to avoid, reduce, remedy or compensate for significant potential negative impacts, and to create or enhance potential positive impacts, such as environmental and social benefits. In this context, the term “mitigation measures” includes operational controls as well as management actions. These measures are often established through industry standards and may include:

- Changes to the design of the project during the design process (e.g., changing the development approach);

- Engineering controls and other physical measures applied (e.g., wastewater treatment facilities);

- Operational plans and procedures (e.g., waste management plans); and

- The provision of like-for-like replacement, restoration or compensation.

For potential impacts that are assessed to be of major significance, a change in design is sometimes required to avoid or reduce the significance. For potential impacts assessed to be of moderate significance, specific mitigation measures such as engineering controls are often sufficient to reduce these impacts to ALARP (‘as-low-as-reasonably-possible’) levels. This approach takes into account the technical and financial feasibility of mitigation measures. Potential impacts assessed to be of minor significance are usually sufficiently managed through good industry practice, operational plans and procedures.

In developing mitigation measures, the first focus is on measures that will prevent or minimize potential impacts through the design and management of the Project rather than on reinstatement and compensation measures.

## Positive Impacts - Pre-Construction

- Employment opportunities arising from recruitment of workers

- Skill acquisition and enhancements to locals and future workforce

- Improvement in quality of life for from the in-kind compensation agreed by the community member

## Positive Impacts During Construction Phase

This section enumerates and discusses the positive impacts associated with the proposed project during construction phase of the project.

### Creation of Employment Opportunities

Various employment opportunities will be available during construction. The opportunities will be both skilled and unskilled. Majority of the unskilled and semi-skilled jobs will be taken up by the local community. Employment of the locals will increase skill transfer from the contractors.

The approximate number of workers to be employed by the proposed project is not yet known, however, this will contribute to easing unemployment level in the area. There will be a trickledown effect to the economy at large resulting from new income revenues as well as services provided through this project.

The impact significance is low as it will employ few people over a short period

Enhancement Measures

- Contractor should ensure that they prioritise the local community in allocating job opportunities.

- Contractor should ensure that job opportunities are not discriminatory

- Equal opportunities should be given to both men and women

### Improving local economy

During this phase, the project will require supply of building materials most of which will be sourced locally at the nearest trading centre and its environs to the extent possible. Therefore, the project will provide ready market for local enterprises with such materials and boosts the local economy.

The businesses that will benefit during this phase are such as hotel, shops, artisan industries and food vending who will be benefit directly from the construction, as people working there will need commodities from them. This will promote the informal sector in securing some temporary revenues and hence improved livelihoods.

One of the responsibilities of the PAPs of the proposed Solar Mini-grid is to undertake wiring of their premises before there are connected and payment of a connection fee of Ksh 1000. The MOE through its implementing agency KP should consider supporting at least 50 households that are very poor through installation of ready boards to offset the cost of wiring so that they can also access electricity.

The impact significance is low as it will buy few materials over a short period of time

- KP should ensure that their contractors/suppliers remit taxes and have a tax compliance certificate

- Prioritise local purchases over imports.

- Remit taxes on behalf of employees

- Contractor should prioritise local purchases over imports;

- Contractor should give preference to the local labourers which increases the local’s ability to spend

## Positive Impacts during Operation Phase

### Quality, Reliable Power Supply

There is no electricity in Mkokoni This is a maiden project with an aim of supplying power through solar because the area is far away from the national power grid. Once operational, household and public institutions (dispensary, primary school) and shopping centre in the area will greatly benefit from the stable power supply.

The impact significance is high as it will provide power where it wasn’t for a long period

Enhancement Measures

- KP should ensure that they have a functional customer support team and a field response team;

- KP should ensure that they communicate power outages early to consumers

### Employment Creation

Employment opportunities will also be created during the operation phase of the project. Opportunities that will be created include unskilled, semi-skilled to skilled jobs. These will involve security personnel, and staff to operate and maintain the Mini-grid. Employment will increase skill transfers.

The impact significance is low as it will employee people to manage the project.

Enhancement Measures

- KP should ensure that they prioritise the local community in allocating job opportunities.

- KP should ensure that job opportunities are not discriminatory

- Equal opportunities should be given to both men and women

### Reduction of Pollution Associated with Thermal Power Generation, Kerosene and Wood Fuel Usage:

Residents in the area use different sources of energy. Electricity supply will imply that as many as are willing can apply for connection and get connected. This will result in reduced individuals and organizations using diesel generators, less reliance on kerosene, wood fuel and charcoal. This would mean less carbon dioxide is released to the environment and destruction of forests will be reduced hence decreasing greenhouse gases.

The impact significance is high as it will provide cleaner energy over a long [period of time for many households

Enhancement Measures

- KP should ensure that the power provided cost is competitive to discourage the locals from using unclean source of power.

- KP should ensure that they communicate power outages early to consumers

### Improvement of Local and National Economy

The mini-grid project will ensure supply of a stable power that will reduce damage to the electronics and this will result in promotion of businesses both in the formal and informal sectors. Availability of power will enable businessmen to scale up their businesses while making it is possible to set up businesses such as salons, barber shops, photocopying machines, cyber cafes, welding, refrigeration of drinks among others. This will result in income improvements at the individual level and for the national economy. More customers will be connected and retail of reliable electricity by the power utility firm will attract increased tax revenues to the government.

The impact significance is low as it will buy few materials over a long period of time

Enhancement Measures

- KP should ensure that their contractors/suppliers remit taxes and have a tax compliance certificate

- Prioritise local purchases over imports.

- Remit taxes on behalf of employees

### Education

Access to electricity at the household level and schools will create opportunities for children be able to study even for longer hours. Additionally, children in households can also access education programs being aired through different radio and T.V. channels. Schools will be able to take advantage of information technology and communication that are becoming a way of life in education sector and learning in general.’

The impact significance is high as it will provide power to schools over a long period for additional study time in the night and morning

Enhancement Measures

- KP should consider having the transmission lines are closer to schools for them to benefit from the power supply;

- KP should consider partnering with the county government in providing street lighting to improve security for children and teachers leaving for school early or leaving late for home

### Health Benefits of the Project

Solar energy for lighting is better than kerosene lamps that are in use currently. This is because kerosene lamps emit particles that cause air pollution. The health risks posed by this indoor air pollution mainly include acute lower respiratory infections. Additionally, insufficient illumination (low light) conditions can cause some degree of eye strain and reading in these conditions over long periods of time may have the potential to increase the development of near-sightedness in children and adults. The project will result in many families replacing kerosene lamps for lighting with electricity there-by reducing chances of the afore mentioned disease incidences.

### Improved Standard of Living

Availability of power will result in lifestyle changes through improved night lighting, pumping of water instead of manual pumping and refrigeration to maintain food safety and quality.

### Security

The area will benefit from improved security since houses, businesses and public institutions will be well lit using electricity. This is as a result of more security flood lights bulbs which helps keep off opportunistic crimes including gender-based violence.

### Communications

Access to electricity will lead to improved communication. This will be enabled by the fact that charging of mobile phones will be easier and cheaper. Access to mass media like radio and T.V will provide opportunity for the households to access a wide range of information which is useful for decision making.

## Positive Impacts during Decommissioning Phase

### Employment Opportunities

Once the project has served its purpose it will then be decommissioned. This will involve demolition and removal of the facility. During demolition, unskilled, semi-skilled and skilled employment opportunities will be available to the public.

### Site Rehabilitation

After demolition of the proposed project, rehabilitation of the project site will be carried out to restore it to its original status or to a better state than it was. This will include replacement of topsoil and re-vegetation which will lead to restoration of the visual, vegetative and aesthetic state of the site.

## Negative Impacts during Pre-construction Phase

### Land Take

The identified site for the proposed Mini-grid is part of a 0.411 Ha of Public Land that they set aside for construction of public facilities. The assessment found that;

- No residential houses or businesses premises were on the piece of land

- No socio-economic activity was taking place on the land

- No physical relocation will take place.

Way Leaves

Supply of electricity will involve passing of low voltage (LV) lines to connect the customers to power. It is estimated that a total of 7.8 km of LV circuit will be constructed mainly along the road reserve and along the boundaries to supply power.

The impact significance for this impact is assessed minor considering the community willingly allocated the land for project construction.

Mitigation Measures

- Land for mini-grids will be acquired by NLC compulsorily and affected communities compensated in-kind.

- The contractor will sign and adhere to the agreement for use of community land for contractor facilities and worker’s camps, and restoration of the site after use.

- The construction activities will be restricted to within the allocated land and the immediate surroundings only.

- After construction work, any land taken for a temporary basis for storage of material will be restored to their original form.

- Consultations with the community during construction of the low voltage lines

## Negative Impacts During Construction Phase

Despite the positive impacts identified, the project will also have negative impacts. However, adverse impacts are not anticipated due to its size and nature and most of the impacts will be experienced during construction phase of the project. The negative impacts and their mitigation are discussed below.

### Vegetation Clearance

The construction process of the proposed Mini-grid and other associated facilities and structures will involve clearing of the existing vegetation cover (mainly grass) and trees. The project site is located in open area with minimal settlement around besides the dispensary and residential homes. Both the magnitude and sensitivity of this impact will be low. The impact will be direct, permanent and minor.

Mitigation Measures

- Clear only the necessary areas

- Ensure proper demarcation and delineation of the project area to be affected by construction works.

- Specify locations for vehicles and equipment, and areas of the site which should be kept free of traffic, equipment, and storage.

- Designate access routes and parking areas

- Re-vegetation including planting of trees around the plant/facility

### Soil Erosion Impact

During clearing of the area to pave way for groundbreaking soil erosion may take place. This will be due to surface run off or blowing away by the wind if not properly managed. This is bound to happen because the soil will be loose. The area is gently slopy on the lower side and surface run off can also result to soil erosion. The impact significance will be minor due to the nature of the works and the fact that construction activities will be confined in the small project area.

Mitigation Measures

- The contractor shall avoid groundbreaking during the seasons of high rainfall to avoid erosion.

- Monitoring of areas of exposed soil during rainy seasons to ensure that any incidents of erosion are quickly controlled.

- The contractor should ensure that construction related impacts like erosion and cut slope destabilizing should be addressed through landscaping and grassing, carting away and proper disposal of construction materials

- Use silt traps where necessary

- Cover soil stockpiles.

- Landscaping with grass on areas without electrical installation (lower areas)

- The contractor should ensure recovery of exposed soils with grass and other ground cover as soon as possible.

- The contractor should put up proper drainage to avoid unnecessary erosion and do compaction of spoil areas to avoid land instability in form of soil subsidence, slip and mass movement.

- Areas compacted by vehicles during site preparation and construction should be scarified (ripped) by the contractor in order to allow penetration of plant roots and the re growth of the natural vegetation

### Contamination of Soil from Fossil Fuels

The potential sources of soil contamination during construction phase are oil /fuel leaks or spills from machinery used in site preparation and trucks used in transporting construction materials. Depending on the size and source of the spill, liquid and gaseous state, petroleum hydrocarbons may remain mobile for long periods of time, threatening to contaminate the soil. The significance of the impact to the soil will be minor due to the nature of the works and the fact that construction activities will be confined in the small project area.

Mitigation Measures

- Construction vehicles must be maintained in good state and proper servicing to ensure no oils are likely to leak

- Care must be exercised not to spill any fossil fuels

- Any contaminated soil shall be scooped and disposed-off appropriately.

### Dust Emissions

Initial activities such as site clearing, excavation if done in dry weather conditions will result in dust pollution. Dust emission from construction machinery is regarded as a nuisance when it reduces visibility and is aesthetically displeasing. This is expected during construction works. Dust will be generated from construction earthworks, transportation activities and aggregate mixing.

The receptors were noted to be mainly residential and a health facility. The distances from a source that dust impacts can occur is highly site specific and will depend on the extent and nature of incorporated mitigation measures, prevailing wind conditions, rainfall and the presence of natural screening. Due to the variability of the weather, it is impossible to predict what the weather conditions will be when specific construction activities are being undertaken. Therefore, the assessment of construction dust impacts is typically qualitative.

Mitigation Measures

- The construction area should be fenced off to reduce dust to the public

- Sprinkle loose surface earth areas with water to keep dust levels down.

- Construction trucks moving materials to site, delivering sand and cement to the site should be covered to prevent material dust emissions into the surrounding areas;

- Masks should be provided to all personnel in areas prone to dust emissions during construction

- Stockpiles of excavated soil should be enclosed/covered/watered during dry or windy conditions to reduce dust emissions.

- Drivers of construction vehicles must be sensitized so that they limit their speeds so that dust levels are lowered.

- Trees can be planted around the plant provided they do not cast shadows to the solar panels to act as wind breakers and hence decrease dust pollution

### Vehicle Exhaust Emissions

Exhaust emissions are likely to be generated by the construction vehicles and equipment. Motor vehicles that will be used to ferry construction materials would cause air quality impact by emitting pollutants through exhaust emissions. There are few Receptors (settlements) within 500 m of the project site and the impact magnitude will be medium and sensitivity medium hence the impact significance will be moderate.

Mitigation Measures

- Drivers of construction vehicles must be sensitized so that they do not leave vehicles idling so that exhaust emissions are lowered.

- Maintain all machinery and equipment in good working order to ensure minimum emissions of carbon monoxide, NOX, SOX and suspended particulate matter;

### Pollution from Solid Waste Generation

It is expected that solid waste will be generated during construction phase of the project. Solid waste is anticipated to be produced during site preparation, civil works, spoil from excavations and will include; mortar, wood, paper, waste paper wrappings, conductor off cuts, masonry chips and left-over food stuffs. Effects of mismanaged waste include:

- Public nuisance due to littering or smell in case of rotting

- Contamination of soils and water courses

- Creation of breeding grounds for vermin like rodents and cockroaches

The significance of this impact will be minor due to the nature of the works and the fact that construction activities will be confined in the small project area.

Mitigation Measures

- Ensure spoil from excavations is arranged according to the various soil layers. This soil can then be returned during landscaping and then rehabilitation, in the correct order which they were removed that is top soil last;

- Segregate waste and dispose of appropriately using a licensed waste handler

- Provide litter collection facilities such as bins and create awareness campaigns to segregate as early as possible, using the appropriate bins

- Contractor to put in place and comply with a site waste management plan

- The contractor should comply with the requirement of OSHA ACT 2007 and Building rules on storage of construction materials

- Use of durable, long-lasting materials that will not need to be replaced as often, thereby reducing the amount of waste generated over time

- Recovery of materials remains and return to stores

- Re-use of materials where possible

- Proper budgeting to avoid waste generation

### Impacts on Water Resources and Water Quality

During construction, excavation activities will involve soil exposure which results in soil erosion due to wind and surface runoff due to rains. Seepage from spilled fuels and oils and leaking machinery can also negatively impact groundwater water which could lead to potential contamination. Generally, due to the localized area of impact, the overall significance of the related impacts on water quality is considered to be minor, provided the necessary mitigation/ management measures are implemented.

Mitigation Measures

Measures shall be put in place to minimize erosion and sediment mobility, especially during construction. These measures include:

- Clear the necessary areas only.

- Appropriate remedial measures shall be implemented by the contractor in the event of erosion.

- Infrastructure shall be designed to ensure that contaminated run-off does not reach watercourses.

- In the event of an oil spill the procedures contained in the emergency response plan of the contractor will come into effect.

- No vehicle maintenance and service shall be done at project site but in approved garages or service stations to avoid any possible oil and fuel spills that could contaminate soils and possibly ground water quality.

- Ensure that potential sources of petro-chemical pollution are handled in such a way to reduce chances of spills and leaks.

- Construction activities to avoid any unchanneled flow of water at the site

- Storage areas that contain hazardous substances should be bundled with an approved impermeable liner and provision for a pit to be made in case of oil spill.

- The excavation and use of rubbish pits during construction should be strictly prohibited.

- A waste disposal area should be designated within the active construction area and this should be equipped with suitable containers i.e., skips or bins of sufficient capacity and designed to contain and prevent refuse from being blown by wind,

- Areas contaminated by spilled concrete and/or fuels and oils leaking from vehicles and machinery should be cleaned immediately.

- The contractor to source for alternative source of water for construction purposes to avoid potential conflict with the community

### Noise and vibration

During construction activities noise pollution will occur and is bound to be a nuisance and a disturbance to neighboring communities. This noise is from construction equipment, excavation works, concrete mixing and vehicles coming to site but will be temporary. From the prediction of the specialist study on ambient noise quality measurements, the traffic noise that will be emitted by traffic accessing the proposed project site during construction is expected to have an adverse impact on ambient noise. The level of traffic noise will increase depending on the traffic volume. General guideline indicates that an increase of 20% in traffic volume approximates to a noise level increase of around 1 dB, while a doubling of traffic volume results in a noise level increase of about 3 dB. It is however, worth noting that the level of noise is attenuated with increase in distance from the source and thus the sites/objects in close proximity to the source will receive more noise in comparison to those at remote location. The impact significance has therefore been assessed minor. This due to the fact that the impact magnitude is low and the receptor sensitivity is medium.

Mitigation Measures for Noise and Vibration

These proposed mitigation measures aim to ensure that noise generated during construction is kept to minimum and adheres to relevant noise standards. They include:

- Fencing off the construction site with iron sheet during construction

- Install portable barriers to shield compactors thereby reducing noise levels.

- Use of noise-suppression techniques to minimize the impact of construction noise at the project site.

- Use equipment designed with noise control elements.

- Co-ordinate with relevant agencies regarding all construction activities.

- Limit vehicles to minimum idling time and observe a common-sense approach to vehicle use, and encourage drivers to switch off vehicle engines whenever possible.

- Set and observe speed limits and avoid raving of engines

- The Contractor shall ensure that construction activities are limited to working hours (i.e., between 8am and 5pm daily) from Monday to Saturday, or as required in terms of legislation.

- Compliance with Noise and Vibration Regulations of 2009 is expected

### Impacts from Hazardous Materials

Some hazardous materials will be used during construction phase of the project. They include insulating oil, paints, solvents and oils. Spilled chemicals can contaminate soil as well as pollute water resources. Additionally, hazardous and flammable substances if improperly stored and handled on site become potential health hazard for construction workers and the public. The amount of hazardous waste generated will be minimal. The significance of the impact will be minor due to a low magnitude and medium sensitivity.

Mitigation Measures

- Maintenance of construction vehicles will not be done on site

- All hazardous products and waste should be labeled and handled properly to avoid contact with the ground

- Material handling to be done by trained and qualified staff

- The contractor site should have designated area (concrete bunded) for storing hazards materials

### Accidental Oil Spills or Leaks

There is possibility of oil leaks from construction vehicles. The construction machines on the proposed site have moving parts which will require continuous oiling to minimize the usual corrosion or wear and tear. These processes may lead to oil spill to the ground. The impact significance will be minor due to the nature of the works and the fact that construction activities will be confined in the small project area.

Mitigation Measures

- In the event of accidental leaks, contaminated top soil should be scooped and disposed of appropriately.

- It is proposed that the refueling and maintenance of vehicles will not take place at the construction site.

- Contractor to create awareness for the employees on site on procedures of dealing with spills and leaks from oil for the construction machinery

- Vehicles and equipment must be serviced regularly and kept in good state to avoid leaks.

- In case of spillage the contractor should isolate the source of oil spill and contain the spillage using sandbags, sawdust, absorbent materials and/or other materials approved by materials.

- Proper training for the handling and use of fuels and hazardous material for construction workers.

- All chemicals should be stored within the bunded areas and clearly labeled detailing the nature and quantity of chemicals within individual containers.

### Fire Hazards

During construction of the project, fire hazards are likely to occur especially when precaution measures are not taken to account. Smoking is one of causes of fires and this can happen if cigarette butts are left carelessly. Additionally, keeping of fuels onsite during construction can be a potential cause of fire. This impact is evaluated to be of moderate significance. All the construction activities will be confined at the project site hence high sensitivity and low magnitude.

Mitigation Measures

The following measures should be put in place to prevent fire hazards:

- Create awareness to the construction workers on potential fire hazards

- Provision of firefighting equipment (extinguishers) on site during construction.

- No smoking shall be done on construction site

- ‘No smoking’ signs shall be posted at the construction site

- A fire evacuation plan must be posted in various points of the construction site including procedures to take when a fire is reported.

### Impacts of construction material sourcing (e.g., quarrying)

The construction of the project will utilize materials such as; stone, ballast, sand and hardcore. It is anticipated that they will be obtained from quarry and mining operations. Conscious or unwitting purchase of these materials from unlicensed operations indirectly supports, encourages and promotes environmental degradation at the illegal quarry sites and causes medium to long term negative impacts at source, including landslides. The significance of this impact will be moderate due to high sensitivity and low magnitude.

Mitigation Measures

- The contractor should source all building materials such as stone, sand, ballast and hard core from NEMA approved sites.

- Ensure accurate budgeting and estimation of actual construction materials to avoid wastage.

- Reuse of construction materials where possible.

### Increased Water Demand

During the construction of the project there will be increased demand for water by the construction workers and the construction works. Water will be mostly used in the construction works and for wetting surfaces or cleaning completed structures. It will also be used by the construction workers to wash themselves and even drink. Although the sensitivity of the receptor (surface water) in the project area is high owing to unavailability of feasible alternative source of water for the local community, the overall significance of impacts is assessed to be negligible due to negligible magnitude of the impact.

Mitigation Measures

- Prudent use of available water

- Consultations with the project local committee on use of water in the community to avoid conflicts with the community

- Contractor to make own arrangements to provide water for construction works different from the community dam to avoid any conflicts with community.

### Energy Consumption

The construction works will consume fossil fuels (mainly diesel) to run transport vehicles and construction machinery. Fossil energy is non-renewable and its excessive use may have serious environmental implications on its availability, price and sustainability. This impact will be negligible owing to the size of the project that will require very few trucks during the construction phase.

Mitigation Measures

Proper planning of transportation of materials will ensure that fossil fuels (diesel, petrol) are not consumed in excessive amounts. Complementary to these measures, the contractor shall monitor energy use during construction and set targets for reduction of energy use.

- Regular maintenance of vehicles to ensure efficient consumption of fuels.

### Occupational Health and Safety Impacts

There are several activities involved during construction. These activities can pose potential health and safety risks to the workers. The activities include excavation, backfilling, civil works, pole erection, stringing of conductors. Risk of accidents and incidents are likely during construction activities. As already noted during construction, the safety and health of employees may be exposed to risk as a result of the use of tools and other machinery to construct the Mini-grid. Occupation safety and health risks includes accidents, fall from heights, pricks by sharp objects etc. The impact on occupational health and safety during the construction phase is evaluated to be of moderate significance. All the construction activities will be confined at the project site hence high sensitivity and low magnitude.

Mitigation Measures

- The contractor should use skilled personnel for activities that demand that.

- Awareness creation/Tool box talks on safety to workers while at construction site and documentation kept

- Workers coming to the site should be knowledgeable on safety precautions to take

- Appropriate PPE (helmet, safety harness, gloves, safety shoes, masks, climbing irons among others)

- Proper housekeeping and maintain good hygiene

- Close supervision of workers

- Engagement of trained first aider on site

- Provide safe drinking water for workers

- Availability of equipped first aid box on site

- Risk assessment by contractor of the construction activities and implement mitigation measures appropriately

- Adherence to occupational Safety and Health Act 2007

- Establish Safety committees

- The contractor must acquire insurance for the workers-WIBA cover

### Community Safety -Access to Site by General Public

If access to the Mini-grid site is not controlled then it can lead to people entering the site including animals. This can result to accidents. Impact significate is rated as moderate considering the high impact magnitude and low receptor sensitivity.

Mitigation Measures

- Proper barricading

- Awareness creation to community

- Hazard communication.

- Controlled access to the site by designated personnel

- Maintain records of any person who comes to site

### Spread of HIV/AIDS and STIs

HIV and AIDS remain a major challenge in Kenya as well as in Mkokoni County. The epidemic continues to adversely impact on all spheres of the County; economic, social and health sectors.

The project construction will improve the economic status of some of the people employed thus increasing the disposable income with the probability of indulgence in substance abuse and using the money to solicit for sex. Researchers have indicated that HIV prevalence rates are higher in areas where there is high disposable income as might be the case during construction of the project

Mitigation measures include:

- Develop and implement at HIV/AIDS Policy to promote awareness of HIV/AIDS and access to treatment.

- Employees contractors and subcontractors will be required to follow, and will be trained in, the Worker Code of Conduct which includes context specific guidelines on worker-community interactions, worker-worker interactions and alcohol and drug use.

- Employees, contractors, and subcontractors will be trained and educated to improve awareness of transmission routes and methods of prevention of sexually transmitted infections, communicable diseases and vector borne diseases, notably malaria, prior to working on the Project site. Other diseases will be covered as appropriate.

- Provide access to free condoms at all worker sites and accommodation.

- Work with NGOs or the Ministry of Health to develop and implement a community sensitisation programme on HIV/AIDs and communicable diseases.

- Continue to implement a programme of stakeholder engagement including a grievance mechanism in communities in the Project Area.

- Monitor health trends during Project construction (and operations) in order to be aware of and respond appropriately to any negative health trends that may be linked to the Project and its workers.

### Increase in competition for scarce resources and strain on public utilities

The influx of workers in the area is expected to lead to increase in demand for public amenities such as hospitals, transport, schools water resources etc. This could lead to a loss of access to these services by locals especially those who could be among the vulnerable categories. Due an increase in demand, cost of housing near the sites will disadvantage the locals.

The nature of the project will require technical skills that might not be available in the community. This might require movement of construction workers into the community. It is expected that technically skilled personnel might be sourced from outside the community while the unskilled labour is expected to be sourced locally. It is therefore a possibility that the neighbouring communities might go out looking for opportunities in project area thus creating competition. The significance of this impact is considered to be minor because the receptor sensitivity will be medium, and the impact magnitude is low.

Mitigation Measures

- Reduction of labour influx by tapping into the local workforce to the extent possible

- Recruitment of local workforce to the extent possible especially unskilled and semi-skilled jobs

- Consultations with and involvement of local community in project planning and other phases of the project

- Awareness-raising among local community and workers on the need to have a good /cordial working relation

- Sensitization/awareness to workers regarding engagement with local community.

- Contactor shall make provision to provide resources needed by the workers if the need for such resources may result to competition e.g., water

- Establishment and operationalization of an effective Grievance Redress Mechanism accessible to community members

- The contractor and the project/community grievance redress committee to work closely address complains raised on time.

- Gender considerations in employment opportunities

- Appropriate compensation for work done

- Respect for community values/culture

- Prompt payments as per the contractual agreements/terms

### Child Labor

Implementation of the project could lead to increased opportunities for the host community to sell goods and services to the incoming workers. This can lead to child labour to produce and deliver these goods and services, which in turn can lead to school truancy. The impact significance is rated minor, based on low sensitivity of the receptor and medium magnitude of the impact.

Mitigation Measures

  - Awareness creation to the community that child labour is illegal and that children have a right to education.

  - Communication to the contractor that child labour is illegal and adherence to employment act is required.

### Gender Based Violence- SEA and SH

Gender-based violence (GBV) is an umbrella term for any harmful act that is perpetrated against a person’s will and that is based on socially ascribed (i.e., gender) differences between males and females. It includes acts that inflict physical, sexual or mental harm or suffering, threats of such acts, coercion, and other deprivations of liberty. GBV in project may manifest in terms of sexual exploitation and abuse (SEA) and workplace sexual harassment (SH).

Sexual Exploitation and Abuse (SEA) is any actual or attempted abuse of a position of vulnerability, differential power, or trust, for sexual purposes, including but not limited to, profiting monetarily and socially from the sexual exploitation of another. Sexual abuse is further defined as “the actual or threatened physical intrusion of a sexual nature, whether by force or under unequal or coercive conditions.” Women, girls, boys and men can experience SEA.

Workplace sexual harassment (SH) includes unwanted sexual advances, request for sexual favors and sexual physical contact.

Sexual exploitation and abuse (SEA) of community members by project workers and sexual harassment (SH) among project workers are forms of GBV that are a potential risk and impacts to this proposed project. GBV has serious and far-reaching negative effects including physical injuries resulting in death or disfigurement, psychological trauma, infection with HIV/AIDS, unwanted pregnancies, social stigmatization and exclusion and economic deprivation among others. Consequently, it is incumbent that preventive measures be mooted to prevent occurrence of such cases.

There are few but rare incidents of gender-based violence in  as identified during FGD with Men, women and youths. However, it cannot be ruled out during project implementation. Thus, the significance of this impact is considered to be Minor considering low sensitivity of the receptor and low magnitude of the impact.

Mitigation Measures

To manage GBV risks, the contractor will prepare a SEA/SH Prevention and Response Action Plan that will include a GRM that ensures confidentiality. The plan should have an Accountability and Response Framework. The plan will include the necessary measures for prevention and response. The contractor can make reference to World Bank’s Good Practice Note for Addressing Gender-based Violence in Investment Project Financing involving Major Civil Works (Sept 2020) for further guidance.

It should be noted that the decision to report a GBV case lies with the survivor or the guardians if the survivor (in case of a minor) and such a decision must be respected. Therefore, the contractor or project will only refer the survivor of guardian to the established referral pathway, including the nearest police station with a gender desk for handling GBV cases. Also, should a survivor choose legal redress, the project will similarly facilitate him/her by referring him/her to the nearest established legal support facility that offers legal support to GBV survivors.

Key tasks will include:

- Community engagement to create awareness on SEA/SH risk/ issues

- Creating awareness to workers on the need to refrain from SEA/SH incidences

- Mandatory awareness creation for workers on required lawful conduct in the community and legal consequences for failure to comply with laws

- Mandatory signing and implementation of code of conduct for the workers

- Creation of partnership or liaison with specialized actors in GBV who can respond appropriately in case of any incidence (provide contacts to community)

- Ensure a survivor centered approach in responding to SEA/SH incidences i.e., decision to report lies with the survivor or the guardian in case of a minor.

- Contractor to provide established referral pathway including police station with a gender desk for handling SEA/SH cases and also free toll numbers/hot lines for reporting GBV

- The contractor will also facilitate any survivor who decides to take legal action by referring them to the nearest established legal support facility that offers legal support to GBV survivors.

- Ensure Confidential reporting and responding to SEA/SH cases if reported;

- Encourage reporting of all SEA/SH incidences to the chief or the grievance redress committee members or community elders; and

- Ensure all complaints on SEA/SH or harassment are reported directly through CREO - county renewable energy officer.

### Public Health Impacts

Construction works/activities will bring people together and new interactions between people are likely to happen. These interactions are likely to pose risks to the social fabric of the community. Such risks include public health related issues such as (COVID-19 infections and spread, HIV/AIDS, communicable and sexually transmitted diseases (STDs). The receptor sensitivity is medium and low magnitude, hence Minor significance.

Proposed Mitigation Measures

- Sensitize workers and the community on prevention and mitigation of HIV/AIDS and other sexually transmitted diseases, through staff training, awareness campaigns and community Barazas.

- Awareness creation and consultations with local communities prior and during construction on the dangers of these diseases

- Informing workers on local cultural values and health matters.

- Provision of condoms to workers

- Allowing migrant workers time to be with their families

- The contractor is impressed upon not to set a construction camp on site.

- The contractor will provide public education/information about HIV/AIDS transmission and prevention measures.

- Ensure equal treatment of workers

- Provide all appropriate COVID-19 preventive measures including campaign to maintain individual measures at the work place.

w) Public Health Impacts Sanitary Waste

Currently at the site there is not sanitary waste system (toilet) except one that is being constructed for the dispensary. There is need to dispose sanitary waste in manner that will not pose health hazards to the workers and the community. The receptor sensitivity is medium and low magnitude, hence Minor significance.

Mitigation Measures

- Construct/ install pit latrines for both genders clearly labelled

### Forced Labour

During construction of the mini-grid the risk of forced labour is likely to occur and precaution is need to safe guard the community from being subjected to forced labour. The impact significance is rated minor, based on low sensitivity of the receptor and medium magnitude of the impact.

Mitigation Measures

- Contractor must adhere to the employment Act which outlaws any form of forced labour

- Community to report any form of forced labour at the site

- Contractor to ensure that all workers have a national ID card or documentation to show they are adults (above 18 years).

### Risks related to Inadequate Stakeholder Engagement

Lack of timely and adequate stakeholder engagement during construction is a recipe for dissatisfaction among stakeholders affected and can result to grievances which may turn to conflicts and delays in project construction. With the implementation of the mitigation measures the impact significance is minor.

Mitigation measures;

- The contractor will design and implement a stakeholder engagement schedule to ensure various stakeholders are engaged at and informed about the project on a timely basis and respond to issues that the stakeholders may require.

- The contractor will also prepare and implement a grievance redress mechanism to deal with grievances. The grievance redress mechanism committee of this GRM should also include representatives from the community.

## Negative impacts during Operation phase of the project

NOTE: According to the MOE the proposed project will be constructed by a third party (contractor) who will also operate and maintain the solar mini-grid for a period of ten years and then hand over the plant to Kenya Power who is the implementing agency of the plant on behalf of the MOE. Therefore, mitigation measures against negative impacts during the first ten years will be the responsibility of the contractor after which  KP will take over.

### Solid Waste Generation

The proposed Mini-grid is expected to generate some amounts of solid waste during its operation phase. The type of the solid waste generated during the operation of the project will consist of paper, drums, plastic, cables, meters, panels. Such wastes can be injurious to the environment. Some of these waste materials especially the plastic, cables, metals, polythene among others are not biodegradable hence may cause long-term injurious effects to the environment. The overall impact significance on land due to waste disposal during O&M phase has been assessed as minor due to medium sensitivity and low magnitude.

Mitigation measures

The contractor will be responsible for efficient management of solid waste generated by the project during its operation. In this regard, the contractor;

- Will provide waste handling facilities such as labelled waste bins for temporarily holding solid waste generated at the site.

- He shall put in place an emphasis on prudent waste generation and will give priority to reduction at source. This option will demand a solid waste management awareness among the employees.

- Separation of hazardous waste from non-hazardous waste is required

- Use long-lasting materials that will not need to be replaced as often, thereby reducing the amount of waste generated.

- He will ensure that waste is disposed of regularly and appropriately.

- Waste should then be handled, collected, transported and disposed according to the Environmental Management and coordination (waste management) regulations of 2006.

### Liquid Waste/Oils Generation

The solar Mini-grid will have a small diesel backup generator which will operate in the event that the solar energy is limited for example during rainy and cloudy seasons. From its operations there will be waste oil. There is also potential for oil spills and accidents during oil loading to the generator, storage and operations. These oil spills can pollute the soil and even ground water. The liquid waste to be generated is hazardous hence may cause long-term injurious effects to the environment. The overall impact significance on land due to liquid waste disposal has been assessed as minor due to medium sensitivity and low magnitude.

Proposed mitigation measures

- Proper storage of the oil is required to ensure no leakages/ spills to the ground

- Frequent inspection and maintenance of the generator to minimize leakages.

- No vehicles should be serviced or maintained at the Mini-grid area.

- The waste oil or used oil must be disposed-off using NEMA approved waste handlers

- Proper training for the handling and use of fuels for the operators of the Mini-grid.

- In the event of accidental leaks, contaminated top soil should be scooped and disposed of in accordance to the law

### Increased oil Consumption

The proposed Mini-grid shall consume fuel/oil in the process of backing up the solar energy required. The fuel is produced mainly through non-renewable resources, implying this will have adverse impacts on these non-renewable resources base and their sustainability. The impact will be of minor significance.

Mitigation Measures

To ensure efficient energy consumption during the operation phase of the project, the contractor to install an energy-efficient lighting system at the project site facilities. This will contribute immensely to energy saving during the operational phase of the project. In addition, the plant operators will be sensitized to ensure energy efficiently in their daily operations.

### Increased Storm Water Flow

The panels, building roofs and pavements of the proposed Mini-grid will lead to increased volume and velocity of storm water or run-off flowing across the area covered by the solar panels during operation phase. This will lead to increased amounts of storm water entering the drainage systems. The impact will be of minor significance.

Mitigation Measures

- Construct the drainage system in a way to follow natural drain of the water

- Concrete only the required area and leave the rest of the land with vegetation like grass

- Construct rain harvesting system on the control buildings/office and harness into storage tanks for use

### Fire Outbreaks

Carelessness and negligence both at the solar mini-grid and by the PAPs of electricity may cause fires. With the mitigation measures in place the impact is evaluated to be of moderate significance due to high sensitivity and low magnitude.

Mitigation Measures

- The power plant must contain firefighting equipment (Portable fire extinguishers) of recommended standards and in key strategic points

- Detection/alarm systems that can detect fire should be considered and installed

- A fire risk assessment and evacuation plan should be prepared and posted at strategic points and should include procedures to take when a fire is reported.

- Workers especially operators of the plant must be trained on fire fighting and management

- ‘No smoking’ signs shall be posted within the Mini-grid area

- A fire Assembly point should be identified and marked

### Visual Impacts

Once complete the Mini-grid will present visual impacts, both by its physical presence and by visual impacts of its associated structures. Visual intrusion caused by the Mini-grid may cause alteration to the natural scenery of the project area. Some people however, do not notice structures or do not find them objectionable from an aesthetic perspective. To some, the Mini-grid and its utilities may be viewed as part of the infrastructure necessary to enhance everyday lives and activities while to other it represents economic development. The project and its surrounding area are new for such developmental project and will have visual impacts during initial period of Project and the same will disappear over a period of time. Based on the above, significance of visual impact on landscape during operation phase of the project has been assessed as minor due to low receptor sensitivity and impact magnitude being medium.

Mitigation Measures

- The visual negative impacts can be mitigated through putting up a fence round to keep off/screen the solar panels.

- Planting of short trees along the fence

### Water demand

During this period the demand for water will be lesser than that used in construction. However, some amounts of water will be needed in wiping of the panels and use at the solar plant facility. Therefore, caution need to be exercised to ensure prudent use of water. The impact is assessed to be negligible due to very low magnitude of the impact.

Mitigation Measures

- There is need to source for a sustainable water source for use

- Install water-conserving automatic taps

- Encourage water harvesting from rooftops and storage for cleaning purposes (washing the panels off dust)

- Any water leaks through damaged pipes and faulty taps should be fixed promptly.

### Sanitary waste

Although there are few people who will be running the Mini-grid during operation phase provision for disposal of sanitary waste must be put in place through septic tanks. The impact is assessed to be negligible due to very low magnitude of the impact.

Mitigation Measures

The area is not served by a sewer system and sanitary waste will be drained through use of septic tanks.

### Flooding

Flooding may occur and cause damage to the plant and other associated infrastructure but the risk of occurrence is low since the area is not known for regular flooding. The impact is assessed to be negligible due to very low magnitude of the impact.

Mitigation measures

- Ensure drainage channels are free of any obstruction at all times i.e., not blocked

- Construct more channels and or expand existing ones

- Raise foundations of the solar panels and ensure a proper and firm concrete base

- Create flooding diversions and or spill ways to divert water from getting into the solar power facility

### Workers Occupation Health and Safety

Working within the Mini-grid can poses potential health hazards and accidents to workers. Therefore, caution must be taken to ensure that the Mini-grid does not pose a health and safety risks to workers. Because the maintenance activities will be conducted less frequently, the impact magnitude on occupational Safety and Health will be low. Considering that the accidents may result in injuries and death, the sensitivity is considered to be High. Therefore, the significance is Moderate.

Mitigation Measures

- Ensure only qualified staff are employed to work in the facility

- All workers operating the Mini-grid must be equipped with appropriate and adequate person protective equipment (PPE) such as; safety footwear, helmet among others.

- Operators must be skilled on firefighting management

- Annual environmental audits should be done

- WIBA cover for staff is mandatory

### Hazardous waste

The amount of hazardous waste generated will be very low and possibly originate from maintenance works and would include; used up batteries, damaged panes, waste oil, and their containers, used rags and spent clean-up rags. This impact is assessed as minor due to medium sensitivity and low magnitude.

Mitigation Measures

- These waste wastes should not be mixed with other non-hazardous waste

- Operator to have a designated waste storage area for absolute lead-acid batteries awaiting disposal

- These wastes should be disposed by NEMA approved handlers

### Noise and Vibration

Negligible noise and vibration will be produced during operation phase of the project and would be from the backup generator.

Mitigation Measures

The generator room should be made sound proof to ensure no noise of a nuisance level will be produced. The contractor should also monitor noise levels by taking tests and putting in appropriate measures.

### Electric and magnetic fields (EMFs)

Electric magnetic fields are only anticipated during operation period, but these are negligible. The exposure to would be little EMFs is highly negligible because the EMFs produced by the electrical installation are low. Consequently, the study does not anticipate impacts of EMFs.

### Shocks and electrocutions to the PAPs

Majority of the PAPs who will be customers and users of the power have not used electricity before. Failure to take appropriate precaution while interacting with electricity can result in electric shocks, fires and even electrocution/death. Impact significate is rated as moderate considering the high impact magnitude and low receptor sensitivity.

Mitigation Measures

The following precaution/preventive measures need to be observed in order to prevent risk of electric shocks, fires and electrocutions.

- Inspect the wiring of the houses before connecting power

- Safety awareness campaigns to the community before connection of power on safety precautions such as

  - Require community to engage a certified technician to do wiring in the premises

  - Use of quality materials while wiring

  - Refraining from individual illegal extensions of power lines to other houses

  - Observing safety measures while using electricity such as not touching sockets and switches with wet hands or wiping with wet cloths

  - Keeping off all electricity infrastructure e.g., not tying livestock on electric poles, no cutting earth wires that run along some electric poles, not interfering with sockets or switches

  - Reporting any electric wire/conductors if found fallen on the ground

  - Report any incident regarding electricity at the local office –staff in charge of operating the Mini-grid

### Community safety -Access to the facility by general public

Once operational the facility/plant will need controlled access from the public to avoid any safety risks. The contractor will put the following measures to ensure the public will not access the site without permission. Impact significance is rated as moderate considering the high impact magnitude and low receptor sensitivity.

Mitigation Measures

- Fencing off the facility to keep of community members, children and livestock from entering into the facility

- Controlled access to the site only with prior approval

- Maintain records of any person who comes to site

### Risks related to poor or inadequate stakeholder engagement (Conflict)

During operation of the project there are grievances that may arise from community and other stakeholders related to poor or inadequate engagement of stakeholders and other need for information or challenges in using power by the community. Therefore, the contractor will design and implement a grievance redress mechanism to deal with grievances. The grievance redress mechanism committee should also include representatives from the community. With the implementation of  the mitigation measures the  impact significance is minor to negligible.

Mitigation measures

- Employ from the community to the extent possible

- Engage the community members and other stakeholders in a timely manner

- Work closely with the GRM committee members in solving the conflicts

- Solve all conflicts/grievances at the earliest time possible

- Ensure all grievances are logged and closed

- Monitoring the pattern of grievances to come up will long term measures

### Gender Based Violence- SEA/ SH

Gender based violence risk is also possible during operation phase although the labor force will be smaller. the impact is assessed as minor due to the low magnitude and medium receptor sensitivity. Therefore, measures must be put in place to address GBV risks.

Mitigation Measures

To manage GBV risks, the contractor will prepare a SEA/SH Prevention and Response Action Plan that will include a GRM that ensures confidentiality. The plan will include the necessary measures for prevention and response.

Key tasks will include

- Community engagement to create awareness on GBV risk/ issues

- Creating awareness to workers on the need to refrain from GBV incidences

- Mandatory awareness creation for workers on required lawful conduct in the community and legal consequences for failure to comply with laws

- Mandatory signing and implementation of code of conduct for the workers

- Creation of partnership or liaison with specialized actors in GBV who can respond appropriately in case of any incidence (provide contacts to community)

- Ensure a survivor centered approach in responding to GBV incidences i.e., decision to report lies with the survivor or the guardian in case of a minor.

- Contractor to provide established referral pathway including police station with a gender desk for handling GBV cases and also free toll numbers/hot lines for reporting GBV

- The contractor will also facilitate any survivor who decides to take legal action by referring them to the nearest established legal support facility that offers legal support to GBV survivors.

- Ensure Confidential reporting and responding to GBV cases if reported;

- Encourage reporting of all GBV incidences to the chief or the grievance redress committee members or community elders; and

- Ensure all complaints on GBV or harassment are reported directly through CREO - county renewable energy officer.

### Public Health Impacts –HIV/AIDs

There is potential for HIV/AIDs risks during operation phase. Therefore, the contractor need to put measures to prevent the same. Based on the fact that the receptor sensitivity will be medium and the impact magnitude low, the impact significance will be Minor.

Mitigation Measures

- Sensitize workers and the community on prevention and mitigation of HIV/AIDS and other sexually transmitted diseases, through staff awareness and awareness campaigns for the community

- The contractor will provide public education/information about HIV/AIDS transmission and prevention measures.

- Provision of condoms to workers

- Allowing migrant workers time to be with their families

### Public health Impacts -Covid 19 disease

It is likely that the project will be implemented during the Covid 19 pandemic and so preventive measures must be put in place to prevent the disease from spreading. The receptor sensitivity will be medium and the impact magnitude low, therefore, the impact significance will be Minor.

Mitigation Measures

- Social distance must be observed

- Provision of hand wash facilities before access

- Provide thermal guards for temperature check and monitoring for workers and any other person coming to site

- Enforce wearing of masks

- Make provision for testing and treating especially of workers

- Display Ministry of Health guidelines on COVID 19 at strategic points and ensure adherence

- Create awareness on COVID 19 preventive measures

- Provision of contact numbers for the nearest health facility for testing and treatment

- Adhering to any other measures from the ministry of health which may be issued from time to time

### Dust emissions

During operation phase not much dust will be generated from the facility but wind and dust storms are potential impacts. This impact will be negligible because there will be no activities on site that will have the potential to generate dust.

Mitigation Measures

- Trees can be planted around the plant/facility provided they do not cast shadows to the solar panels to act as wind breakers and hence decrease dust pollution

- Ensure planting of grass around and within the facility compound

### Vehicle exhaust emissions

Exhaust emissions are likely to be generated by the vehicles coming to the facility though on a low risk. Due to the low magnitude of the impact and the low sensitivity, the significance will be minor.

Mitigation Measures

- Drivers of the vehicles must be sensitized so that they do not leave vehicles idling so that exhaust emissions are lowered.

- Company vehicles should be well maintained

## Negative impacts during decommissioning phase

Preparation for decommissioning

The solar power plant may be decommissioned due to various reasons and there are impacts that will need to be mitigated. Once KP makes the decision for decommissioning the following will be required;

- Prepare a Decommissioning Plan and submit to NEMA and the County Governments of Lamu to obtain approval for implementation.

- Implement the decommissioning plan including backfilling, revegetation, disposal of waste material, recycling of recyclable material among others

Some of the negative impacts associated with the proposed project during its decommissioning phase include;

### Noise and Vibration

The demolition works will lead to significant deterioration of the acoustic environment within the project site and the surrounding areas. This will be as a result of the noise from demolition works. The impact significance has been assessed minor due to the fact that the impact magnitude is low and the receptor sensitivity is medium.

Mitigation Measures

Significant impacts on the acoustic environment will be mitigated by the KP who will put in place several measures that will mitigate noise pollution. The following noise-suppression techniques will be employed to minimize the impact of temporary noise at the project site.

- Install portable barriers to shield compressors and other small stationary equipment where necessary.

- Use quiet equipment (i.e., equipment designed with noise control elements).

- Co-ordinate with relevant agencies in case the noise produced will require a license.

- Limit pickup trucks and other small equipment to a minimum idling time and observe a common-sense approach to vehicle use and encourage workers to shut off vehicle engines whenever possible.

- Demolish mainly during the day when most of the neighbours are out working.

### Solid Waste Generation

Demolition of the Mini-grid and related infrastructure will result in generation of solid waste. The waste will contain the materials used in construction including concrete, metal, wood, glass, paints, adhesives, sealants and fasteners, conductors, poles solar panels and batteries. Although demolition waste is generally considered as less harmful to the environment since they are composed of inert materials, there is growing evidence that large quantities of such waste may lead to release of certain hazardous chemicals into the environment. The impact will be of major significance due to high magnitude and medium receptor sensitivity. The batteries and panels need to be disposed in a specific way, in accordance to the manufacturer’s guidelines and relevant regulations (both National and Lamu County Government regulations).

Mitigation Measures

- Demolition contractor to adhere to the various manufacturer’s guidelines and requirements regarding demolition and disposal

- Segregation of waste in order to separate hazardous waste from non-hazardous waste and other streams of waste

- Provision of facilities for proper handling and storage of demolition materials to reduce the amount of waste caused by damage or exposure to the elements

- Adequate collection and storage of waste on site

- Safe transportation to the disposal sites / designated area

- Hazardous waste must be disposed by NEMA approved waste handler

### Dust Emissions

Some dust will be generated during demolition works. This will affect demolition staff as well as the neighbours. The impact will be of minor significance.

Mitigation Measures

High levels of dust concentration resulting from demolition or dismantling works will be minimized as follows:

- Watering all active demolition areas to kill dust.

- Cover all trucks hauling soil, sand and other loose materials or require all trucks to maintain at least two feet of freeboard.

### HIV/AIDs awareness and prevention

Interactions during the decommissioning phase will be for a very limited time. The project will sensitize workers and the surrounding communities on prevention and mitigation of HIV/AIDS and other sexually transmitted diseases, through staff training and awareness campaigns/ to the community. This impact is assessed to be Minor due to the low magnitude and medium receptor sensitivity.

## Social Protection

There will adequate mechanisms in place to protect local vulnerable population especially women and minors from risks associated with influx of workers (harassment, underage sex). This system will ensure having security on site provided by the contractor as well as sensitization and enforcement by the contractor. There will also be a code of conduct established for contractor employees and contract workers acknowledging a zero-tolerance policy towards child labor and child sexual exploitation. Additionally, the contractor will employ their skilled staff and apply unskilled construction labor from the local population as far as possible to minimize on influx of foreigners into the community.

## Social Inclusion

Gender Mainstreaming

Projects usually affect women and men differently, and their roles are highly delineated. The project shall ensure that both men and women are equally consulted about the project and benefit from employment and other opportunities the project will present.

In addition, among communities, some groups are faced with barriers that prevent them from fully participating in political, economic, and social life. Disadvantage is often based on social identity, which may be derived from gender, age, economic status, ethnicity, disability, among other factors. These factors make some groups of people more vulnerable to project impacts than others alongside posing barriers to accessing project benefits. Thus, development projects affect people differently but vulnerable groups are more severely affected than those that are better off.  In this project, some groups of the society that can be categorized as the vulnerable. These include the very poor, poor female headed households, poor children headed households, the poor elderly and the special needs persons (disabled). To ensure social inclusion and social sustainability, deliberate effort must be made to ensure the vulnerable take advantage of the project benefits as well as shielding them adverse impacts of the project.

# CHAPTER EIGHT: ENVIRONMENTAL AND SOCIAL MANAGEMENT AND MONITORING PLAN (ESMMP)

## Introduction

Environmental and Social Management and Monitoring Plan (ESMMP) for development projects provides a logical framework within which identified negative environmental and socio–economic impacts can be mitigated and monitored. The ESMMP has been developed to be used as tool to manage the environmental and social impacts that the activities of the proposed project will cause. The contractor before construction will make reference to this ESMMP and develop specific implementation plans. In addition, the ESMMP assigns responsibilities of actions to various actors and provides a timeframe within which mitigation measures and monitoring can be done.

The key objectives of the ESMMP are:

- To monitor the implementation of mitigation measures against potential adverse impacts of construction and operation phases of the project to ensure that they conform and comply with relevant environmental and social policies, guidelines and legislation

- To assess for emerging non-anticipated adverse environmental and social impacts and implement relevant mitigation measures to maintain them within acceptable levels

- To maintain best practice in environmental, social health and safety during project construction and operation

The ESMMP outlined below addresses the identified potential negative impacts and mitigation measures of the proposed Mini-grid during pre-construction, construction, operational and decommissioning phases, based on the chapter of Environmental Impacts and Mitigation Measures of the potential negative impacts.

## Monitoring

Monitoring denotes a systematic process of collecting, analysing and using information to track the progress of implementation of the ESMMP including coming up with measures to address any emerging issues. Monitoring of the ESMMP will involve recording information to track performance and recommendations to keep implementation of ESMMP on track. Reporting is a key component of the monitoring exercise.

The proposed ESMMP will be subjected to monitoring. Monitoring will have two elements: routine monitoring against standards or performance criteria; and periodic review or evaluation. Monitoring will often focus on the effectiveness and impact of the ESMMP as a whole.

During construction phase, the Implementing agency (KP) shall monitor the contractor’s activities in order to verify that the management measures/procedures/specifications are implemented as contained in the ESMMP. Compliance will mean that the contractor is fulfilling their contractual obligation.

During operation phase, KP will monitor facility’s operations to ensure compliance with management measures in the ESMMP and operation procedures. As part of this monitoring, the KP will undertake or statutory initial environmental audit as required by the ESIA/EA Regulations, 2003 and subsequent annual environmental audits.

## Plan Monitoring

All of the management plans make provision for monitoring and evaluation. Special attention should be given to the monitoring arrangements relating to biophysical impacts, occupational health and safety, social risks, facility operational and emergency response.

During the construction phase of the project, the contractor’s Environmental Health and Safety Officer (EHSO) shall report on the implementation of the ESMMP i.e., all environmental, safety and health impacts as well as accidents and incidents to the implementing agency. The social specialist of the contractor will report on implementation of the social measures as spelt out in the ESMMP.

The reported impacts and incidents will be captured on a database to ascertain trends and track progress in the implementation of preventive and corrective actions, and benchmarking against other, similar operations.

During operation, the implementing agency – KP will monitor the health and safety of personnel and contractors, in compliance with legislative requirements. Emergency incidents should be reported to the relevant authorities. The reported impacts and incidents will be captured on a database to identify weakness in the emergency response plan and track progress in the implementation of preventative and corrective and benchmarking against other similar operations.

The Environmental and Social Management and Monitoring Plan (ESMMP) will provide the basis for monitoring of potential Environmental, social and health Impacts associated with the project. The ESMMP provides effective observation and documentation of monitorable parameters that will help in analyzing the effectiveness of the proposed mitigation measures with the advantages of improving operational efficiency, promoting competitive advantage, improving risk management, reducing liabilities and improving business performance.  The ESMMP has been provide below.

## Environmental and Social Monitoring by Contractors

KP will require that contractors monitor, keep records and report on the following environmental, health and social issues of the proposed project.

- Safety: hours worked, recordable incidents and corresponding root cause analysis (lost time incidents, medical treatment cases), first aid cases, high potential near misses, and remedial and preventive activities required (for example, revised job safety analysis, new or different equipment, skills training, and so forth).

- Environmental incidents and near misses: environmental incidents and high potential near misses and how they have been addressed, what is outstanding, and lessons learned.

- Major works: those undertaken and completed, progress against project schedule, and key work fronts (work areas).

- E&S requirements: noncompliance incidents with permits and national law (legal noncompliance), project commitments, or other E&S requirements.

- E&S inspections and audits: to include date, inspector or auditor name, and records reviewed, major findings, and actions recommended and implemented.

- Workers: number of workers, indication of origin (expatriate, local, nonlocal nationals), gender, age and skill level (unskilled, skilled, supervisory, professional, management).

- Training on E&S issues: including dates, number of trainees, and topics.

- Footprint management: details of any work outside boundaries or major off-site impacts caused by ongoing construction—to include date, location, impacts, and actions taken.

- External stakeholder engagement: highlights, including number of formal and informal meetings, and information disclosure and dissemination—to include a breakdown of women and men consulted and themes coming from various stakeholder groups, including vulnerable groups (e.g., disabled, elderly, children, etc.).

- Details of any security risks: details of risks the contractor may be exposed to while performing its work—the threats may come from third parties external to the project.

- Worker grievances: details including occurrence date, grievance, and date submitted; actions taken and dates; resolution (if any) and date; and follow-up yet to be taken—grievances listed should include those received since the preceding report and those that were unresolved at the time of that report.

- External stakeholder e.g., community grievances: grievance and date submitted, action(s) taken and date(s), resolution (if any) and date, and follow-up yet to be taken—grievances listed should include those received since the preceding report and those that were unresolved at the time of that report. Grievance data should be age and gender-disaggregated.

- Major changes to contractor’s environmental and social practices.

- Deficiency and performance management: actions taken in response to previous notices of deficiency or observations regarding E&S performance and/or plans for actions to be taken—these should continue to be reported until KP determines the issue is resolved satisfactorily.

Table 8-1: Environmental and Social Management and Monitoring Plan

Social Impacts

| Potential Impacts | Recommended Mitigation Measures | Project phase | Responsibility | Monitoring Indicator | Frequency | Estimated Cost (Ksh) |
| --- | --- | --- | --- | --- | --- | --- |
| Local employment | -Prioritize hire of locals for all unskilled labour. -Implement a local recruitment plan that is fair and transparent (including recruitment processes that ensure inclusivity of both men and women, vulnerable individuals, minority clans, ethnic groups and VMGs. -Adhere to labour laws, and labour management practices (timely renumeration, equitable compensation for both genders for equal work etc.) -Create awareness to workers and the community on worker and project grievance redress mechanisms. | Construction Operations Decommissioning | Construction contractor Operations & Maintenance contractor KPLC | -Fair and transparent local recruitment plan in place. -Recruitment processes (job adverts, interviews, selection etc.). -Number of locals employed based on gender, vulnerability, ethnic group, clan etc. -Type of employment (skilled, semi-skilled and unskilled). -Grievances raised, those aggrieved, status of resolution. | Quarterly | Contractor’s cost |
| Local Sourcing | -Source materials from local businesses/communities, and where necessary give opportunities to businesses owned or operated by vulnerable individuals. | Construction Decommissioning |  | -Number and types of businesses sourced from, businesses owned and operated by vulnerable individuals, types and quantities of materials etc. | Quarterly | No additional cost |
| Land acquisition and compensation for land, wayleaves, and potential economic displacements | In line with the RPF provisions; -The contractor will implement and adhere to agreements for temporal use of land and restoration of land after use. -Compensate affected communities in-kind (priority F) for the loss of land. -The construction activities will be restricted to within the allocated land and the immediate surroundings only. -After construction work, any land taken for a temporary basis for storage of material will be restored to their original form. -Consultations with the community on the low voltage lines. | Pre- Construction | Contractor- (contractors’ facilities, workers camps) Proponent- (project land for generation assets and wayleaves and potential economic displacement) | -Land Acquisition and consultation report (consultation (minutes and lists of participants). -Type and amount of compensation paid to affected persons. - Priority community project implemented and handed over to affected communities. -Signed agreements with communities on the use and restoration of their land. | Quarterly | Value of compensation in kind project will be equivalent to the value of land acquired as per NLC |
| Labor Influx and related impacts (SEA/SH, HIV/AIDs and other STIs) | -Tap into the local workforce to the extent possible to reduce labour influx. -Recruit local workforce to the extent possible especially for unskilled and semi-skilled jobs. -Consult with and involve local community in project planning and other phases of the project. -Raise awareness among local community and workers on the need to have a good /cordial working relation -Sensitize workers regarding engagement with local community. -Make provision to provide resources needed by the workers if the need for such resources may result to competition e.g., water. -Establish and operationalize an effective Grievance Redress Mechanism accessible to community members. -The contractor and the project/community grievance redress committee to work closely address complains raised on time. -Include gender considerations in employment opportunities. -Provide appropriate compensation for work done. -Respect for community values/culture. -Prompt payment of workers as per the contractual agreements/terms. | Construction Decommissioning | Proponent, Contractor | -Records of employees/updated employee register. -Number of local community employees and external employees/ updated employee register. | Quarterly | 50,000.00 |
| Child labour | -Employ workers who are 18 years and above, and with a valid national ID at the time of hire. -Implement and monitor the employment register regularly. Compliance with the national labor laws and labour management practices. -Put visible signage on site “No Jobs for children” -Do not allow children at the project site. | Construction Decommissioning | Contractor, Proponent | -Updated employment register indicating locals employed, their ages, national identification numbers etc. -Grievances raised, aggrieved persons and status on resolution etc. | Quarterly | 20,000.00 |
| GBV- SEA and SH | -Prepare an SEA/SH Prevention and Response Action Plan, to manage the SEA/SH risks. -The Action Plan to be proportionate to potential SEA/SH risks, and to include measures such as awareness creation for communities and workers; identification of referral services for survivors and a GRM that ensures confidential reporting of GBV cases. -Implement a code of conduct signed by all those with physical presence on site. | Construction Operations Decommissioning | Construction contractor Operations & Maintenance contractor KPLC | -Minutes of awareness creation sessions for the community and workers on GBV-SEA/SH. -Code of conduct signed by all those with physical presence on site. -GRM that ensures confidentiality of GBV cases in place. Documented referral services for survivors. -Grievances raised, aggrieved persons and status on resolution etc | Quarterly | 50,000.00 |
| Forced Labor | -Adhere to the Employment Act which outlaws any form of forced labour. -Report any form of forced labour at the site. -Ensure that all workers have a national ID card or documentation to show they are adults (above 18 years). | Construction Decommissioning | Contractor Proponent | -Number of reported cases of forced labour. | Quarterly | 20,000.00 |
| Risks related to Inadequate stakeholder engagement | -Prepare a stakeholder engagement/consultation plan (SEP) that is proportionate to the subproject and the identified stakeholders. -Timely and prior disclosure of project all project information, including project instruments, the full rights and entitlements of project affected persons, sub-project positive and negative impacts and opportunities, proposed subproject budget. -In line with the SEP, undertake adequate consultations prior to construction and throughout the project cycle with all segments of the community and other relevant stakeholders. -Prepare and implement a grievance redress mechanism to deal with grievances. -The grievance redress committee to include representatives from the community. -Sensitize stakeholders on SEP and GRM. | Construction Operations Decommissioning | Construction contractor Operations & Maintenance contractor KPLC | -Availability of and implementation of the Stakeholder Engagement Plan. -# of stakeholder consultations held -Record of stakeholder consultations held (minutes of meetings and list of participants). -Information disclosed, to whom it was disclosed (men women, PWD, youth, vulnerable individuals and households etc., methods and languages used in the disclosure (culturally appropriate and accessible), grievances raised and status on resolution etc. -Concerns raised andactons raised. | Quarterly | 30,000.00 |
| Exclusion of VMGs and vulnerable individuals and households | -- In line with the provisions of the ESMF, VMGF and Social Assessment ensure the following. - Early identification and inclusion of VMGs and disadvantaged groups. - Meaningful consultation to effectively participate in the project. - Timely and prior disclosure of relevant project information to VMGs and disadvantaged groups. - Adequate and ongoing consultations with VMGs and disadvantaged groups in line with the SEP. - All concerns or grievances raised are fully resolved in a timely manner. - Access to culturally appropriate project benefits and opportunities. | Pre-construction Construction Operations Decommissioning | Construction contractor Operations & Maintenance contractor KPLC | Minutes of consultative meetings with all community segments including VMGs and vulnerable individuals and households, grievances raised and status on resolution etc. | Quarterly | No additional cost |
| Inaccessibility of project benefits to VMGs and other vulnerable individuals due to affordability challenges | -Consult VMGs and Vulnerable individuals and households on charges for sub project services, and put in place specific interventions to ensure the vulnerable equally access project benefits. | Operations | Operations & Maintenance contractor KPLC | -Interventions to enable those vulnerable access project benefits. -Number of complaints raised by VMGs/vulnerable individuals regarding access to project services. -GRM that is culturally appropriate and accessible. Grievances raised and status on resolution etc | Quarterly | No additional cost |
| Inadequate grievances management | -Constitute a Local Grievances Committee is in consultation with all community segments, and incorporates the existing local dispute resolution mechanism. -Implement a workers grievances mechanism. -Awareness on the culturally appropriate and accessible GRM to all community segments including VMGs, vulnerable individuals and households and CSOs -All reported grievances are logged, dated, processed, resolved and closed out in a timely manner. -Proportionate representation of VMGs and vulnerable individuals in the local grievances committee. -GRM provides for confidential reporting of particularly sensitive social aspects such as GBV, as well as anonymity. | Construction Operations Decommissioning | Contractor Proponent | -Local Grievances Committee in place, composition of committee, awareness of community and workers on project and worker GRMs, updated GRM logs, types of grievances -Availability of grievance redress process -Number of grievances reported -Number of grievances resolved in a timely manner -Number of grievances escalated to national courts and the World Bank Grievances Redress Service and Inspection Panel. | Quarterly | No additional cost |
| Environmental Impacts |  |  |  |  |  |  |
| Vegetation clearance | - Clear only the necessary areas - Ensure proper demarcation and delineation of the project area to be affected by construction works. - Specify locations for vehicles and equipment, and areas of the site which should be kept free of traffic, equipment, and storage. - Designate access routes and parking areas - Re-vegetation including planting of trees around the plant/facility | Construction | Contractor | -Number of trees cleared -Planted trees | Once off | 50,000.00 |
| Soil erosion | - Avoid groundbreaking during the seasons of high rainfall to avoid erosion. - Monitoring of areas of exposed soil during rainy seasons to ensure that any incidents of erosion are quickly controlled. - Construction related impacts like erosion and cut slope destabilizing should be addressed through landscaping and grassing, carting away and proper disposal of construction materials - Use silt traps where necessary - Cover soil stock piles - Landscaping with grass on areas without electrical installation (lower areas) - Monitoring of areas of exposed soil during rainy seasons to ensure that any incidents of erosion are quickly controlled. | Construction | Contractor | Assess size of rills or Gulleys forming from accelerated run off from compacted areas | Quarterly | Part of contractor’s fee |
| Contamination of soil from fossil fuels | - Ensure waste water generated is discharged or drained into approved drainage facilities - Construction vehicles must be maintained in good state and proper servicing to ensure no oils are likely to leak - Care must be exercised not to spill any fossil fuels - Any contaminated soil shall be scooped and disposed-off appropriately. - No servicing vehicles on site | Construction | Contractor | Records of any leakages from construction equipment/ vehicles. | Quarterly | 50,000.00 |
| Dust emissions | - The construction area should be fenced off to reduce dust to the public - Suppress dust during dry periods by use of water sprays; - Stockpiles of excavated soil should be enclosed/covered/watered during dry or windy conditions to reduce dust emissions. - Burning of woody debris & construction waste to be prohibited - Use of personnel protective equipment (PPE) -masks should be provided to all personnel in areas prone to dust emissions - Restrict speed on loose surface roads during dry or dusty conditions - Keep stockpiles and exposed soils compacted and re-vegetate as soon as possible. - Construction trucks moving materials to site, delivering sand and cement to the site should be covered to prevent material dust emissions into the surrounding areas - Plant short trees to break speed of wind | Construction | Contractor | -Visual Observation of dust -Provision of PPEs especially masks | Daily | 100,000.00 |
| Vehicle exhaust and emissions from Generator | - Drivers of construction vehicles must be sensitized so that they do not leave vehicles idling so that exhaust emissions are lowered. - Maintain all machinery and equipment in good working order to ensure minimum emissions of carbon monoxide, NOX, SOX and suspended particulate matter - Maintain equipment in good running condition – no vehicles to be used that generate excessive black smoke - Use of diesel which is Sulphur- free to run the power producing generators to be encouraged - The stack chimney of the generators will be increased from its normal height of 3 meters to 6 meters | Construction | Contractor | -Engine maintenance records - inspection of stacks | Quarterly | 100,000.00 |
| Solid waste generation | - Ensure spoil from excavations is arranged according to the various soil layers. This soil can then be returned during landscaping and then rehabilitation, in the correct order which they were removed that is top soil last; - Segregate waste - Provide litter collection facilities such as bins - Contractor to put in place and comply with a site waste management plan - The contractor should comply with the requirement of OSHA ACT 2007 and Building rules on storage of construction materials - Use of durable, long-lasting materials that will not need to be replaced as often, thereby reducing the amount of waste generated over time - Recovery of materials remains and return to stores - Re-use of materials where possible - Proper budgeting to avoid waste generation - Proper disposal of waste in line with solid waste regulation - Construction wastes to be managed in accordance with construction standards in Kenya | Construction | Contractor | Presence of well-maintained receptacles and centralized collection points | Quarterly | 100,000.00 |
| Impacts on Water Resources and Water Quality | - Clear the necessary areas only. - Appropriate remedial measures shall be implemented by the contractor in the event of erosion. - Infrastructure shall be designed to ensure that contaminated run-off does not reach water source i.e., earth dam. - Contractor to develop an oil-spill containment plan as part of the emergency response plan. In the event of an oil spill the procedures contained in the emergency response plan of the contractor will come into effect. - No vehicle maintenance and service shall be done at project site - Ensure that potential sources of petro-chemical pollution are handled in such a way to reduce chances of spills and leaks. | Construction | Contractor | -Oil spill containment plan. -Provision of fuel/oil drip and spill trays | Quarterly | 150,000 |
| Noise & vibration | - Construction activities to avoid any unchanneled flow of water at the site - Storage areas that contain hazardous substances should be bunded with an approved impermeable liner and provision for a pit to be made in case of oil spill. - The excavation and use of rubbish pits during construction should be strictly prohibited. - A waste disposal area should be designated within the active construction area and this should be equipped with suitable containers i.e., skips or bins of sufficient capacity and designed to contain and prevent refuse from being blown by wind, - Areas contaminated by spilled concrete and/or fuels and oils leaking from vehicles and machinery should be cleaned immediately | Construction | Contractor | Noise levels-Records of noise measurements done by contractor within the project area and at distances of 30m from the Solar mini-grid | Quarterly | 150,000.00 |
| Impacts from Hazardous materials - | - Maintenance of construction vehicles will not be done on site - All hazardous products and waste should be labeled and handled properly to avoid contact with the ground - Dispose hazardous waste through a NEMA approved waste handler | Construction | Contractor | Presence of well-maintained receptacles and centralized collection points | Quarterly | 100,000.00 |
| Accidental Oil Spills or Leaks | - In the event of accidental leaks, contaminated top soil should be scooped and disposed of appropriately. - Refueling and maintenance of vehicles will not take place at the construction site. - Create awareness for the employees on site on procedures of dealing with spills and leaks - Vehicles and equipment must be serviced regularly and kept in good state to avoid leaks. - In case of spillage the contractor should isolate the source of oil spill and contain the spillage using sandbags, sawdust, absorbent materials and/or other materials approved by materials. - All chemicals should be stored within the bunded areas and clearly labeled detailing the nature and quantity of chemicals within individual containers. | Construction | Contractor | Records of all accidental spills and number of liters | Quarterly | 150,000.00 |
| Fire Hazards | - Create awareness to the construction workers on potential fire hazards - Provision of firefighting equipment on site during construction. - No smoking shall be done on construction site - ‘No smoking’ signs shall be posted at the construction site - A fire risk assessment and evacuation plan should be prepared and must be posted in various points of the construction site including procedures to take when a fire is reported. - Designate an assembly point | Construction | Contractor | -Records of any Fire incidences -Fire equipment and evacuation plan | Quarterly | 100,000.00 |
| Impacts of construction material sourcing (e.g., quarrying) | - Source all building materials such as stone, sand, ballast and hard core from NEMA approved sites. - Ensure accurate budgeting and estimation of actual construction materials to avoid wastage. - Reuse of construction materials where possible. | Construction | Contractor | Sources of raw materials (from local community) | Quarterly | Part of contractor’s cost |
| Increased water demand | - Prudent use of available water - Consultations with the project local committee on use of water in the community to avoid conflicts with the community - Source and utilize a sustainable and reliable water supply for both construction and operation phase. | Construction | Contractor | Water usage records | Quarterly | Part of contractor’s cost |
| Energy Consumption | - Ensure responsible electricity use at the construction site through sensitization of staff to conserve electricity by switching off electrical equipment or appliances when they are not being used. - Proper planning of transportation of materials will ensure that fossil fuels (diesel, petrol) are not consumed in excessive amounts. - Complementary to these measures, they monitor energy use during construction and set targets for reduction of energy use. | Construction | Contractor | Energy consumption records | Quarterly | No additional cost |
| Occupational Health and safety Impacts | - Use skilled personnel for activities which demand skills/technical tasks - Awareness creation/Tool box talks on safety to workers while at construction site - Workers coming to the site should be knowledgeable on safety precautions to take - Appropriate PPE (helmet, safety harness, boots, masks, climbing irons) - Proper general house keeping - Close supervision of workers - Risk assessment by contractor of the construction activities and implement mitigation measures appropriately - Adherence to occupational Safety and Health Act 2007 - Availability of equipped first aid box on site - Provide safe drinking water for workers - Engagement of trained first aider on site - Ensure the WIBA cover is taken for the staff - Establish safety committees | Construction | Contractor | Records of any near misses, incident, and accidents. Records of corrective actions implemented if there was an accident. | Quarterly | 1,000,000.00 |
| Community safety –access | - Proper barricading - Hazard communication. - Controlled access to the site by designated personnel - Maintain records of any person who comes to site | Construction | Contractor | Presence of a controlled access and records of every person accessing the site | Daily | 20,000.00 |
| Public Health Impacts | - Sensitize workers and the community on prevention and mitigation of HIV/AIDS and other sexually transmitted diseases, through staff training, awareness campaigns and community Barazas. - Awareness creation and consultations with local communities prior and during construction on the dangers of these diseases - Informing workers on local cultural values and health matters. - Provision of condoms to workers - Allowing migrant workers time to be with their families - The contractor is impressed upon not to set a construction camp on site. - The contractor will provide public education/information about HIV/AIDS transmission and prevention measures. - Ensure equal treatment of workers - Provide all appropriate COVID-19 preventive measures including campaign to maintain individual measures at the workplace. | Construction | Contractor | Number of awareness creation sessions conducted. -Availability of and distribution of condoms | Quarterly | 20,000.00 |
| Sanitary waste | - Construct/ install pit latrines for both genders clearly labelled | Construction | Contractor | Presence of separate and clean washrooms for both the gents and ladies | Quarterly | 300,000.00 |
| Solid Waste Generation | - Provide waste handling facilities such as labeled waste bins - Emphasis on prudent waste generation and give priority to reduction at source - Solid waste management awareness to operators - Operator to contract a NEMA licensed waste handler to collect and dispose solid waste | Operation | Contractor | Presence of well-maintained receptacles and centralized collection points | Quarterly | 50,000.00 |
| Liquid Waste/Oils Generation | - Proper storage of the oil is required to ensure no leakages - Frequent inspection and maintenance of the generator to minimize leakages. - No vehicles should be serviced or maintained at the Mini-grid area. - The waste oil or used oil must be disposed-off appropriately. - Proper training for the handling and use of fuels for the operators of the Mini-grid. - In the event of accidental leaks, contaminated top soil should be scooped and disposed of appropriately. | Operations | Operations & Maintenance contractor KPLC | -Engine maintenance records -Oil spill containment plan | Quarterly | 200,000.00 |
| Increased oil Consumption | - Efficient energy consumption - Install an energy-efficient lighting system | Operations | Operations & Maintenance contractor KPLC | Energy consumption records | Quarterly | No additional cost |
| Increased storm water flow | - Construct the drainage system in a way to follow natural drain of the water - Concrete only the required area and leave the rest of the land with vegetation like grass - Construct rain water harvesting system on the control buildings/office and harness into storage tanks for use | Operations | Operations & Maintenance contractor KPLC | Provision of a drainage system and a rain water harvesting system | Quarterly inspections | 200,000.00 |
| Fire Outbreaks | - The power plant must contain firefighting equipment (Portable fire extinguishers) of recommended standards and in key strategic points - Detection/alarm systems that can detect fire should be and installed - A fire evacuation plan should be prepared and posted at strategic points and should include procedures to take when a fire is reported. - Workers especially operators of the plant must be trained on fire management - ‘No smoking’ signs shall be posted within the Mini-grid area - A fire Assembly point should be identified and marked | Operations | Operations & Maintenance contractor KPLC | -Provision of serviced fire equipment, evacuation plan and safety signages -Records of fire safety training | Quarterly | 50,000.00 |
| Visual Impacts | - Fence round the solar Mini-grid to keep off/screen the solar panels. | Operations | Operations & Maintenance contractor KPLC | Presence of a perimeter fence | Quarterly inspections | No additional cost |
| Water demand | - Ensure prudent use of water. - Install water-conserving automatic taps. - Any water leaks through damaged pipes and faulty taps should be fixed promptly. | Operations | Operations & Maintenance contractor KPLC | Water usage records | Quarterly | 20,000.00 |
| Sanitary waste | - Provide sanitary waste facilities for both genders clearly marked - Disposal of waste through septic tanks | Operations | Operations & Maintenance contractor KPLC | Presence of separate and clean washrooms for both the gents and ladies | Quarterly | No additional cost |
| Flooding | - Ensure drainage channels are free of any obstruction at all times i.e., not blocked - Construct more channels and or expand existing ones - Raise foundations of the solar panels and ensure a proper and from concrete base - Create flooding diversions and or spill ways to divert water from getting into the solar power facility | Operations | Operations & Maintenance contractor KPLC | -Provision of drainage system -Raised foundations for the structures | Quarterly | 100,000.00 |
| Occupation health and Safety | - Ensure only qualified staff are employed to work in the facility - All workers operating the Mini-grid must be equipped with appropriate and adequate person protective equipment (PPE) such as; safety footwear, helmet among others. - Operators must be skilled on firefighting management - Annual environmental audits should be done - WIBA cover for staff is mandatory | Operations | Operations & Maintenance contractor KPLC | -Provision of PPEs and WIBA cover -Environmental audit reports | Quarterly | 100,000.00 |
| Hazardous waste-damaged panels | - Segregation from other waste streams - Proper disposal through a NEMA approved/licensed handler | Operations | Operations & Maintenance contractor KPLC | Presence of well-maintained receptacles and centralized collection | Quarterly | 200,000.00 |
| Noise and Vibration | - Generator room should be sound proof to ensure no noise of a nuisance level will be produced. - Monitor noise levels | Operations | Operations & Maintenance contractor KPLC | Noise levels-Records of noise measurements done by contractor within the project area and at distances of 30m from the Solar mini-grid | Quarterly | Part of contractor’s cost |
| Shocks and electrocutions | - Inspect the wiring of the houses before connecting power - Safety awareness campaigns to the community before connection of power on safety precautions such as: - Require community to engage a certified technician to do wiring in the premises - Use of quality materials while wiring - Refraining from individual illegal extensions of power lines to other houses - Observing safety measures while using electricity such as not touching sockets and switches with wet hands or wiping with wet cloths - Keeping off all electricity infrastructure e.g., not tying livestock on electric poles, no cutting earth wires that run along some electric poles, not interfering with sockets or switches - Reporting any electric wire/conductors if found fallen on the ground - Report any incident regarding electricity at the local office –staff in charge of operating the Mini-grid | Operations | Operations & Maintenance contractor KPLC | -Records of awareness sessions conducted -Incidences report | Quarterly | No additional cost |
| Community Safety- Access to site by general public | - Fencing off the facility to keep of community members, children and livestock from entering into the facility - Controlled access to the site only with prior approval - Maintain records of any person who comes to site | Operations | Operations & Maintenance contractor KPLC | Presence of a controlled access and records of every person accessing the site | Daily | Part of contractor’s cost |
| Risks related to poor or inadequate stakeholder engagement (Conflict) | - Employ from the community to the extent possible - Engage the community members and other stakeholders in a timely manner - Work closely with the GRM committee members in solving the conflicts - Solve all conflicts/grievances at the earliest time possible - Ensure all grievances are logged and closed - Monitoring the pattern of grievances to come up will long term measures | Operations | Operations & Maintenance contractor KPLC | Grievance records | Quarterly | 20,000.00 |
| Gender Based Violence –SEA and SH | To manage GBV risks, the contractor will prepare a SEA/SH Prevention and Response Action Plan that will include a GRM that ensures confidentiality. The plan will include the necessary measures for prevention and response and must ensure survivor-based approach | Operations | Operations & Maintenance contractor KPLC | -SEA/SH Prevention and Response Action Plan -Grievance records | Quarterly | 20,000.00 |
| Public Health Impacts –HIV/AIDs | - Sensitize workers and the community on prevention and mitigation of HIV/AIDS and other sexually transmitted diseases, through staff awareness and awareness campaigns for the community - Provision of condoms to workers - Allowing migrant workers time to be with their families | Operations | Operations & Maintenance contractor KPLC | Number of awareness creation sessions conducted. -Availability of and distribution of condoms |  | 20,000.00 |
| Public health Impacts -Covid 19 disease | - Social distance must be observed - Provision of hand wash facilities before access - Temperature check and monitoring of the temperature of workers and any other person coming to site - Enforce wearing of masks - Make provision for testing and treating especially of workers - Provision of contact numbers for the nearest health facility for testing and treatment - Adhering to any other measures from the ministry of health which may be issued from time to time | Operations | Operations & Maintenance contractor KPLC | Availability of hand washing facilities Utilization of hand washing facilities Number of Covid-19 cases reported | Quarterly | 30,000.00 |
| Dust Emission | - Trees can be planted around the plant/facility provided they do not cast shadows to the solar panels to act as wind breakers and hence decrease dust pollution - Ensure planting of grass around and within the facility compound | Operations | Operations & Maintenance contractor KPLC | Visual inspection | Quarterly | 50,000.00 |
| Vehicle Exhaust Emissions | - Drivers of the vehicles must be sensitized so that they do not leave vehicles idling so that exhaust emissions are lowered. - Company vehicles should be well maintained | Operations | Operations & Maintenance contractor KPLC | Engine maintenance records | Quarterly | No additional cost |
| Noise and Vibration | - Install portable barriers to shield compressors and other small stationary equipment where necessary. - Use quiet equipment (i.e., equipment designed with noise control elements). - Co-ordinate with relevant agencies in case the noise produced will require a license. - Limit pickup trucks and other small equipment to a minimum idling time and observe a common-sense approach to vehicle use and encourage workers to shut off vehicle engines whenever possible. - Demolish mainly during the day when most of the neighbors are out working. | Decommissioning | Contractor | Noise levels-Records of noise measurements done by contractor within the project area and at distances of 30m from the Solar mini-grid | Once off | 20,000.00 |
| Solid Waste Generation | - Demolition contractor to adhere to the various manufacturer’s guidelines and requirements regarding demolition and disposal - Segregation of waste in order to separate hazardous waste from nonhazardous waste and other streams of waste - Provision of facilities for proper handling and storage of demolition materials to reduce the amount of waste caused by damage or exposure to the elements - Adequate collection and storage of waste on site - Safe transportation to the disposal sites / designated area - Hazardous waste must be disposed by NEMA approved waste handler | Decommissioning | Contractor | Presence of well-maintained receptacles and centralized collection points | Daily | 700,000.00 |
| Dust Emissions | - Cover all trucks hauling soil, sand and other loose materials or require all trucks to maintain at least two feet of freeboard | Decommissioning | Contractor | Visual inspection | Daily | 20,000.00 |
| Public Health- HIV/AIDS | The project will sensitize workers and the surrounding communities on prevention and mitigation of HIV/AIDS and other sexually transmitted diseases, through staff training and awareness campaigns/ to the community. | Decommissioning | Contractor | Records of awareness creation sessions conducted. -Availability of and distribution of condoms | Once off | 20,000.00 |
|  | Total |  |  |  |  | 4,380,000.00 |

  - Approach to Environmental Impact Management

The proposed ESMMP will be the responsibility of the proponent/ KP and the contractor as outlined. This section presents the range of approaches that will be used to manage potential impacts of the proposed project.

## Management Plan during Construction Phase

The contractor will prepare targeted management plans to deal with specific environmental and social aspects guided by the ESMMP and any other emerging issues on the ground. The contractor shall prepare these plans and have them approved by both the proponent and the Bank before they mobilize to the site:

- Construction management plan

- Rehabilitation and site closure plan

- Local recruitment plan

- Workplace health and safety plan

- Community safety plan

- Emergency management and response plan

- SEA/SH Prevention and Response plan

- Stakeholder Engagement management plan

- Grievance Redress mechanism

- Labor influx management plan

### Construction Management Plan

The construction management plan for the proposed project shall include the following:

- Management of Fuels and other Hazardous Materials

- The Contractor shall comply with all applicable laws, regulations, permit and approval conditions and requirements relevant to the storage, use, and proper disposal of hazardous materials.

- Management of the Construction Site

- The contractor shall prevent littering and the random discard of any solid waste on or around the construction site

- The contractor shall manage other solid and liquid waste

- Fire Prevention and Management

- The Contractor shall take all necessary precautions to prevent fires caused either deliberately or accidentally during construction process.

- The Contractor shall prepare a fire prevention and fire emergency plan as a part of the plans to be submitted to KP.

- Management of Air Quality

- The Contractor shall institute appropriate measures to minimize or avoid air quality impacts. This can be achieved through formulation of air quality management plan.

- Neighboring Landowner and Occupier Relations

- The Contractor shall respect the property and rights of neighboring landowners and occupiers at all times and shall treat all persons with deliberate courtesy.

- The contractor shall respect any special agreements between the KP and the neighbours e.g., the wayleaves agreements signed between Kenya power and landowners will need to be respected by the contractors.

- Complaints Register

The contractor shall establish and maintain a register for periodic review by the KP  that logs all the complaints raised by the neighbours or the general public about construction activities. The register shall be regularly updated, and records maintained including the name of the complainant, his/her domicile and contact details, the nature of the complaint and any action taken to rectify the problem.

- Construction Control

The construction control for the proposed project shall cover the following:

Control of Access

The contractor shall ensure that the construction site is accessed by authorized persons only and up-to-date records kept

i) Control of material supply and burrow areas

- The contractor shall, as far as possible, source all material needed to construct the proposed project from the licensed quarries

- In instances where materials are to be obtained from a new burrow area; the contractor shall comply with relevant legislations.

- The contractor shall prepare a method statement including plans, detailing the expected quantity of excavation, temporary and permanent drainage control, the final contouring of the burrow pit and the proposed method of rehabilitation.

### Rehabilitation and Site Closure Plan

- After completion of construction activities, the contractor shall clear the site of construction materials and dispose wastes in appropriate disposal sites.

- The contractor shall remove all temporary works on the construction site and grow grass on areas that are not covered by the installations to control erosion

### Local Recruitment Plan

The contractor will prepare a local recruitment plan to guide on recruitment of locals. The plan shall pay attention or adhere to Employment Act.

In designing the local recruitment plan contractor shall:

- Comply with the provisions of Employment Act, 2007

- Wherever possible, give priority to qualified local people when hiring employees.

The mitigation measure is:

- Prepare a local recruitment strategy that is fair and transparent to ensure all community segments - men, women, vulnerable individuals, minority clans, and VMGs who meet OP 4.10 criteria) - can access subproject benefits during construction and that prioritizes hire of locals for skilled, semi-skilled and unskilled labour.

### Workplace Health and Safety Plan

The workplace health and safety plan to be implemented by the contractor and KP shall include the following key measures:

- The contractor shall comply with all relevant legislative requirements governing worker health and safety at the work place (e.g., OSHA 2007 and its subsidiary legislations).

- The contractor shall prepare and implement measures to minimize diseases likely to be contracted by the construction workers as a result of the proposed project such as HIV &AIDs and other communicable diseases

- The contractor shall have obligations of managing the safety of its employees by;

  - Provision of appropriate PPEs to employee

  - Training employees on competence

  - Employing competence and qualified staff

  - Provision of First Aid Kits onsite

  - Should have a trained first aider

  - Document and create awareness on safe work procedures and work instruction

- The contractor will manage accidents by having an emergence response plan which will include contacts for emergency service providers e.g., ambulances, fire brigade and nearest hospitals

- Health and safety performance will be continuously monitored, and procedures reviewed with the aim of eliminating risk as far as reasonably practicable.

### Community Health and Safety Plan

The community health and safety plan to be implemented by the contractor shall include:

- Adherence to OSHA 2007 Act and its subsidiary legislations to ensure that health and safety of immediate neighbors and the public is not threatened.

- The contractor to ensure that construction work is undertaken in manner not likely pose risks to community health and safety.

- The contractor shall undertake an independent risk assessment prior to construction. The findings of this assessment will inform the development of a community safety plan and create awareness to the community on the same

### Emergency Preparedness Plan

The Contractor shall develop an emergency plan that will enable rapid and effective response to all types of environmental emergencies in accordance with recognized national and international standards.

The emergency plan shall include establishment of a network of communication between the Contractor and emergency services including police, ambulance services, and fire brigades among others.

### SEA/SH Prevention and Response Action Plan

The contractor will prepare a SEA/SH Prevention and Response Action Plan that will include a GRM that ensures confidentiality. The plan should have an Accountability and Response Framework. The plan will include the necessary measures for prevention and response of GBV impacts.

The mitigation measures shall include:

- Ensure that local employment opportunities are equitably accessible to all segments of the community,

- Ensure equal pay for equal work

- Prepare and implement GBV (SEA/SH management) plan that includes sensitisation of community members and subproject workers on the potential of the subproject giving rise to, exacerbating and/or mitigating SEA and SH, and the appropriate mitigation measures

- Map all GBV service providers and document referral services for survivors, and, sensitize community members and subproject workers on the referral pathways.

- Prepare and implementing a functional and accessible contractor GBV GRM for use by workers and community members (as appropriate).

- The GBV GRM should allow for anonymous incident reporting and should be GBV survivor-centric

- Sensitize community members and workers on contractor GRMs

- Prepare and sensitise Code of Conduct (CoC) for SEA and SH, and their responsibilities for the same, to demystify the stigma associated with SEA and SH

### Stakeholder Engagement Management Plan

A Stakeholder Engagement Plan is a formal approach to communicate with project stakeholders to achieve their support for the project. The plan prepared shall specifies the frequency and type of communications, media, contact persons, and locations of communication events. The SEP is a useful tool for managing communications between the contractor and other stakeholder. The plan should meet the following objective of a SEP.

- To help improve project design and implementation

- To inform third parties about changes that affect them

- To take their views into account in the implementation of projects

- To identify adverse impacts and mechanisms to enhance project benefits

- To identify risks from and to a project

- To increase project ownership and sustainability

- To comply with Bank policies that require consultations

The plan shall put this measure in to consideration:

- In consultation with the identified stakeholders, prepare a stakeholder engagement plan (SEP) that is based on their locations (maps) and their information needs at the various subproject phases

## Grievance Mechanism

One of the key roles of the Grievance Redress Committees, is to address disputes led by the administrative chiefs. All PAPs will be informed how to register grievances or complaints, including specific concerns about land and environment. The PAPs will be informed about the dispute resolution process, specifically about how the disputes will be resolved in an impartial and timely manner. The Land Acquisition Tribunal will provide opportunity for appeal when a solution will not be found using the established local mechanisms. The court will deal with land related disputes. The Environmental and Land Court provides for opportunity for appeals for decisions made under the Land Acquisition Tribunal. However, the Land Act 2012 and Environment and Land Court Act 2011 advocates for Alternative Dispute Resolution (ADR) methods in tackling land related disputes. Alternative dispute resolution approaches will be given preference and based on customary rules, arbitration, or third-party mediation. ADR will be promoted or defended as a resolution to disputes related to land.

## Grievance Redress Mechanism

### Introduction

Grievance mechanisms should receive and facilitate resolution of the affected institutional or communities’ concerns and grievances. Community concerns should be addressed promptly using an understandable and transparent process that is culturally appropriate and readily acceptable to all segments of affected communities, at no cost and without retribution. Mechanisms should be appropriate to the scale of impacts and risks presented by a project. Grievances can be an indication of growing stakeholder concerns (real and perceived) and can escalate if not identified and resolved. The management of grievances is therefore a vital component of stakeholder management and an important aspect of risk management for a project. Projects may have a range of potential adverse impacts to people and the environment in general, identifying grievances and ensuring timely resolution is therefore very necessary. As such the project has developed a grievance management process to serve as a guide during project implementation.

The constitution of Kenya section 159, Land and Environmental Court Act 2011, National Land Commission Act 2012, and Land Act 2012 advocates for alternative dispute resolution mechanisms before seeking formal legal redress in disputes relating to environment, land, and resettlement. In practice this can be the village head and other local or traditional dispute resolution mechanisms.

The Land Act 2012 and National Land Commission Act 2012 obligate the NLC to support grievances and disputes related to resettlement or land amicably in conjunction with the implementing agencies-KPC/REREC. KPC/REREC will be expected to put in place mechanisms and structures that arbitrate or negotiate with PAPs whenever there are any grievances concerning land or environment.

### National GRC

It will comprise of KOSAP Project Implementation Unit at the Ministry of Energy and the implementing agencies. Matters that could not be resolved at the county level will be escalated to this National GRC by the CEC.

### Arbitration or legal redress in a court of law (the Environment and Land Court) and the Land Acquisition Tribunal

Its the last level of the GRM for the community or project affected persons and it will only be approached once all the three levels have been exhausted. Members of the project/ grievance redress committee will be chosen by the community members themselves. The committee chosen will be in charge of giving project information to the community and be a focal point for reporting project related issues of concern or grievances.

### World Bank Grievance Redress Service (GRS)

The GRS will ensure that complaints received are promptly reviewed in order to address project-related concerns. Project affected communities and individuals may submit their complaint to the WB’s independent Inspection Panel which determines whether harm occurred, or could occur, as a result of WB non-compliance with its policies and procedures. Complaints may be submitted at any time after concerns have been brought directly to the World Bank's attention, and Bank Management has been given an opportunity to respond.

### National Grievances Redress Committee (NGRC)

NGRC has been established at the National level to ensure participatory and transparent implementation of the project. The NGRC will help the project carry out its mandate efficiently- particularly ensuring effective and amicable settling of disputes among the communities/PAP’s.

Members to NGRC include representation from the following agencies and entities

- Representative from the Ministry, chair of the Committee

- Representative from NLC to handle matters that involve land take

- Representative of the Implementing Agencies (IA)-KPC and REREC

- Representative from the Ministry’s Legal office to guide on Alternative Dispute Resolution methods

- Representative from the County Grievance Redress Committee-depending on the matter at hand; Land or Environment

- Representative from Gender and Social Development Office who will be responsible for ensuring gender issues are well addressed.

- Representative from NEMA to handle environmental issues

- County Surveyor/Physical planner from the county Lands office

- Project Affected Person’s-to represent the matter before the committee

Functions of the National Grievances Redress Committee

- Ensuring effective flow of information between PAPs, the implementing agency and the County Grievance Redress committee on matters brought before the committee

- Co-ordinate County Grievance Redress Committees (LGRC)

- Co-ordinate activities between the various organizations involved; facilitate grievance and conflict resolution at the highest level

- Resolving disputes that may arise within the project. If it is unable to resolve any such problems, the PAP’s can seek legal redress.

### County Grievance Redress Committees (CGRC)

CGRC has been established at the county level to ensure participatory and transparent implementation of the project. The CGRC will help the project carry out its mandate efficiently- particularly ensuring effective communication with the communities.

Members to CGRC will include representation from the following agencies and entities

- Representative of NLC, to grant legitimacy to the acquisition process and ensure that legal procedures as outlined in Land Act 2012

- Representative of the implementing agency

- Representative of NEMA to handle environmental issues

- The County Administration representative, which will provide the much-needed community mobilization, and support to the sub-project.

- County Land Survey Officer will survey all affected land and produce maps.

- The County Gender and Social Development Officer who will be responsible for ensuring gender programs are adhered to.

- The County Lands Registrar will verify all affected land and validate the same.

- Two PAP representatives from Location Grievance Resettlement Committee – act as voice for the PAPs

- NGOs and CBOs locally active in relevant fields

The CGRC will have the following specific responsibilities:

- Ensuring effective flow of information between PAPs and the implementing agency

- Coordinate Locational Grievance Redress Committees (LGRC)

- Coordinate activities between the various organizations involved; facilitate grievance and conflict resolution; and provide support and assistance to vulnerable groups.

- Conducting extensive public awareness and consultations with the affected people so that they can air their concerns, interests, and grievances.

- Resolving disputes that may arise within the project. If it is unable to resolve any such problems, channel it to the National Grievance Redress committee before utilizing the appropriate formal grievance procedures.

### Locational Grievance Redress Committee (LGRC)

Since counties are large, further decentralized Grievance Redress Committee for Mkokoni has been established and will handle the grievances arising from Mkokoni solar off grid project.

At the time of assessment, it was noted that the committee was constituted in July 2021 during the land acquisition forum. The membership of LGRCs were elected from each category of PAPs except the locational Chief and assistant chiefs who will be automatic members of the team by virtue of their positions.

The implementing agency representatives present during this forum included MOEP, KPC and REREC (County Renewable Energy Officer). They held a consultative forum with the community and constituted an LGRC consisting of nine (9) members. The members consisted of three (3) ladies, four (4) men and two (2) youth all identified and elected from each category of PAP except for the location Chief and village administrator who are automatic members of the team.

It was however identified that the LGRC was yet to elect their chairperson and secretary and also yet to formulate a leadership structure among themselves.

The LGRCs will work under guidance and coordination of CGRC and the implementing agencies. Their membership comprises of the following:

- The locational Chief, who is the Government administrative representative at the locational unit and who deals with community disputes will represent the Government in LGRC

- Assistant Chief, who supports the locational Chief and Government in managing local community disputes in village units will form membership of the team.

- Female PAP, elected by women PAPs, will represent women and children related issues regarding the project

- Youth representative, elected by youths, represents youth related concerns in the LGRCs

- Male representatives elected by the members of the PAPs

- Vulnerable persons representative will deal and represent vulnerable persons issues in the LGRCs.

- CBO representatives

The committee representatives present during the public consultation forum informed that they were yet to have an initial meeting and equally the members were yet to be informed of their specific roles on the project.

The LGRC will be assigned specific roles for the projects. The anticipated roles will include the following;

The roles of LRCCs will include among others:

- Conducting extensive public awareness and consultations with the affected people.

- Help ensure that local concerns raised by PAPs as regards to the project are promptly addressed by relevant authorities.

- Resolve manageable disputes that may arise relating to the project. If it is unable to resolve/help refer such grievances to the CGRCs instituted.

- Ensure that the concerns of vulnerable persons such as the disabled, widowed women, orphaned children affected by the sub project are addressed.

- Assist the community in recording grievances, including helping those who cannot write or read.

- Help the vulnerable groups access project benefits

- Ensure that all the PAPs in their locality are informed about the project

Arbitration

National Grievance Redress Committee

County Grievance Redress Committee (CWG’s)

Locational Grievance Redress Committee

Community Liaison Officer (Contractor) & County Renewable Energy Officer (CREO)

Arbitration

National Grievance Redress Committee

County Grievance Redress Committee (CWG’s)

Locational Grievance Redress Committee

Community Liaison Officer (Contractor) & County Renewable Energy Officer (CREO)

Figure 8. KOSAP Grievance Redress Mechanism

Figure 8. KOSAP Grievance Redress Mechanism

It should be noted that if complainants are not satisfied with the grievance process, even after arbitration they have the right to present their complaint through the court system.

It is expected that most disputes will be resolved at the lowest level-Locational Grievance Redress Committee in coordination with existing GRM.

A record of any/all grievances received and handled should be kept at all phases of the implementation process.

### Disclosure

All the grievance redress mechanisms available to the sub-project will be disclosed to all affected persons and other stakeholders. The disclosure will include information on the reporting mechanisms, including telephone numbers, email addresses, postal addresses, and contact persons (where applicable), etc.

## World Bank Grievances Redress Mechanism

The World Bank has established 2 grievance redress mechanisms that provide avenues for individuals and communities to submit complaints directly if there is belief that they have been, or are likely to be, adversely affected by a World Bank-funded project.  In this project PAPs and other stakeholders have the right to know and access at no cost these GRMs as described below.

World Bank Grievances Redress Service

The Grievance Redress Service (GRS) is an avenue for individuals and communities to submit complaints directly to the World Bank if they believe that a World Bank-supported project has or is likely to have adverse effects on them, their community, or their environment.  The GRS enhances the World Bank’s responsiveness and accountability to project-affected communities by ensuring that grievances are promptly reviewed and addressed.  Complaints must be in writing and addressed to the GRS and sent through the following methods namely:

Those aggrieved or their representatives can report their complaints through the following mediums; (i) Online by accessing the online form; (ii) Sending an Email to grievance@worldbank.org; or (iii) Submitting a letter to the World Bank Headquarters in Washington D.C., United States or World Bank Kenya County Office.

World Bank Inspection Panel

The Inspection Panel is an independent complaints mechanism for people and communities who believe that they have been, or are likely to be, adversely affected by a World Bank-funded project.  The Panel is an impartial fact-finding body, independent from the World Bank management and staff, reporting directly to the Board.  The Inspection Panel process aims to promote accountability at the World Bank, give affected people a greater voice in activities supported by the World Bank that affect their rights and interests, and foster redress when warranted.  In September 2020, the Board updated the resolution that created the Panel and added to the Panel functions.  At the same time, the Board approved a resolution establishing the World Bank Accountability Mechanism (AM).  The new AM began operations in early 2021 and houses the Panel to carry out compliance reviews and a new Dispute Resolution Service (DRS), which will give complainants another way to have their concerns addressed.  Contacts for registration of complaints to the IP are; (i) Tel: +1 202 458 5200: and (ii) Email: ipanel@worldbank.org.

Government Management of Land Acquisition Disputes

The Environment and Land Court, established under the Environment and Land Court Act 2011, is a superior court (with offices across the country) that hears and determines disputes relating to land and the environment.  Likewise, the Land Acquisition Tribunal established under the Land Act 2012; (PART VIIIA 133A) has jurisdiction to hear and determine appeals from the decision of the NLC on the process of compulsory acquisition of land. Therefore, in the first instance, such appeals are referred to the Tribunal. However, a party dissatisfied with the decision of the Tribunal may appeal to the Environment and Land Court on a question of law only. The regulations to set the Land Acquisition Tribunal established under the Land Value (Amendment) Act of 2019 are underway. Besides, the Judicial Service Commission will chair the Land Acquisition Tribunal once operational.

### Labor Influx Management Plan

The purpose of this plan is to provide a clear set of actions and responsibilities for the control of impacts linked to in-migration within the Project’s area of influence. This plan will be regularly reviewed and updated to reflect revised Project design, socio-economic changes and learning experienced during its implementation.

The objectives of this plan are as follows:

- Monitor the scale of project induced in-migration into the project area and specific in-migration ‘hotspots’;

- Support local government and communities to manage both internal and external immigration into the project area; and

- Mitigate and manage any negative impacts and enhance and promote any positive impact related to labor influx.

The plan shall consider these measures:

- Prepare and Implement a Labour Management Plan (LMP) with policies and measures for ensuring that:

- Subproject managers and workers are sensitised on:

  - County/National Labour laws

  - County/National Child Labour laws

  - National/International Forced Labour laws

- Enforce:

  - The Code of conduct

  - County/National Labour laws

  - County/National Child Labour laws

  - National/International Forced Labour laws

### Rehabilitation and Decommissioning Management Plan

The rehabilitation and decommissioning management plan include the following:

#### Planning for Closure

a) The implementing agency shall investigate practical options for closure of the facility at least one year before decommissioning and submit a report to relevant authorities NEMA included.

b) KP shall develop rehabilitation and decommissioning plan in conjunction with relevant stakeholders at least one year before the end of facility’s operations.

c) KP shall explore options of re-use and recycling of the facility’s components/structures.

#### Decommissioning

a) The KP shall take into consideration the health and safety of personnel, contractors, neighbours and the public during the planning and implementation of the demolition process.

b) The KP shall undertake a further survey to identify any contaminated areas and remediate them accordingly.

#### Post Closure

The KP shall ensure that the facility’s site is free of impacts associated with the closure and demolition

The KP shall develop, rollout and implement a monitoring plan that includes:

a) Monitoring of the rehabilitated site to confirm whether progress is satisfactory.

b) Outline of how land improvement and future land use will be affected by the past operations and decommissioning of the associated infrastructure.

## Institutional Implementation Arrangements for the Proposed Project

This section presents roles and responsibilities of proponent, implementing agency, supervision consultant and contractor. The project is jointly implemented by the Ministry of Energy and Kenya Power. Specific roles are presented below;

### Proponent -Ministry of Energy and Petroleum (MoEP)

The MoEP will provide overall coordination and oversight of the project. MOE will be responsible for overall responsibility for safeguards due diligence, and compliance monitoring. The MOE will also provide funding for the project planning and implementation.

### KOSAP Project Implementation Unit

The MOE has already put in place a Project Implementation Unit (PIU) to guide implementation of the project. The PIU is already implementing the project. In the PIU Environmental and Social issues are spearheaded by an Environmental and Social Safeguards Expert whose role is to coordinate and oversee implementation of safeguards. The PIU reports to the MOE.

### The Implementing Agency (KP)

KP will be responsible for implementation and operation of the project on behalf of the MOE. Some of the key responsibilities include but not limited to are;

- KP will supervise construction works through a supervision consultant and also directly

- Monitoring the progress of the project in terms of the safeguards and technical aspects.

- Monitoring of the ESMMP implementation

- Ensuring the project is on course in terms of timelines

Note: The Solar Mini-grid will be installed operated and maintained by the contractor for the first ten (10) years and then handed over to REREC engineers and operators. So, for the ten years REREC will be monitoring the operations of the contractor.

### County Government of Lamu

The County government is a key stakeholder. The roles of the county government include giving relevant approvals needed, assisting is process of allocating land for Mini-grid, solving grievances that cannot be sorted at project level, monitoring progress of the project among others.

### National Environmental Management Authority

This authority is responsible for approval of ESIA report and licensing and is free to check progress of implementation of ESMMP

### Roles and Responsibilities of the Supervising Consultant

- The consultant must appoint an ESHS officer who will be reporting on the ESMMP implementation supervision

- The consultant ESHS officer be required to generate various reports including production of minutes of monthly site visits and quarterly supervision reports detailing environmental, health, social and safety compliance on quarterly basis amongst other technical aspects

- Reporting on the ESMMP implementation progress and recommendations

### Roles and Responsibilities of the Contractor

- Implementation of the contractor related aspects of the ESMMP and regularly (monthly) reporting

- The contractor on his part will have to appoint an EHS officer and a Social Specialist to coordinate and report on the ESMMP implementation respectively.

- The contractor to engage a Community Liaison Officer to act as a link between the community and the contractor and support the Social Specialist.

- The contractor will also have the obligation of managing the  E&S risks related to his/her  operations.

- Maintaining the required level of stakeholder engagement and communication, including providing project schedule information to the public, accepting and resolving public grievances, advertising and hiring local workers.

- Maintain a working grievance redress mechanism.

- The contractor is to comply with all regulations and by-laws at the county level and other relevant regulations and laws

- The contractor shall refer to ESIA recommendations and the ESMMP when preparing the contractors- ESMMP and the specific plans

- The contractor shall provide water required for use in connection with the works including the work of subcontractors and shall provide temporary storage tanks, if required

- The contractor shall make his own arrangements for sanitary conveniences for his workers. Any arrangements so made shall be in conformity with the public health requirements for such facilities and the contractor shall be solely liable for any infringement of the requirements.

- The contractor shall be responsible for all the actions of any subcontractors whom he subcontracts.

- The contractor shall take all possible precautions to prevent nuisance, inconvenience or injury to the neighboring properties and to the public generally, and shall use proper precaution to ensure the safety of the community

- All work operations which may generate noise, dust, vibrations, or any other discomfort to the workers and/or visitors of the client and the local community must be undertaken with care, with all necessary safety precautions taken.

- The contractor shall take all effort to muffle the noises from his tools, equipment and workmen to not more than 70dBA

- The contractor shall upon completion of working, remove and clear away all plant, rubbish and unused materials and shall leave the whole site in a clean and tidy state to the satisfaction of the Proponent. He shall also remove from the site all waste

- No shrubs, trees, bushes or underground thicket shall be removed except with the express approval of the proponent.

- No blasting shall be permitted without the prior approval of KP and the local authorities.

- Borrow pits will only be allowed to be opened up on receipt of permission from the approving authorities.

- The standard of workmanship shall not be inferior to the Kenya Bureau of Standards where existing. No materials for use in the permanent incorporation into the works shall be used for any temporary works or purpose other than that for which it is provided. Similarly, no material for temporary support may be used for permanent incorporation into the works.

- Disposing of the waste generated during construction activities in accordance to the ESMMP.

- The contractor EHS officer will report on ESMMP implementation during construction period. The aspect to be reported by the contractor will include safety issues i.e. hours worked, recordable incidents and corresponding Root Cause Analysis (lost time incidents, medical treatment cases), first aid cases, incidents and accidents, potential near misses, and remedial and preventive activities required (for example, revised job safety analysis, new or different equipment, skills training etc.); Environmental incidents and near misses; noncompliance incidents with permits and national law; Training on E&S issues (dates, number of trainees, and topics); Details of any security risks; Worker & External stakeholder grievances and E&S inspections by contractor, including any authorities.

Environmental and Social concerns need to be part of the planning and development process and not an afterthought, it is therefore advisable that all the risks and impacts of the project be prevented and mitigated at the earliest opportunity possible to ensure smooth implementation of the project. Finally, a comprehensive Environmental and Social Management and Monitoring Plan (ESMMP) has been prepared and will guide in implementation of mitigation measures.

## Management of Impacts during Operation Phase

The operation phase of the proposed project will be mainly power supply, line maintenance and clearing of wayleaves. A contractor (contracted to run the plant for a number of years before handing over to kp) will be responsible for all the mitigation measures for negative impacts during the operation phase for the first ten years after which responsibility will be KP. This will be done by implementation of the following steps:

- Inspections

- Corrective action

- Reporting

# CHAPTER NINE: CONCLUSIONS AND RECOMMENDATIONS

## Conclusions

During the preparation of this report for the proposed development, it is observed and established that most of the negative social and environmental impacts can be mitigated and have potentially short term low significant effects. The positive impacts are highly rated and will benefit the community at Mkokoni and the county at large. The project proponent, the implementing agency and the contractor must adhere to prudent implementation of the social and environmental management and monitoring plan. The contractor should commit to obtaining all necessary permits and licenses from the relevant authorities and have qualified and adequate personnel to do the project as proposed. The ESIA has proposed adequate safety and health mitigation measures as part of the relevant statutory requirements.

The analysis of the ESIA has demonstrated that the construction and operation of the proposed Solar Mini-grid will have positive impacts to the government and Kenyan society at large. The impacts will include; Increase in reliable and sustainable clean energy, employment to local community members, increase in the national/local investment, increase in government revenue, improvement of standards of living for Mkokoni residents.  However, despite the outlined positive impacts, the proposed development will cause some negative impacts such as; noise, dust generation, soil erosion, oil spills, fire hazards, electrocution, shocks, solid waste generation, occupational health hazards, social risks such as labour influx, demand for resources, gender-based violence, conflicts, public health impacts (HIV & AIDs, Covid 19) among others that need to be avoided, reduced and mitigated against.

It is the duty of NEMA to consider licensing the project subject to EIA study; in accordance with the Environmental Management and Coordination Act, EMCA of 1999 and its Amendment, 2015 and the Environmental Impact Assessment and Audit Regulations, Legal Notice No. 101 of 2003.

An Environmental and Socio- economic Management Plan (E&SMP) outline has been developed to ensure sustainability of the project area activities from construction through operation to decommissioning. The plan provides a general outlay of the activities, associated impacts, mitigation action plans and appropriate monitorable indicators. Implementation timeframes and responsibilities are defined, and where practicable, the cost estimates for recommended measures are also provided.

A monitoring plan that highlights some of the environmental performance indicators that should be monitored has been developed. Monitoring creates possibilities to call to attention changes and problems in environmental quality. It involves the continuous or periodic review of operational and maintenance activities to determine the effectiveness of recommended mitigation measures. Consequently, trends in environmental degradation or improvement can be established, and previously unforeseen impacts can be identified, or pre-empted and mitigation measures proposed.

From the findings of this study, the following conclusions are made:

- The proposed project will generate socio-economic benefits which would not be realized if the ‘NO development option’’ is considered.

- The beneficiary community has been consulted among other stakeholders and project information shared including the negative impacts and the views of the stakeholders is that the project is long overdue.

- The potential adverse impacts associated with the proposed project are possible to mitigate successfully. The impacts before implementation of mitigation measures are assessed as very low to medium low and the ratings are expected to improve further with the implementation of the proposed mitigation measures

- The impacts that will be adverse will be temporary during the construction phase and can be managed to acceptable levels with the implementation of the recommendation of the mitigation measures for the project.

- The project will be designed, constructed, and operated according to the acceptable industry norms and standards. Successful implementation of the proposed ESMMP will ensure environmental sustainability

The proposed project design has integrated mitigation measures with a view to ensuring compliance with all the applicable laws and procedures. The Solar Mini-grid and associated structures will be installed to the required planning/architectural/structural designs and standards. During project implementation, operation and decommissioning stages sustainable environmental management would be ensured; avoiding inadequate use of natural resources, conserving nature sensitively and guaranteeing a respectful and fair treatment of all people working on the project, general public at the vicinity and the expected PAPs of the project.

In relation to the proposed mitigation measures that will be incorporated during construction, operational and decommissioning phases; the development’s input to the society and environment; the project is considered beneficial and important.

## Recommendations

It is strongly recommended that a concerted effort is made by the implementing agency in particular, to implement the Environmental Social Management and Monitoring Plan provided herein. Following the commissioning of the project, statutory Environmental and Safety Audits shall be carried out in compliance with the national legal requirements, and the environmental performance of the site operations should be evaluated against the recommended measures and targets laid out in this report.

Recommendations

- The KP and the contractor must adhere to relevant legal and regulatory framework to ensure compliance and success of the project

- Adherence to the mitigation measures as spelt out in the ESMMP and monitoring of the same is mandatory to ensure environmental and social sustainability of the project.

- Cultivate and maintain a good working relationship with the community members

- Ensure social inclusion of the vulnerable groups by paying attention to the most vulnerable and provide ready boards as spelt out

- Contractor to plant trees in construction phase to promote environmental sustainability

- Stakeholder engagement to the carried out throughout the construction and operation and decommissioning phases.

- Contractor to ensure grievance redress mechanism is established and operational

- Environmental Audits should be carried annually or as prescribed by the Authority during the operational phase and invitation of Inspectors and Experts from NEMA to ascertain compliance with the provided ESMMP and set NEMA regulations and Standards.

- Diligence on the part of the contractor and proper supervision by the KP is crucial for mitigating the potential impacts and ensuring structural strength, safety, and efficient operation of the project.

Authorization Opinion

In terms of NEMA requirement the environmental practitioner is required to provide an opinion as to whether the activity should or should not be authorized. The expert is reticent to venture such an opinion since we are not an elected entity mandated to make decisions on behalf of authority. Nevertheless, in this section a qualified opinion is ventured and in this regard the Lead expert believes that sufficient information is available for NEMA to take a decision. The fundamental decision is whether to allow development which brings socio-economic advantages and is consistent with planning and certain development and social responsibility and upliftment of policies, but which may impact on an area as a result of negative impacts identified. The Lead Expert believes that the ESIA have shown that the applicant’s preferred alternative and technological alternatives are generally acceptable. The ESIA has also assisted in the identification of essential mitigation measures that will mitigate the impacts associated with the project to within acceptable limits.

In conclusion, the expert is of the opinion that on purely ‘environmental’ grounds (i.e., the project’s potential socio-economic and biophysical implications) the application as it is currently articulated in the applicant’s proposal should be approved provided the essential mitigation measures are implemented. It is in the opinion of the Environmental Consultant that the anticipated negative impacts can be readily and effectively mitigated and the proposed project does not pose any significant threat to the Environment and may be licensed to proceed

# APPENDICES

| No | Appendix | Item |
| --- | --- | --- |
| 1 | Appendix 1 | Minutes & list of EIA consultation meeting |
| 2 | Appendix 2 | FGD lists |
| 3 | Appendix 3 | Minutes of Land acquisition meeting |
| 4 | Appendix 4 | Land identification form |
| 6 | Appendix 5 | Firm and Lead expert EIA practising licences |

## Appendix 1 – Minutes of the ESIA meeting and the attendance list

### Minutes of the ESIA meeting

| MINUTES OF EIA CONSULTATION HELD AT MKOKONI, LAMU COUNTY |  |
| --- | --- |
| Date: 30th SEPTEMBER 2021 Venue: Mkokoni | Time: 1428HRS |

PRESENT List of attendants is appended herein.

AGENDA - Introduction - Opening Remarks - Remarks by the consultant - Concerns/Issues from participants - Responses to the issues raised - Acceptance/rejection of the proposed project - Adjournment

| Item No | Description | Action by |
| --- | --- | --- |
| Min 1/21 | Introduction |  |
| 1.1 1.2 | The meeting was opened by a word of prayer from Ustadh The assistant chief welcomed the guests to the island. He thanked the locals for attending the meeting and welcomed the CREO Mr. George. | Ustadh Assistant Chief |
| Min 2/21 | Opening Remarks |  |
| 2.1 2.2 | George explained the project to everyone in the meeting. He explains the compensatory project for the land that was set aside for the project. Mark explained the compensatory project further stating that it will come from one of three areas which are health, water or education. The project cost should also be equal to or less than 1 million Kenya Shillings. The project should also be within a 10km radius from the mini grid. | George Ofula-CREO Mark Oyier-MOE |
| Min 3/21 | Remarks by the consultant |  |
| 3.1 3.2 3.3 | Lavina introduced the consultant from Norken International and Centric Africa and counterparts from the ministry and Kenya Power. Henry explained the ESIA process and public participation which is a requirement by the law. He then listed the benefits of the project and some of the anticipated negative environmental and social impacts. Pius explained there will be no compensation for any trees cut along the way of the power. He also added the connection fee of the electricity was 1000 Kenya Shillings after which tokens will be paid depending on the household usage. The wiring and meter box will also be on one’s cost. | Lavina Omondi Henry Karanja Pius Nyaga-Kenya Power |
| Min 4/21 | Concerns / Issues from participants |  |
| 4.1 4.2 | Ahmed Mohamed was concerned on the Stakeholder Fatigue that the Mkokoni community has experienced. Many different teams have visited the site and the project is yet to commence. He asked for transparency from the consultants. Salma Mohamed welcomed the project highly. He was concerned whether to choose a CPR that is not among the provided sectors. Shali Mohamed was concerned on what will happen when battery/diesel will end. | Ahmed Mohamed Shali Mohamed |
| Min 5/21 | Responses to concerns/issues raised |  |
| 5.1 5.2 | On stakeholder fatigue, the 1st meeting was to explain the project to the residents, 2nd meeting was for the land acquisition process and the 3rd meeting was for ESIA process. The project will start once the report is approved by NEMA and a license is issued and contractor bidding is completed. The locals should be patient. In addition to the above responses, the team assured the community that; The contractor will not come with all the workers needed to work at the project site, unskilled labour will be sourced from the locals for example digging holes, cooking food for those working. However, not all the youths in the area will get jobs since it’s a small project. The connection fee will be 1000 Kenyan Shillings and the wiring will be on one’s cost and should be done by a professional. Tokens will then be paid after connection and work like mobile airtime and depend on one’s usage. The site will be guarded at all times. There will be no compensation for any trees cut to make way for the poles. The Mini grid will have a back-up generator for days when the sun is not enough. | Lavina The study Team |
| Min 6/21 | Acceptance/Rejection of the project |  |
| 6.1 | All the members present accepted and welcomed the project | All |
| Min 7/21 | Adjournment |  |
| 7.1 | The meeting was adjourned at 5: 58pm by the assistant chief and members proceeded to the focus group discussions | Assistant Chief |
| Minutes Prepared By: …NGUGI SHARON WATIRI………………………………….. Date…30/9/2021…………….. Minutes Confirmed By: - MUSTAFA SHEE Date……30/9/2021… Assistant Chief - ………………..………………………… Date……………… |  |  |

### The Public Participation List of attendance

### FGD Lists

Male FGD List

Women FGD List

Youth FGD List

## Appendix 2: Minutes Of Community Consultation Meeting Leading To Voluntary Land Acquisition and GRC Constitution

MINUTES OF COMMUNITY CONSULTATION MEETING LEADING TO VOLUNTARY LAND ACQUISITION AND GRC CONSTITUTION HELD ON 23/09/2020 AT MKOKONI VILLAGE

Min: 1 Agenda:

- Preliminaries

- Project design

- Land acquisition consultations

- Positive and Negative impacts of the proposed project /mitigation measures

- Way forward

- A.O.

Min 2 Meeting Preliminaries

The meeting started at 11.12am with a word of prayer from an elder. Village Headman (Ahmed Mohamed) then welcomed members present and then requested Ward administrator Mr Jamal Fumo to do the introduction part to the visitors. He welcomed the team from MoE, KPLC, REREC and Lamu county government in a special way, he further welcomed the community members present for attending the developmental meeting in the community. He further emphasized the importance of having electricity in their community since it will improve their standards. The ward Admin thanked the visitors for finding time to come and share with the community details about the project, its economic benefits, electricity connection procedures and land requirements. He said the community was open to any project that was meant to uplift their livelihoods and their way of life stressing that the area was greatly undeveloped. For many years the community had been yearning for electricity and that it was by the grace of God that this was about to be realised. The Ward Admin   then invited the County Renewable Energy Officer (Mr. George Otula) to address the community and then introduce the visitors to address the Baraza.

Min 3. Introduction of the Project Implementation Unit Team (PIU)

Samuel Abaya thanked all community members present and went on introducing team members from MoE, KPLC, REREC and Lamu county government. He in turn invited Eng. Zadock to take members through the project design after the introduction. The visiting team introduced themselves as following;

- Irene Maina			- Wayleaves Officer - KPLC

- Samuel Abaya 		- Social Safeguards Officer - KPLC

- Simon Mwangangi 		- Environmental Officer - KPLC

- Joseph Korir	 	 	- Surveyor – KPLC

- Samwel Olela			- Environmental Officer – REREC

- Eng Zadock Rotich 		- Engineer – KPLC

- Dorothy Kagweria 		- Ministry of Energy

- Bernard Kataka 		- Manager – Lamu, KPLC

Min. 4 Project Design

Eng. Zadock – explained to the meeting that the government of Kenya through vision 2030 is planning that every household should be connected with power hence the government has come up with this project called Kenya off Grid Solar Access Project (KOSAP) that is meant to connect Kenyans in the rural areas which are far from the national grid. This project is being implemented in the 14 counties where Lamu is one of them and the process of starting the project has commenced in other counties. He further noted the proposed project will have solar panels, small diesel generator, control room, distribution lines to various homesteads. The project is being funded by the World Bank and the government of Kenya.

Engineer (Zadock Rotich – KPLC). The mini grids will entail the installation of solar PV, battery storage and thermal diesel units.  All electricity consumers supplied through mini grids will be KPLC customers, and pay the same tariff for each category charged to users connected to the national grid. In Lamu County, 3 mini grid sites had been identified. One of this project sites is Mkokoni where a given number of potential households had been mapped for connection. The main purpose of the Baraza was to consult and engage the community in land acquisition process for the mini grid and the establishment of a grievance resolution committee. He further explained that the land acquired will be used to erect a powerhouse comprising solar panels, diesel generator, batteries and inverters.

Zadock continued to explain that households will pay Kenya Shillings One Thousand (Kshs. 1,000.00) as connection fees. KPLC will also be involved in metering of the power to the various consumers. Wiring of premises and households is the responsibility of the Premise/Household owner. However, owners should ensure that wiring is done by a certified technician who should also provide them with a wiring certificate after completion.

Payment of electricity will be done through a pre-paid meter token system. This ‘pay as you go” mechanism will entail purchases of tokens through a vendor or directly purchasing and paying through the mobile. He then welcomed the Manager KPLC-Lamu County to speak to the gathering

Manager – Lamu (Bernard Kataka) addressed the occasion and mention that he has been in Lamu since the year 2015, mentioned few power generation that has been done in the county e.g Mpeketoni, Mokowe and Faza. He explained that each household will be connected to power and the payment has been reduce from the current rate of Kshs 15K to 1K being the connection fee. He also explained that power is not all about switching but usage. The wiring should be done by a qualified person

Min 5 Land acquisition process

The Surveyor, Mr Joseph Korir told the Baraza that the land required for the construction of the Mini grid is 0.42094. He said that the main purpose of the Baraza was to seek community consent for land acquisition for the project. He revealed that there are three land ownership categories in Kenya which are Community land, Private land and Public land. The Surveyor informed the meeting of the following criteria to be used in regard land donation.

The team Surveyor Joseph Korir told the meeting that the team appreciated the time they took to come for the meeting to discuss the project. He informed the meeting that the projects would be implemented in 14 counties in the country. He said Lamu is the county in which the project is being implemented. Mr. Korir explained to the meeting that the project could only commence once the project proponent acquires land where the project will be constructed.

Mr. Korir confirmed to the community present that land is both a social and economic factor of life. The land for the community has been inherited through generation. He also said that the land within the community is categorized as community land. Further confirmation of the same will be carried out during the acquisition process. He explained to the gathering that he would map out the land donated. The project he said required a minimum of 2 (two) acres.  He said that since the town is expanding due to the increasing population a minimum 2 acres will be sufficient, however, to be able to cater for the increasing population, the community can  consider donating 5 (five) acres  of land. The Surveyor asked the meeting if it was the first time they had heard about the project. The members of the community confirmed that a team had visited the town some time earlier regarding this said project.

Mr. Korir explained to the gathering that the team that had previously come to their area was a team of consultants. The members present confirmed the same and that they had shown them the site of the proposed mini grid. He told them that the team that had come previously were consultants who had come to view the land. He further said that he was the surveyor of the team and would take the coordinates of the land to commence the land acquisition process. He further explained that he would then prepare a sketch map of the land and forward the same to the County Government for approval. Once the county approved the scheme it would be forwarded to the National Land Commission for approval and the process of preparation of a letter of allotment. The meeting was told that the title would finally be in the name of Kenya Power and Lightening Company (KPLC). Mr. Korir then welcomed the Mr. Abaya speak to the community.

Min 6.  Community rights and entitlements

Mr. Abaya explained to the community that even though they had donated the land, it was necessary that we disclosed to the community that they were also entitled to compensation. He further explained to the gathering the options that they are entitled to. The first thing was that the community may have donated the land but are entitled to compensation for the land. This Compensation monies would however be held on their behalf in an escrow account by the County, and the monies plus accrued interest released to them upon registration.

The other option of compensation explained to the community was that the community can also be compensated in kind. The community can request for compensation in kind like a well, or classrooms to be built or any other item that will benefit the community.

Another option would be compensation of land for land. The community may request the Government to buy a similar piece of land for the community. To compensate for land donated for construction of the mini grid. He informed the meeting that they are at liberty to deliberate on the options given and they should not feel coerced to donate the land for the project. With the remarks made he once again thanked the community for supporting the project.

At this point the community members through their leadership agreed to donate land freely without being given back any form of compensation options as mentioned above. He further noted that the proposed project will benefit the community more than anything else.

Min 7: Positive and Negative impacts of the proposed project /mitigation measures

The Team Environmental and Social Expert Simon Mwangangi and Samuel Abaya explained to the meeting once again for listening to the input of all the Team members. Mr. Samuel told the meeting that a list of attendance would be circulated where all present would write their names and sign the form. They were informed that minutes would be taken as we proceeded with the meeting.

Samuel told the gathering that it was important that there be consensus for the land donated. He said the team was ready and open to discuss any issue or dissenting voices regarding the land donated for the project.

Mr. Simon explained to the meeting that another meeting will be held for Environmental and Social Impact Assessment for the proposed site which will be submitted to the National Environmental and Management Authority (NEMA) for review. NEMA officers will undertake site visits to inspect and confirm that an Environmental and Social Impact Assessment had been done on the project and assess the community engagement with the proposed project. Subsequent to this the Contractor would then commence the construction of the mini grid.

Simon then told the meeting that he would give them both the positives and the negatives impacts of the project.  He began with the benefits. He said, the community would enjoy light from electricity and each household connected will no longer need to use paraffin lamps to light their homes. Electricity will be generally cheaper that the use of paraffin for lighting.   Electricity will benefit school going children.

The community will also enjoy power for security lights at night. This will enhance security within the community at night. He further told the community that there may be members in the community who would love to buy televisions. Televisions will be a good source of entertainment and information of current affairs both locally and internationally. With electricity some community members will start businesses, the youth will open Barber shops.

Samuel also told the gathering that the project will come with employment opportunities for the community. This will be in the category of skilled and semi-skilled and unskilled jobs. The project will give priority to the locals for employment opportunities, and especially for unskilled positions. The works will be for masons, electricians when the contractor begins the construction. The work will be available for Men, Women and the youth. The rates payable will be agreed with the contractor but in line with the labour act. The Women will have an opportunity to sell tea, chapatti and food to the workers who will be working on the site of the mini grid.

The Contractor will also buy building materials like sand, gravel, stones and cement from the local community. Materials that will be available within the community for sale will be purchased by the contractor. Some materials like solar panels will be imported for the project.

The local Health Centre will also be supplied with electricity at an affordable cost. This will be a benefit in that the dispensary will now be able to refrigerate medicines that require being stored in cool places for patients. Laboratory and Pharmacy services will be more efficient for the community.

Mr. Simon told the meeting that every project has both positives and negatives effects. He went further to explain the negative aspects of the project. He said the project will involve non-local people coming to work on the site. This means that the non-locals may come with habits that are not culturally acceptable to the community. The workers may walk around the sites without shirts and in shorts. This may be unacceptable behaviour to the community. If the community have rules, they wish to have adhered to, the contractor will hold inductions for all his workers to understand and adhere to cultural standards.

The community will also experience noise pollution during the construction period the noise will be from excavation, drilling and vehicles driving to and from the site. This will be for just a while. The contractor will be limited to working from 8am to 5pm to control the noise. Samuel acknowledged that water is scarce in this area. He said that the contractor will require water from the locals to carry out the construction of the project. This will be an inconvenience for a while.

Dust pollution will also emerge from the site. The contractor will mitigate this by the use of tackifiers and soil stabilizers to reduce the dust. The vehicles may at times be driven at a high speed when transporting materials. The introduction of bumps will be used to control the speed of the vehicles. During construction of the project, the community may have trees on the donated land. In case the land has trees, they will be cut and cleared for the project. However, the contractor will plant trees to replace the ones cut and plant additional trees for the community on the site.

Accidents may occur during this period too. For example, a worker could get injured by a stone falling on them or hammer injuring a worker. The contractor will ensure that all workers wear a helmet, gloves, overall and safety boots at all times when on site. If a worker is found without any of the safety gear, he will be dismissed from the site on the spot. In case of any injury to the workers the Contractor will bear the responsibility for the staff. The contractor will give all the workers the regulations they must abide to while at work.

Samuel also talked about Gender Based Violence as an issue that needed to be mentioned. He said if a man got a job on site and is paid his wages, his wife may demand money knowing that he has been paid. This also applies in vice versa. The woman may work, and the husband may demand money from the wages paid. If one spouse does not cooperate, the consequence could lead to violence in the home.

Another negative may occur when the women are employed on the site or cook for the workers, they may be sexually harassed or sexually abused. Such cases must be reported. HIV AIDS is also a disadvantage. The risk to this exposure is real and members of the community and workers should be aware since everyone is vulnerable.

Child labour is also a negative activity that will not be condoned. A worker may wish to get additional money by bringing in a child to assist in his work. Such a situation will not be accepted.

Electricity as a source of energy can also be dangerous. Children may play around with nails in the sockets in the house. This can cause electrocution. When trying to save such a child, one may be bare footed and become a path for the electricity and get injured. The power poles can also be a curious object for the youth to climb risking their lives by falling from the poles. Precautions need to be taken where children and the community warned on the dangers of electricity. With all the disadvantages the meeting was told that there will be a solution for all the issues.

Samuel then told the meeting that to address grievances, the team will require that a Grievance Redress Mechanism to be put in place by the community. This GRM will have a committee that will help solve the grievances arising from the project. The community will need to identify persons who will sit on the committee and they should comprise a man, woman, youth and a person representing the special group e.g a person living with a disability. The Committee will help address grievances to their conclusion. If in any case the committee is unable to solve an issue, they will be guided by the implementing agency on where to forward the matter. If it is still not solved at that level, then the Kenyan Courts will be used to resolve the issue. He said it is our hope that the grievances will be solved at the local level. The meeting was also told that the members of the Committee will be required to volunteer their services. This is because there will be no payment for their services.

Min. 8 Grievance Resolution Mechanism (GRM)

Mr. Samuel Abaya informed the Baraza on the need for constitution of a locational Grievance Resolution Committee (GRC) for purposes of resolving any grievances that may arise in the lifetime of the project as guided by project frameworks. The local GRC will be the first stop shop for resolution of project related disputes and grievances for project affected persons and interested parties. The GRM should be culturally appropriate, inclusive, and accessible and developed in consultation with the community. Grievances which cannot be resolved by the local GRC shall be escalated to the sub-county GRC and the National GRC respectively. Any unresolved matter can then be referred for arbitration or to a court of law. World Bank’s GRS is also available to stakeholders to lodge their grievances. The GRC should constitute representation from all genders, youth and vulnerable persons. It should be structured in such a way that it provides multiple channels for lodging grievances, ensure anonymity and confidentiality. The following details shall be recorded for each grievance reported; and a close-out form issued to indicate the grievance registered has been closed.

- Date of compliant

- Name of complainant

- ID of complainant

- Telephone contact of complainant

- Nature of complaint

- Name of the Person handling the complaint

- Contacts of person addressing the complaint

- Action taken

- Date of conclusion of complaint

The community nominated the following as members of the GRC:

| No | Name | DESGN. | ID No. |
| --- | --- | --- | --- |
| 1 | Atik Mohamed Atik | Chief | 8520863 |
| 2 | Ali Hassan Ali | Youth | 37927463 |
| 3 | Khadija Mohamed Aboud | Pwd | 34412469 |
| 4 | Ahmed Mohamed | Elder | 2238916 |
| 6 | Salma Mohamed | Women | 20346195 |
| 7 | Baraki Mbwana Athman | Religious leader | 2238845 |

Samuel then concluded by thanking the community for their attention and said we would move to a question and answer session. He also told the meeting that Dorothy a member of the team would meanwhile hold a separate meeting with the girls and women to allow them to also speak their minds and ask questions freely away from the men.

Way Forward

Members present welcomed the project and requested that it be implemented the soonest possible so that their problems of staying without electrical power gets sorted once and for all. They further agreed that the land they are giving for the proposed project is a donation and no any form of compensation will be demanded by the community.

Minute 9: A.O.B

Five community members were identified to sign land donation form on behalf of the community.

Minute 10: Closure of meeting

There being no other business, the Chairperson thanked all the attendants for turning up and their contributions.  Members agreed to keep in touch and clarify on any necessary information as regards the intended projects. The meeting ended with a closing prayer at 13:20 p.m.

PLENARY SESSION

| QUESTION/COMMENTS | ANSWER/REMARKS |
| --- | --- |
| Ali Azwaj Appreciate the implementation and welcomed the project in the area. | Abaya The project implementation will be done as per the requirement of the Government, the community to agree on the project implementation since the project has limited time. |
| Lali Abubakari “How long will we wait for the implementation” Incase of delay in the implementation, if the community gets another project the land will be given out. | Zadock The implementation will be done after tendering, what remains is land acquisition. Manager – Kplc lamu Land donation and community partnership needed for the implementation of the project. The land will be transferred to KPLC Ward admin – Fumo Land donations remains on the community |
| Mohmoud What benefit will we gain by donating the land in kind? How much is the connection fee? | Irene Connection fee is 1k compared to other communities paying 15k. There is no compensation for land donation. |
| Fesuol monte There is no compensation yet the money is from world bank, how will the youths benefit? In case kplc moved the site to another area, can the land be used for another project? | Manager – Kplc lamu The community will be employed in the project works through the skilled and unskilled jobs, the power plant will not be moved to another area that’s why KPLC will do the transfer of land to enable them secure the site. |

FOCUSSED GROUP DISCUSSIONS

The social system amongst the communities is dominantly patriarchal, in which power, leadership, moral authority and control of property are vested in males. Clan-based culture and religion drives this strict male hierarchy and authority. Women, girls and youth roles in society are thus limited as is their decision-making powers. At the apex of the community is the clan and beneath it the elders, below them lies the Male family heads, then their wives and male children. Female children lie at the bottom of society. Due to this cultural set-up of power in the community, when elders, women and youth  are placed together in same meeting some group members may shy away from expressing their views. It is for this reason that, during the course of the Baraza the environmental/social specialist called for separate meetings between the different stakeholders (Women, Youth and elders) in an attempt to allow them to freely express their hopes, fears, aspirations and expectations in relation to the mini grid and the project as a whole. Whereas all the groups expressed their unreserved support for land donation to the project, the following were noted as the main concerns/issues:

Focus Group Discussion with the men

A focus group discussion was held with the men. The main objective of this discussion was to assess whether the men had understood the project and its requirements and to provide them an opportunity to air their issues/give their opinions on the project.  Samuel gave a summary of the project and its requirements again just to keep them abreast of the issues discussed in the public forum. He then asked the men whether they agree to the donation of community land to the project. The men said they support the donation of land for the project. We then allowed for a plenary session to hear their views and question from the men.

| Questions/ comments | Response/ Remarks |
| --- | --- |
| Abu Bakar: How long will the community wait for this project? | Abaya: Currently the project is under preparation stage once the project proponent acquires a piece of land and get the required approvals then the construction will commence. It will roughly take a year tentantively. |
| Bakari Mbwana: What size of land will be required for the proposed mini grid project? | Joseph Korir: If the community can donate 0.411 hectares will be appropriate for the proposed project. |
| Ahmed Mohamed Athman: How far will be the land where the proposed minigrid shall be installed | Eng. Zadock: We recommend the proposed minigrid is constructed next to the settlement for the purpose of ensuring all residents of Mkokoni are connected with power in their households. |
| Mzee Ali: Expressed his gratitude to the government for initiating such project in their community. He further asked who the financials of the proposed project? | Abaya: The KOSAP project is being funded by the World Bank and the government of Kenya |

The men noted the following Levels of involvement in the proposed project namely;

- To do manual work

- Provision of security services

- Provision of local available building materials

- To be consulted regularly

- Assist in dispute resolution

Women

A focus group discussion was held with women. The main objective of this discussion was to assess whether the women had understood the project and its requirements and to provide an opportunity for them to air their issues/give their opinions on the project.

Dorothy (MOE) explained to the women that it was important to hold a separate discussion with them so that they have an opportunity to freely express themselves. She explained the agenda of the visit by the officers from the National and County government was to undertake an environmental and social screening of the proposed site to check for its suitability in terms of environmental, technical, social and health requirements.  The second objective was to undertake community engagement to sensitize the community on the project. The third objective was to explain the land requirements for the project and the need for a project grievance redress mechanism. Dorothy then gave a summary of the project in terms of its positive and negative impacts and their mitigation measures and the requirements for donating land. She also explained the need for the women to select a representative to the project committee who would represent their views/issues to the committee for redress.

The discussion went further to bring out issues on how the women can take advantage of the project benefits rather than taking a back seat. She then explained to them that women would benefit more from the electricity because there are the ones who are more exposed to unclean energy as they are the ones who spend more time in the kitchen. They would also benefit from access to information through use of radios and TV that are powered by electricity enabling them to make informed choices on different issues. They were also set to benefit if they could set up small businesses such as salons, cold drink kiosks, selling frozen blocks to fishermen for fish storage; either individually or in Merry-go round groups in order to uplift their socio-economic status. Children will have time to study and enhanced security   due to the fact that the area will be well lit among other benefits.

Question, Suggestions, feedback and response for Focus Group Discussion with women

| Name of Person making the contribution | Question, Comment, Suggestion | Feedback/Responses by project team |
| --- | --- | --- |
| Ruweiyda Mohamed Mkokoni | -We welcome the project; it will open a lot of business opportunities for us and help those of us with businesses to grow -When should we expect lights to be on in Mkokoni? | -Noted -The implementation is at an advance stage and the contractors should be on site by July 2021 |

Youth

The youth were particularly excited about oncoming mini grid as they anticipated employment opportunities that would accrue during project implementation phase as well as opportunities to establish income generating business ventures upon completion (economic empowerment). They also wanted to know whether the project had a component for training of local youth on electrical installation.

Youth group discussion

### List of Participants

### FGD Lists

Women FGD Lists

Men FGD Lists

Youth FGD Lists

## Appendix 3: Lead Expert’s License

() As per the Energy Act of 2019, this role will now be performed by the Energy and Petroleum Regulatory Authority (EPRA).